## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER/ORGANISATIONAL LEVEL)
FOR
2016/2017 FINANCIAL YEAR

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vision and Mission
3. Departments
4. Municipal Transformation and Organisational Development
5. Basic Service Delivery
6. Local Economic Development
7. Municipal Finance Management and Viability
8. Good Governance and Public Participation
9. Monthly Revenue and Expenditure
10. Monthly Revenue and Expenditure by Vote
11. Capital Cashflow
12. Capital Cashflow by Vote
13. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1) of MFMA states that On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must—
(a) consider the statement or report;
(b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan;
(c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget;
(d) issue any appropriate instructions to the accounting officer to ensure—
(i) that the budget is implemented in accordance with the service delivery
and budget implementation plan; and
(ii) that spending of funds and revenue collection proceed in accordance
with the budget;

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## MTOD
Indicator No | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 16/17 R'000 | Start Date | End Date | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept
4. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
1 | Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2016/2017 financial year by 31 May 2017 | IDP review for 2015/2016 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2017 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2016, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2016 | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | Complete the IDP analysis phase and conduct the IDP representative forum. | Conduct Strategic Planning session and compile the IDP strategic chapter | Draft IDP completed and submitted to Council for adoption by 31 March 2016 | Final IDP submitted to council for adoption by 31 May 2016 | Operational | Operational | Operational | Operational | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM
2 | Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Collect information from departments, Develop a draft SDBIP, Submit to departments for inputs, Incorporate inputs and submit to council for approval by 31 March 2015. Submit to the Mayor for signature, Submit to council for noting. | Makhado Municipality | Income | Operational | 1/4/2016 | 30/6/2017 | N/A | N/A | N/A | SDBIP signed by the Mayor within 28 days after approval of the budget | Operational | Operational | Operational | Operational | Signed SDBIP | MM
3 | Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2017 | 8 | 8 | Quarterly performance reports | Develop a reporting template and send to departments, Receive completed template and consolidate into one report. Organise SDBIP Management meeting to consider the report. Submit the report to Council for approval. | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | 2 (Draft Annual Report 2015/2016 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 | 1 (First Quarter SDBIP performance Report 2016/2017) | 4 (Mid Year Budget and Performance Assessment Report 2016/2076 in terms of section 72 MFMA, Draft and Final Annual Report 2015/2016, Oversight Report 2014/2015) | Third Quarter SDBIP performance Report | Operational | Operational | Operational | Operational | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM
4 | Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2015 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% | Performance agreements | Develop draft performance agreements. Engage the relevant Section 57 Managers. Submit the final performance agreement to Municipal Manager for signing. Submit the signed agreement to MEC for Cooperative Governance Human Settlement and Traditional Affairs. | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | 100% | 100% | 100% | 100% | Operational | Operational | Operational | Operational | Signed Performance Agreements | MM
5 | Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2015 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Write a memorandum for approval of panel members and dates. Invite the participate Conduct assessment and compile assessment report. | Makhado Municipality | Income | Operational | 1/7/2015 | 30/6/2016 | 1 (Annual Assessment 2013/2014) | 1 (Informal Assessment 2014/2015) | 1 (Formal Assessment 2014/2015) | 1 (Informal Assessment 2014/2015) | Operational | Operational | Operational | Operational | Scorecards, Attendance Register | MM
6 | Human Resources and Organizational Development | Invest in human capital | % of municipalities budget actual spent on implementing the WSP 2015/2016 | New Indicator | 0.31% (2596927.18/835130000) | Training inline with the WSP | Spending of budget on training of employees and councillors | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | 0.31% (2596927.18/835130000) |  |  | Operational | Operational | Section 71 reports | CORP
7 | Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2017 | Draft Organogram 2015/2016 | Approved Organogram by May 2017 | Organogram review | Reviewing of organizational structure | Makhado Municipality | Income | Operational | 1/7/2015 | 30/6/2016 | N/A | Invite inputs from departments regarding the new organogram | Submit the draft organogram to Council for provisional approval. Consultation with organised labour | Submit the final Draft Organogram to Council for approval | Operational | Operational | Operational | Operational | Invitations to the depts, Minutes and attendance register, Council resolutions, | CORP
8 | Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2017 | 67 employees appointed | 30 | Personnel Recruitment | Personnel Recruitment as per priority list | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | Advertisement of 10 posts (1st bench) | Shortlisting and appoint of the 1st bench post (10) | Advertisement of 20 posts (2nd bench) | Shortlisting and appoint of the 1st bench post (20) | Advertisement and appointment letter |  | Operational | Operational | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP
9 | Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | New Indicator | 8 | Recruitment in terms of EE Plan | Appoint personel at the three highest level following the EE Plan | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | 8 employees |  |  | Operational | Operational | Appointment letters | CORP
10 | Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2017 | 6 events | 6 events | Employee Assistance Campaigns | Organize and present Employee Assistance campaigns for all staff in all regions | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | 2 events | 1 event | 1 event | 2 events |  |  | Operational | Operational | Invitations, attendance registers and close-out report | CORP
11 | Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2017 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Development of 3 outstanding HR policies | Compile Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy and submit to Council for approval- then implement | Makhado Municipality | Income | Operational | 1/7/2016 | 30/6/2017 | Development of 3 draft policies | Submit the draft policies to Council for provisional approval | Submit the draft policies to LLF for consultation | Submit the final darft poicies to Council for approval. (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) |  |  | Operational | Operational | Approved 3 policies and the council resolutions (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP
12 | Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2017 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | 15 awards of bursary | Makhado Municipality | Income | 450000 | 1/7/2016 | 30/6/2017 | Bursary Committee meeting to review External Bursary Policy and procedures | Advertisement for applicants to respond | Award 15 bursaries to qualifying applicants | Bursary committee meeting to evaluate progress | Operational | Operational | Operational | Operational | Advert, List of qualifying leaners and Letters of bursary awards | CORP
13 | Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2017 | 49 events done in 2014/15 | 43 for 2015/16 | Special Programs | Organize and conduct the special programs undertaken in the different desks of the Special Programs Unit | Makhado Municipality | Income | 600000 | 1/7/2016 | 30/6/2017 | 17 | 8 | 12 | 12 | Operational | Operational | Operational | Operational | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP
14 | Spatial and Town Planning | Advance Spatial Planning | To purchase Plan Print Machine for Building Section by 31 March 2017 | Old Machine | Plan Print Machine for Building Section purchased | Plan Print Machine | Purchasing of Plan Print Machine for Building Section | Makhado Municipality | INCOME | 250000 | 1/7/2016 | 31/12/2016 | Develop Specification | Tender advertisement | Supply of machine | N/A | [5 empty] | DEVP
15 | Spatial and Town Planning | Advance Spatial Planning | To finalise the extension of Civic Centre by 31 December 2016 | New bui;lding | Extension of Civic Centre finalized | Extension of Civic Centre | Extension of Civic Centre finalisation | Makhado Municipality | INCOME | 100000 | 1/7/2016 | 31/12/2016 | Extension of civic centre final touches | Extension of civic centre final touches | N/A | N/A | [5 empty] | DEVP
16 | Spatial and Town Planning | Advance Spatial Planning | To finalize the New Disaster centre -Erf 235 30 June 2017 | New bui;lding | New Disaster centre -Erf 235 finalized | New Disaster centre -Erf 235 | Finalise Roofing, Plastering,electrical connection and Plumbing, Tilling,Glazing,installation of doors | Makhado Municipality | INCOME | 500000 | 1/7/2016 | 31/12/2016 | Finalise Roofing | Plastering,electrical connection and Plumbing | Tilling,Glazing,installation of doors | Project completion | [5 empty] | DEVP
17 | Spatial and Town Planning | Advance Spatial Planning | To purchase 18 x Aircons for new offices by 31 March 2017 | New bui;lding | 18 x Aircons for new offices purchased | 18 x Aircons for new offices | Purchasing of 8 x Aircons for new offices | Makhado Municipality | INCOME | 200000 | 1/7/2016 | 31/12/2016 | Coordinate purchasing of aircons | Coordinate purchasing of aircons | Coordinate purchasing of aircons | N/A | [5 empty] | DEVP
18 | Spatial and Town Planning | Advance Spatial Planning | To purchase 2 x Theodolities for Survey Technician by 31 March 2017 |  | 2 x Theodolities for Survey Technician purchased | 2 x Theodolities for Survey Technician | Purchasing 2 x Theodolities for Survey Technician | Makhado Municipality | INCOME | 100.000.00 | 1/7/2016 | 31/12/2016 | Develop Specification | Tender advertisement | Supply of theodolite | N/A
| Spatial and Town Planning | Advance Spatial Planning | Information Recreational Park and Botanical Garden (Phase 2) |  | Information Recreational Park and Botanical Garden (Phase 2) | Information Recreational Park and Botanical Garden (Phase 2) | Information Recreational Park and Botanical Garden (Phase 2) | Makhado Municipality | INCOME | 700000 | 1/7/2016 | 31/12/2016
| Spatial and Town Planning | Advance Spatial Planning | Upgrading of Ayob Motors Traders Market by |  | Ayob Motors Traders Market upgraded | Ayob Motors Traders Market | Upgrading of Ayob Motors Traders Market | Makhado Municipality | INCOME | 300000 | 1/7/2016 | 31/12/2016
19 | Spatial and Town Planning | Advance Spatial Planning | Upgrading of Dzanani Traders Market 30 June 2017 |  | Upgrading of Dzanani Traders Market | Upgrading of Dzanani Traders Market | Upgrading of Dzanani Traders Market | Makhado Municipality | INCOME | 200000 | 1/7/2016 | 31/12/2016 | Develop Specification for designs and erection of market stalls | Tender advertisement | Appointment and commencement with designs | Erection of Market stalls commencement
| Spatial and Town Planning | Advance Spatial Planning | [5 empty] | Makhado Municipality | INCOME
20 | Spatial and Town Planning | Advance Spatial Planning | Development of informal business area Ext 12 by 30 June 2017 |  | Informal business area Ext 12 developed by 30 June 2017 | Development of informal business area |  | Makhado Municipality | INCOME | 3000000 | 1/7/2016 | 30/06/2017 | Design the plans internally. Develop specifications for tender advertisement | Tender advertisement for construction of informal business area for motor mechanics | Appointment and commencement with construction | Construction completed
21 | Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Application received, Site visits, Stand demarcated and compile a report | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). |  |  | Operational | Operational | Site inspection report, Register of applications | DEVP
15 | Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Receive housing queries and attend to them in a form of meetings or written correspondence | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) |  |  | Operational | Operational | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP
22 | Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2015 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Response to applicant in writing | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of building plans assessed/# of building plans received) | 100% (# of building plans assessed/# of building plans received) | 100% (# of building plans assessed/# of building plans received) | 100% (# of building plans assessed/# of building plans received) | Operational | Operational | Operational | Operational | Building plans register | DEVP
23 | Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | Operational | Operational | Operational | Operational | Zoning certificates issued | DEVP
24 | Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | Operational | Operational | Operational | Operational | EXCO resolutions | DEVP
25 | Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) |  |  | Operational | Operational | Site inspection report, Register of applications | DEVP
26 | Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2015 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Operational | Operational | Operational | Operational | Copy of occupancy certificates issued | DEVP
27 | Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Application Assessment Report, Register of applications |  |  | Operational | Operational | Application Assessment Report, Register of applications | DEVP
28 | Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | INCOME | 1000 000 .00 | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) |  |  | Operational | Operational | Application Assessment Report, Register of applications | DEVP
29 | Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | INCOME | Z | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) |  |  | Operational | Operational | Application Assessment Report, Register of applications | DEVP
30 | Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Receive application, Send to MM for approval, Notify the applicants to go and pay, After receiving the proof of payment a venue is booked. | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) |  |  | Operational | Operational | Bookings register | DEVP
31 | Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Receive complaints, Liaise with the commissioner and complainant, Arrange a meeting if need | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2017 | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) |  |  | Operational | Operational | Correspondence letters and emails. | DEVP
32 | Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Conduct inspection, Upon identifying a contravention a notice is issued | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) |  |  | Operational | Operational | Duplicate notices | DEVP
33 | Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2015 | 240 | 240 | Routine Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 60 | 60 | 60 | 12 |  |  | Operational | Operational | Inspection form, Register | DEVP
34 | Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | INCOME | Operational | 1/7/2016 | 30/6/2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) |  |  | Operational | Operational | Inspection form, Register | DEVP
35 | Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2015 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Conduct public consultation on street names. Compile a list of street names for approval by Council. | Makhado Municipality | INCOME | 200000 | 1/7/2016 | 30/6/2017 | Proposed names | Consultations on proposed names. | Draft Street Names | Street names completed for R293 Towns | 200000 | 200000 | Operational | Operational | Expenditure Report | DEVP

## MFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Project Description | Location | Funding Source | Budget 15/16 R'000 | Start Date | End date | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
6. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2017 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Capture spending on capital project. Compile spending report in terms of section 71 report. | Makhado Municipality | INCOME | 163938800.12 | 1/7/2016 | 30/6/2016 | 10% | 40% | 70% | 100% | N/A | N/A | OPEX | OPEX | Quarterly Financial Report | MM and All Directors | 99 | 7539142
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2017 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Capture spending on MIG project. Compile spending report in terms of section 71 report. | Makhado Municipality | INCOME | 112264000 | 1/7/2015 | 30/6/2016 | 10% | 40% | 70% | 100% | N/A | N/A | OPEX | OPEX | Quarterly Financial Report | MM | 100 | 5690000
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2017 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Capture spending on INEP project. Compile spending report in terms of section 71 report. | Makhado Municipality | INCOME | 17000000 | 1/7/2015 | 30/6/2016 | 10% | 40% | 70% | 100% | N/A | N/A | OPEX | OPEX | Quarterly Financial Report | MM | 101 | 0.75473
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2017 | 100% | 100% | FMG | Capture spending on FMG project. Compile spending report in terms of section 71 report. | Makhado Municipality | INCOME | 1600000 | 1/1/2016 | 31/3/2016 | N/A | N/A | 100% (80000) | N/A |  |  | OPEX | OPEX | Expenditure Report | B&T | 102
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2017 | 90% | 90% (308004300) | Revenue Collection | Collection of payment for services such as electricity, property rates, refuse removal | Makhado Municipality | INCOME | 342227123 | 1/7/2015 | 30/6/2016 | 20% | 45% | 70% | 90% |  |  | OPEX | OPEX | Section 71 report (c1 schedule) | B&T | 103
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2017 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Send the policies for inputs by other department. Present the draft review to management. Submit to council for approval. | Makhado Municipality | INCOME | Operational | 1/1/2016 | 30/6/2016 | N/A | N/A | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | Final Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Debts Collection) | N/A | N/A | OPEX | OPEX | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 104
Budget and Reporting | Sound financial management and viability | To table the draft budget to Council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to Council | Draft budget | Collect budget from departments, Consolidate the budget, Present the draft to management, Submit to council for approval | Makhado Municipality | INCOME | Operational | 1/1/2016 | 31/3/2016 | N/A | N/A | Draft budget tabled to council | N/A | N/A | N/A | OPEX | OPEX | Draft budget and Council Resolution | B&T | 105
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2017 | Final budget was submitted to Council | Final budget submitted to Council | Final budget | Take the draft budget for public participation with the IDP. Incorporate inputs and submit the budget for final approval | Makhado Municipality | INCOME | Operational | 1/4/2016 | 31/5/2016 | N/A | N/A | N/A | Final budget | N/A | N/A | OPEX | OPEX | Final budget and Council Resolution | B&T | 106
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Compile the financial statement. Review the compiled financial statement. Present to management meeting. Submit to AG for auditing. | Makhado Municipality | INCOME | Operational | 1/7/2015 | 31/8/2015 | Financial statements compiled and submitted to AG | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Copy of Financial statements | B&T | 107
Budget and Reporting | Sound financial management and viability | # of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Section 71 report submission | Compile the section 71 report. Submit to treasury within 10 days after month end. Submit to council for approval. | Makhado Municipality | INCOME | Operational | 1/7/2015 | 30/6/2016 | 3 | 3 | 3 | 3 | N/A | N/A | OPEX | OPEX | Copy of acknowledgement of receipt by Treasuries | B&T | 108
Supply Chain Management | Sound financial management and viability | To review the Supply Chain Management policy by 30 June 2017 | 2014/ 15 Supply Chain Management policy was reviewed and amended | Supply Chain Management policy reviewed | Supply Chain Management policy | Submit the Supply Chain Management policy to Committee for review | Makhado Municipality | INCOME | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | To submit Supply Chain Management policy to Council for adoption if ther are amendments |  |  |  |  | Council Resolution | B&T | 109
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2017 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Asset Register | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Makhado Municipality | INCOME | Operational | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | N/A | N/A | OPEX | OPEX | Schedules of Asset Register movement | B&T | 110

## LED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 15/16 R'000 | Start Date | End Date | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
7. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Community works programme, Expanded public works programme, Community projects | Makhado Municipality | Income | Operational | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | 600 |  |  | OPEX | OPEX | EPWP, CWP, and Community Projects reports | MM and DEVP | 111
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2016 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Identify the officials to serve Host Makhado annual show | Makhado Municipality | Income | 1200000 | 1/7/2016 | 30/9/2016 | Host official opening and the Three Days Makhado Annual Show. | N/A | N/A | N/A | 168698.7 | 177 977.13.13 | OPEX | OPEX | Annual Show Report and Audited Financial Statements | DEVP | 112
Local Economic Development | Invest in local economy | # of LED projects supported 30th June 2014 | 9 | 6 | LED Strategy | Community works programme, Transnet/Furniture, Rural Farmers (tractor landing), Salaunavhe Poultry farm, Local Builder Training (NHBRC), Dzanani Informal traders facility | Makhado Municipality | Income | Operational | 1/7/2016 | 30/9/2017 | N/A | N/A | N/A | 6 | 100 | Project implementation plan, Project report | OPEX | OPEX | LED strategy implementation report | MM and DEVP | 113

## GGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location | Funding Source | Budget 16/17R'000 | Start Date | End date | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
8. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate Stategic and operational Risk Assessment and review and approval of risk and fraud management policies by 30 June 2017 | Strategic and Operational Risk Assessment Report developed / coordinated and 6 policies, plans and strategies reviewed and approved | 7 risk activities cordinated | Risk Management project | Facilitate and coordinate risk management activities | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | Strategic and Operational Risk Assessment Report developed / coordinated and review and approval of the folllowing policies, plans and strategies: - Risk Management Plan 2016/2017 - Risk Management Policy and Strategy, - Fraud Management Policy - Fraud and Corruption Procedure Manual - Loss Control Policy - Fraud Response Plan developed, | N/A | N/A | OPEX | OPEX | Attendance register, Minutes and Programme | MM | 114
Risk Management | Good governace and Administrative Excellence | Coordinate quarterly Strategic and Operational monitoring risk report | 4 quarterly Strategic and Operational monitoring risk report Coordinated | 4 activities cordinated | Risk Management project | Facilitate and coordinate risk management activities | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | Develop Quarterly Strategic Monitoring Risk Report, | Develop Quarterly Strategic Monitoring Risk Report, | Develop Quarterly Strategic Monitoring Risk Report, | Develop Quarterly Strategic Monitoring Risk Report, |  |  |  |  | Strategic Monitoring Risk Report | MM | 115
Risk Management | Good governace and Administrative Excellence | Coordinate Risk Management Committee meetings | 4 Risk Management Committee meetings held | 4 activities cordinated | Risk Management project | Facilitate and coordinate risk management activities | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | Cordinate1 Risk Management Committee meeting | Cordinate1 Risk Management Committee meeting | Cordinate1 Risk Management Committee meeting | Cordinate1 Risk Management Committee meeting |  |  |  |  | Minutes and Attendance register | MM | 116
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | N/A | N/A | OPEX | OPEX | Case Register | MM | 117
Public Participation | Good governace and Administrative Excellence | To review the public participation by 31 March 2017 | No policy | Public Participation policy reviewed | Public Participation Policy | Review the 2 Public Participation Policy | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | Compile public participation policy and submit to Council for approval of Draft Policy | Conduct public consultation of the draft public participation policy | Submit the final version of the Public Participation Policy to Council for approval | N/A |  |  | OPEX | OPEX | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 118
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 30 June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 38 wards | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | 369,884 | 390,227 | OPEX | OPEX | Minutes, Attendance register, Ward committee quarterly report | CORP | 119
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 6 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool Quarry Pound Street and diverse Financial Hawkers and Market | Makhado Municipality | INCOME | 1/7/2015 | 1/7/2016 | 30/6/2017 | Development of the 6 draft policies | Submit the 6 draft 6 policies to Council for provisional approval | Workshopping of Councillors and Public Participation on draft by laws | Final submission of the 6 policies to Council for final approval and publishing in Provincial Gazette | 900000 | 949000 | OPEX | OPEX | 6 draft policies Council resolution Invitations, attendance registers, Final council resolutions and Promulgation notice for by laws | CORP | 120
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval by 30th June 2015 | N/A | N/A | OPEX | OPEX | Council Resolution, Copy of the plan | MM | 121
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | Approved three (3) year Internal Audit rolling plan and Annual plan | N/A | N/A | OPEX | OPEX | Copy of the plan | MM | 122
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Implementation of the Approved Internal Audit Plan | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | N/A | N/A | OPEX | OPEX | Internal Audit report to Audit and Performance Audit Committee | MM | 123
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2017 | 7 | 7 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | 2 | 1 | 1 | 1 | N/A | N/A | OPEX | OPEX | Minutes, Attendance register, invitations | MM | 124
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2017 | 4 | 4 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | 1 | 1 | 1 | 1 | N/A | N/A | OPEX | OPEX | Council resolution, Attendance register | MM | 125
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 1 | 1 | IAA and APAC Assessment report | Organize IAA and APAC Assessment report and submit to council | Makhado Municipality | INCOME | OPEX | 1/7/2016 | 30/6/2017 | 1 | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Report, Council Resolution | MM | 126
Information Technology | Good governace and Administrative Excellence | Implement automisation of municipal call centre by | Manual system | Computerized call center system | Implement automisation of municipal call centre | Implement automisation of municipal call centre | Civic Center | INCOME | 500000 | 1/7/2016 | 30/6/2017 | Compile specification, call for tender advertisement | Evaluate tenderand appoint service provider | Install and commission the system | Project sign off |  |  | OPEX | OPEX |  | CORP | 127
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 December 2016 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Increase speed of server output to networks for data transfer between workstations and servers | Civic Center and regional offices | INCOME | 100000 | 1/7/2016 | 30/6/2017 | Conduct internal analysis and submit to IMPC | Complile spec and submit to bid committee | Evaluate quatations and allocaye projects | Project sign off |  |  | OPEX | OPEX | Orders, Payment certificate and intallation report | CORP | 128
Information Technology | Good governace and Administrative Excellence | To install server harddrive 31 December 2016 | Phase 1 done | Server harddrive installed | Server harddrive | Upgrade of server harddrives to increase capacity | Civic Center | INCOME | 150000 | 1/7/2016 | 30/6/2017 | Compile specification, call for quatationt | Evaluate quoate and appoint service provider | Install and commission | Project sign off |  |  | OPEX | OPEX | Appointment letter, Project agreement, installation report and payment certicate | CORP | 129
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Upgrade server room | Upgrade of server room by removing carpets and workstation equipment | Civic Center | INCOME | 100000 | 1/7/2016 | 31/12/2016 | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business | Evaluate PINACLE AFRAC'S proposal and decide on the wayforward | N/A | N/A |  |  | OPEX | OPEX | Approved memorandum, Written propoal, wayforward outcomes | CORP | 130
Information Technology | Good governace and Administrative Excellence | To install telephone and computer network infrastructure new offices Civic Center |  | Network infrastructure new offices Civic Center | Network infrastructure new offices Civic Center | Network infrastructure new offices Civic Center |  | INCOME | 230000 | 1/7/2016 | 31/12/2016 | Link of telephone and computer services between Civi centre and new building | Installation of new points and telephone and cables | N/A | N/A | [6 empty] | 140
Information Technology | Good governace and Administrative Excellence | To procure and install the new VEEAM backup server by | Only two telephone points | New VEEAM backup server function | VEEAM backup server | Procure and install the new VEEAM backup server |  | INCOME |  | 1/7/2016 | 30/06/2017 | Compile specification, call for quatation | Evaluate quoate and appoint service provider | Install and commission | Project sign off | [6 empty] | 150
Information Technology | Good governace and Administrative Excellence | To add extra telephone points at Municipal Stores complex |  | Add extra telephone points at Municipal Stores complex | Telephone points at Municipal Stores complex | Telephone points at Municipal Stores complex | Makhado Municipality | INCOME | 200000 | 1/7/2016 | 31/03/2017 | Compile specification, call for quatation from the existing service provider | Deliver install and commission telephone services | Testing and project signed off | N/A | [6 empty] | 151
Information Technology | Good governace and Administrative Excellence | To Implement MCGICTP in the policy, 2015 | No ICT strategy | Implementation MCGICTP, 2015 | Implementation MCGICTP, 2015 | Develop ICT startegy and businesss impact analayasis as pre reruisite for business conituniuty | Makhado Municipality | INCOME | 500000 | 1/7/2016 | 31/03/2017 | Complile specification and call for tender for specicizide services | Evaluate tenders and appoint service provider | Submit ICT strategy to Council forapproval | N/A | [6 empty] | 152
Information Technology | Good governace and Administrative Excellence | Upgrade VIP HR ESS Software (for employee leave application apart from existing VIP Leave module) |  | ESS Software (for employee leave application apart from existing VIP Leave module) | ESS Software (for employee leave application apart from existing VIP Leave module) | Upgrade VIP HR premier to include ESS module | Civic Center | INCOME | 200000 | 1/7/2015 | 31/12/2015 | Call for quatation from existing service provider and get approval to MMM | Implement the module and allow for testing period | Project signed off | N/A |  |  | OPEX | OPEX |  | CORP | 153
Information Technology | Good governace and Administrative Excellence | Replace fixed sound & recording system in Council Chamber |  | Replace fixed sound & recording system in Council Chamber | Replace fixed sound & recording system in Council Chamber | Replace fixed sound & recording system in Council Chamber |  |  | 500000
Information Technology | Good governace and Administrative Excellence | To purchase Laptopa/ Computers, and printers |  | Laptopa/ Computers, and printers purchased | Purchase Laptopa/ Computers, and printers | Purchase Laptopa/ Computers, and printers | Makhado Municipality | INCOME | 400000 | 1/7/2015 | 31/12/2015 | Submit quatations to IMPC and call for quatations | Evaluate quatations and appoint service provider | Dellivery of all equipements | N/A | [6 empty] | 154
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality | INCOME | OPEX | 1/7/2015 | 30/6/2017 | 1 | 1 | 2 | 2 | Operational | Operational | OPEX | OPEX | Minutes, Attendance register, notice of invitations. | CORP | 156
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Makhado Municipality | INCOME | OPEX | 1/7/2015 | 30/6/2017 | 6 | 6 | 6 | 6 | Operational | Operational | OPEX | OPEX | Minutes, Attendance register, notice of invitations. | CORP | 157
Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Reviewed Bathopele service standards | Review the 2014/15 ed Makhado Bathopele Service Standards and submit to Council for approval | Makhado Municipality | INCOME | OPEX | 1/7/2015 | 31/12/2017 | Distribute for comments of all departments | Submit reviewed Service Standards to Council for approval | N/A | N/A | N/A |  | OPEX | OPEX | Approved 2015 Batho Pele Service Standards | CORP | 158
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Comprehensive website policy | Develop website policy for approval by Council | Civic Center | INCOME | OPEX | 1/7/2015 | 31/12/2017 | Submit to Council for approval | Implement website policy | N/A | N/A |  |  | OPEX | OPEX | Council approval of policy | CORP | 159
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality | INCOME | OPEX | 1/7/2015 | 30/6/2017 | 1 | 1 | 1 | 1 | N/A | N/A | OPEX | OPEX | Attendance register and Programme | CORP | 160
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Imbizo Feedback Session | Giving Feedback to community on service delivery issues raised during 2014/2015 financial year | Makhado Municipality | INCOME | OPEX | 1/7/2015 | 30/08/2017 | 1 | N/A | N/A | N/A |  |  | OPEX | OPEX | Attendance register and program | CORP | 170
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework by 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | Income | INCOME | OPEX | 1/7/2015 | 30/08/2017 | 1 | N/A | N/A | N/A |  |  | OPEX | OPEX | Approved Stakeholders management Framework and council resolution | CORP | 180
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | Income | INCOME | OPEX | 1/7/2015 | 30/06/2016 | 1 | N/A | N/A | N/A |  |  | OPEX | OPEX | Approved Communication strategy and council resolution policy and council resolution | CORP | 190
INCOME
INCOME
INCOME

## MRE
LIM344 Makhado - Supporting Table SA25 Budgeted monthly revenue and expenditure
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Revenue By Source
Property rates |  | 3673557.72 | 3680000 | 3742000 | 3630000 | 3945000 | 3845000 | 3512000 | 3412000 | 3658000 | 3223000 | 3460000 | 3861307.7461 | 43641865.4661 | 46693269.4319 | 49119040.5726
Property rates - penalties & collection charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - electricity revenue |  | 24071766.17 | 21432000 | 22490000 | 25600000 | 24758000 | 26456000 | 23071766.17 | 22458700 | 24560000 | 25607000 | 24880000 | 23475961.48 | 288861193.82 | 324101869.02 | 363641872.85
Service charges - water revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - sanitation revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - refuse revenue |  | 818509.38 | 852000 | 812566 | 827000 | 812333 | 818000.38 | 800000.38 | 817000 | 813000 | 814000 | 820000 | 719482.2548 | 9723891.3948 | 10403778.0048 | 10944266.7264
Service charges - other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment |  | 37811.83 | 31000 | 33800 | 37450 | 31000 | 37811.83 | 33000 | 33000 | 34000 | 32900 | 37811.83 | 69618.9118 | 449204.4018 | 480612.4406 | 505580.8158
Interest earned - external investments |  | 276512.41 | 267000 | 288000 | 208000 | 267000.41 | 233000.41 | 254800 | 254000 | 247000 | 245088 | 284500 | 460066.2008 | 3284967.4308 | 3514649.6884 | 3697239.9442
Interest earned - outstanding debtors |  | 1098700 | 1008500.01 | 1058700 | 1021500 | 1050000 | 1087100 | 1040890 | 1008500.01 | 1018500.01 | 880000 | 960001 | 748589.0393 | 11980980.0693 | 12818680.5103 | 13484626.2802
Dividends received |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines |  | 138112.65 | 235000 | 148700 | 162000 | 125800 | 125487 | 104500 | 134560 | 148700 | 139112 | 138112.65 | 40693.9127 | 1640778.2127 | 1755500.0943 | 1846700.4207
Licences and permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agency services |  | 947025.57 | 888000 | 935020 | 900450 | 988002 | 945000 | 780000 | 880555 | 947025.57 | 808000 | 947025.57 | 1284559.9626 | 11250663.6726 | 12037301.0045 | 12662653.1665
Transfers recognised - operational |  | 120000000 | 11600000 | 5000000 | 1920000 | 144000000 | 0 | 0 | 0 | 72490000 | 0 | 0 | 8586000 | 363596000 | 368360000 | 366556000
Other revenue |  | 2540000 | 1800900 | 1013000 | 1374000 | 1450000 | 1178665.19 | 1180000 | 1245000 | 2470000 | 1478090 | 2750000 | -1317953.36 | 17161701.83 | 23652834.42 | 24437350.55
Gains on disposal of PPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue (excluding capital transfers and contributions) |  | 153601995.73 | 41794400.01 | 35521786 | 35680400 | 177427135.41 | 34726064.81 | 30776956.55 | 30243315.01 | 106386225.58 | 33227190 | 34277451.05 | 37928326.1481 | 751591246.2981 | 803818494.6147 | 846895331.3264
Expenditure By Type
Employee related costs |  | 18450000 | 18950000 | 18650000 | 18880000 | 18450000 | 32074000 | 18950000 | 18990000 | 18780000 | 18990000 | 18780000 | 21233438.3 | 241177438.3 | 254442197.44 | 267927633.86
Remuneration of councillors |  | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1559609.73 | 22610107 | 23944103 | 25284973
Debt impairment | [12 empty] | 10000000 | 10000000 | 10550000 | 11109150
Depreciation & asset impairment | [12 empty] | 153426319.32 | 153426319.32 | 161864766.86 | 170443599.52
Finance charges |  | 542000 | 522450.54 | 520286.54 | 534000 | 567000 | 588000 | 521000 | 532000 | 519000 | 520286.54 | 520286.54 | 294693.9451 | 6181004.1051 | 6613174.9204 | 6956737.2584
Bulk purchases |  | 18078244.34 | 18178000.34 | 18757000.34 | 17654000 | 16000000 | 16800000 | 17870000 | 18978244.34 | 19078244.34 | 17078888.34 | 19078067.34 | 19388242.9 | 216938932.28 | 247831036.2 | 283122175.81
Other materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other expenditure |  | 14362465.24 | 14150000 | 11780007 | 14508780 | 11458700 | 11420000 | 14345600 | 14362111 | 14300000.24 | 14362465.24 | 11120000.24 | 38625885.9515 | 184796014.9115 | 187462607.21 | 197656659.4415
Loss on disposal of PPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditure |  | 53346391.15 | 53714132.45 | 51620975.45 | 53490461.57 | 48389381.57 | 62795681.57 | 53600281.57 | 54776036.91 | 54590926.15 | 52865321.69 | 51412035.69 | 244528190.1466 | 835129815.9166 | 892707885.6305 | 962500928.8899
Surplus/(Deficit) |  | 100255604.58 | -11919732.44 | -16099189.45 | -17810061.57 | 129037753.84 | -28069616.76 | -22823325.02 | -24532721.9 | 51795299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | -83538569.6185 | -88889391.0158 | -115605597.5635
Transfers recognised - capital |  | 0 | 0 | 0 | 4590000 | 43609000 | 5780000 | 1190000 | 0 | 74095000 | 0 | 0 | 0 | 129264000 | 136892000 | 143831000
Contributions recognised - capital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contributed assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surplus/(Deficit) after capital transfers & contributions |  | 100255604.58 | -11919732.44 | -16099189.45 | -13220061.57 | 172646753.84 | -22289616.76 | -21633325.02 | -24532721.9 | 125890299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | 45725430.3815 | 48002608.9842 | 28225402.4365
Taxation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attributable to minorities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surplus/(Deficit) | 1 | 100255604.58 | -11919732.44 | -16099189.45 | -13220061.57 | 172646753.84 | -22289616.76 | -21633325.02 | -24532721.9 | 125890299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | 45725430.3815 | 48002608.9842 | 28225402.4365

## MREBV
LIM344 Makhado - Supporting Table SA26 Budgeted monthly revenue and expenditure (municipal vote)
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Revenue by Vote
Vote 1 - EXECUTIVE AND COUNCIL |  | 38956700 | 38908000 | 38908000 | 36978000 | 39067000 | 39890000 | 38078000 | 39112000 | 38867300 | 39050400 | 39050400 | 41739367.21 | 468605167.21 | 485863021.7 | 490454136.4
Vote 2 - WASTE MANAGEMENT |  | 450000 | 470000 | 610000 | 650000 | 655000 | 553000 | 557800 | 556000 | 520000 | 510000 | 513000 | 632510.02 | 6677310.02 | 5636338.37 | 5935296.93
Vote 3 - ROAD TRANSPORT |  | 998000 | 994000 | 950000 | 990000 | 1100000 | 1007000 | 1209800 | 1220000 | 1250000 | 1290000 | 1085000 | 923294 | 13017094 | 13733034.18 | 14460884.96
Vote 4 - WATER | [12 empty] | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | 26789000 | 25785600 | 24560900 | 24112000 | 23456700 | 25489000 | 24345000 | 25489000 | 25008000 | 25602300 | 26908000 | 28320378.27 | 305865878.27 | 344107515.42 | 383648632.32
Vote 6 - CORPORATE SERVICES |  | 3909800 | 3921100 | 4825000 | 4709800 | 4712300 | 3867000 | 4175000 | 4189000 | 4170000 | 4187000 | 4186000 | 3218441.76 | 50070441.76 | 52824316.04 | 55624004.81
Vote 7 - PLANNING AND DEVELOPMENT |  | 10000 | 20000 | 30000 | 40000 | 41000 | 43000 | 44000 | 46000 | 47000 | 56000 | 57000 | 56926.51 | 490926.51 | 517927.46 | 545377.61
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | 7000 | 5000 | 7000 | 7000 | 8000 | 9000 | 10000 | 8000 | 8000 | 6000 | 7000 | 9585.47 | 91585.47 | 96622.66 | 101743.67
Vote 9 - HOUSING |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 591.61 | 55591.61 | 58649.16 | 61757.56
Vote 10 - OTHER | [12 empty] | 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION |  | 5000 | 8000 | 6000 | 8000 | 7000 | 8000 | 6000 | 8000 | 7000 | 8000 | 6000 | 7094.18 | 84094.18 | 88719.38 | 93421.5
Vote 12 - BUDGET AND TREASURY |  | 2890000 | 2720000 | 2691000 | 2799000 | 2891000 | 2946000 | 2965000 | 2978000 | 2989000 | 3130000 | 3590000 | 3308157.29 | 35897157.29 | 37784350.92 | 39801075.5
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
Total Revenue by Vote |  | 74020500 | 33928700 | 72592900 | 70298800 | 71943000 | 73817000 | 71395600 | 73611000 | 72871300 | 73844700 | 75407400 | 78216346.32 | 880855246.32 | 940710495.29 | 990726331.26
Expenditure by Vote to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL |  |  | 10000000 | 5000000 | 1920000 |  | 0 | 0 | 0 | 76076000 | 0 | 0 | 12775721.33 | 105771721.33 | 104679593.11 | 109734952.2
Vote 2 - WASTE MANAGEMENT |  | 818509.38 | 852000 | 812566 | 827000 | 812333 | 818000.38 | 800000.38 | 817000 | 813000 | 814000 | 820000 | 13630577.92 | 22634987.06 | 23879911.34 | 25145546.65
Vote 3 - ROAD TRANSPORT | [12 empty] | 25228755.48 | 25228755.48 | 26616336.99 | 28027002.87
Vote 4 - WATER | [12 empty] | 19079906.12 | 19079906.12 | 20129300.97 | 21196153.92
Vote 5 - ELECTRICITY |  | 24071766.17 | 21432000 | 22490000 | 25600000 | 24758000 | 26456000 | 23071766.17 | 22458700 | 24560000 | 25607000 | 24880000 | 5429955.24 | 270815187.58 | 304670485.66 | 342974115.91
Vote 6 - CORPORATE SERVICES |  | 3673557.72 | 3680000 | 3042000 | 3630000 | 3945000 | 3045000 | 3512000 | 3412000 | 3658000 | 3223000 | 3460000 | 1150468.46 | 39431026.18 | 41599732.58 | 43804518.43
Vote 7 - PLANNING AND DEVELOPMENT |  | 4194000 | 4257000 | 4179000 | 4420000 | 4187000 | 4003200 | 4500000 | 4890000 | 5609700 | 5123340 | 2578000 | 2395828.79 | 50337068.79 | 52700607.57 | 56309289.76
Vote 8 - COMMUNITY AND SOCIAL SERVICES | [12 empty] | 7486816.63 | 7486816.63 | 7898591.57 | 8317216.91
Vote 9 - HOUSING | [12 empty] | 0 | 0 | 0 | 0
Vote 10 - OTHER |  | 2540000 | 1800900 | 5000000 | 1374000 | 1450000 | 1178665.19 | 1180000 | 1245000 | 2470000 | 1478090 | 2750000 | 4928080.93 | 27394736.12 | 28901446.62 | 30433223.28
Vote 11 - SPORTS AND RECREATION |  | 1469000 | 1645000 | 1783000 | 1648000 | 1796400 | 1384500 | 1870000 | 1802600 | 132600 | 1750300 | 131450 | 2219313.25 | 17632163.25 | 18601932.24 | 19587834.63
Vote 12 - BUDGET AND TREASURY |  | 120000000 | 11600000 | 5000000 | 1920000 |  | 0 | 0 | 0 | 76076000 | 0 | 0 | 34721447.57 | 249317447.57 | 263029947.19 | 276971074.38
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
Total Expenditure by Vote |  | 156766833.27 | 55266900 | 47306566 | 41339000 | 36948733 | 36885365.57 | 34933766.55 | 34625300 | 189395300 | 37995730 | 34619450 | 129046871.72 | 835129816.11 | 892707885.84 | 962500928.94
Surplus/(Deficit) before assoc. |  | -82746333.27 | -21338200 | 25286334 | 28959800 | 34994267 | 36931634.43 | 36461833.45 | 38985700 | -116524000 | 35848970 | 40787950 | -50830525.4 | 45725430.21 | 48002609.45 | 28225402.32
Taxation | [12 empty] | 0 | 0 | 0 | 0
Attributable to minorities | [12 empty] | 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate | [12 empty] | 0 | 0 | 0 | 0
Surplus/(Deficit) | 1 | -82746333.27 | -21338200 | 25286334 | 28959800 | 34994267 | 36931634.43 | 36461833.45 | 38985700 | -116524000 | 35848970 | 40787950 | -50830525.4 | 45725430.21 | 48002609.45 | 28225402.32

## CAP CASHFLOW
LIM344 Makhado - Supporting Table SA30 Budgeted monthly cash flow
MONTHLY CASH FLOWS | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Cash Receipts By Source | [12 empty] | 1
Property rates | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3232865.08 | 43642000 | 46693000 | 49119000
Property rates - penalties & collection charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - electricity revenue | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071765.95 | 288861193.82 | 324101869.02 | 363641872.85
Service charges - water revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - sanitation revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - refuse revenue | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 720396.82 | 9724000 | 10404000 | 10944000
Service charges - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 33069.87 | 449000 | 481000 | 506000
Interest earned - external investments | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 243363.49 | 3285000 | 3515000 | 3697000
Interest earned - outstanding debtors | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 887499.89 | 11981000 | 12819000 | 13485000
Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 121760.85 | 1641000 | 1756000 | 1847000
Licences and permits | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 833718.73 | 11251000 | 12037000 | 12663000
Agency services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfer receipts - operational | 120000000 | 11600000 | 5000000 | 1920000 | 144000000 | 0 | 0 | 0 | 72490000 | 0 | 0 | 5000000 | 360010000 | 369813000 | 367641000
Other revenue | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1536958.92 | 20748000 | 22199000 | 23353000
Cash Receipts by Source | 152718254.02 | 44318254.02 | 37718254.02 | 34638254.02 | 176718254.02 | 32718254.02 | 32718254.02 | 32718254.02 | 105208254.02 | 32718254.02 | 32718254.02 | 36681399.6 | 751592193.82 | 803818869.02 | 846896872.85
Other Cash Flows by Source
Transfer receipts - capital | 0 | 0 | 0 | 4590000 | 43609000 | 5780000 | 1190000 | 0 | 74095000 | 0 | 0 | 0 | 129264000 | 136892000 | 143831000
Contributions recognised - capital & Contributed assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proceeds on disposal of PPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Short term loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Borrowing long term/refinancing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase (decrease) in consumer deposits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (Increase) in non-current debtors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) other non-current receivables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) in non-current investments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cash Receipts by Source | 152718254.02 | 44318254.02 | 37718254.02 | 39228254.02 | 220327254.02 | 38498254.02 | 33908254.02 | 32718254.02 | 179303254.02 | 32718254.02 | 32718254.02 | 36681399.6 | 880856193.82 | 940710869.02 | 990727872.85
Cash Payments by Type
Employee related costs | 18450000 | 18950000 | 18650000 | 18880000 | 18450000 | 32074000 | 18950000 | 18990000 | 18780000 | 18990000 | 18780000 | 21233438.3 | 241177438.3 | 254442197.44 | 267927633.86
Remuneration of councillors | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1559609.73 | 22610107 | 23944103 | 25284973
Finance charges | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 457848.06 | 6181000 | 6613000 | 6957000
Bulk purchases - Electricity | 18078244.34 | 18178000.34 | 18757000.34 | 17654000 | 16000000 | 16800000 | 17870000 | 18978244.34 | 19078244.34 | 17078888.34 | 19078067.34 | 19388242.9 | 216938932.28 | 247831036.2 | 283122175.81
Bulk purchases - Water & Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants - other municipalities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other expenditure | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 165584973.8315 | 184796014.9115 | 187462607.21 | 197656659.4415
Cash Payments by Type | 40708670.73 | 41308426.73 | 41587426.73 | 40714426.39 | 38630426.39 | 53054426.39 | 41000426.39 | 42148670.73 | 42038670.73 | 40249314.73 | 42038493.73 | 208224112.8215 | 671703492.4915 | 720292943.85 | 780948442.1115
Other Cash Flows/Payments by Type
Capital assets | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 11319600 | 163938000 | 204440000 | 192200000
Repayment of borrowing | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 1800000 | 1900000 | 2000000
Other Cash Flows/Payments | [10 empty] | 36000000 | 0 | 36000000 | 15000000 | 10000000
Total Cash Payments by Type | 54583070.73 | 55182826.73 | 55461826.73 | 55488826.39 | 52504826.39 | 66928826.39 | 54874826.39 | 56023070.73 | 56813070.73 | 54123714.73 | 91912893.73 | 219543712.8215 | 873441492.4915 | 941632943.85 | 985148442.1115
NET INCREASE/(DECREASE) IN CASH HELD | 98135183.29 | -10864572.71 | -17743572.71 | -16260572.37 | 167822427.63 | -28430572.37 | -20966572.37 | -23304816.71 | 122490183.29 | -21405460.71 | -59194639.71 | -182862313.2215 | 7414701.3285 | -922074.83 | 5579430.7385
Cash/cash equivalents at the month/year begin: | 5000000 | 103135183.29 | 92270610.58 | 74527037.87 | 58266465.5 | 226088893.13 | 197658320.76 | 176691748.39 | 153386931.68 | 275877114.97 | 254471654.26 | 195277014.55 | 5000000 | 12414701.3285 | 11492626.4985
Cash/cash equivalents at the month/year end: | 103135183.29 | 92270610.58 | 74527037.87 | 58266465.5 | 226088893.13 | 197658320.76 | 176691748.39 | 153386931.68 | 275877114.97 | 254471654.26 | 195277014.55 | 12414701.3285 | 12414701.3285 | 11492626.4985 | 17072057.237

## CAP BV
LIM344 Makhado - Supporting Table SA28 Budgeted monthly capital expenditure (municipal vote)
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Multi-year expenditure to be appropriated | 1
Vote 1 - EXECUTIVE AND COUNCIL |  | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8975000 | 107656000 | 153694000 | 137424000
Vote 2 - WASTE MANAGEMENT |  | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 438000 | 5300000 | 6000000 | 6400000
Vote 3 - ROAD TRANSPORT |  | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 121000 | 1430000 | 1472900 | 1456127
Vote 4 - WATER | [12 empty] | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1781000 | 21383000 | 32909471 | 35335190
Vote 6 - CORPORATE SERVICES |  | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4500000 | 4635000 | 4774050
Vote 7 - PLANNING AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575000 | 2575000 | 2729000 | 2811000
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 9 - HOUSING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - OTHER |  | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 588000 | 7100000 | 3000000 | 4000000
Vote 11 - SPORTS AND RECREATION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY |  | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1168000 | 13994000 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
Capital multi-year expenditure sub-total | 2 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 16021000 | 163938000 | 204440371 | 192200367
Single-year expenditure to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL | [12 empty] | 0 | 0 | 0 | 0
Vote 2 - WASTE MANAGEMENT | [12 empty] | 0 | 0 | 0 | 0
Vote 3 - ROAD TRANSPORT | [12 empty] | 0 | 0 | 0 | 0
Vote 4 - WATER | [12 empty] | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY | [12 empty] | 0 | 0 | 0 | 0
Vote 6 - CORPORATE SERVICES | [12 empty] | 0 | 0 | 0 | 0
Vote 7 - PLANNING AND DEVELOPMENT | [12 empty] | 0 | 0 | 0 | 0
Vote 8 - COMMUNITY AND SOCIAL SERVICES | [12 empty] | 0 | 0 | 0 | 0
Vote 9 - HOUSING | [12 empty] | 0 | 0 | 0 | 0
Vote 10 - OTHER | [12 empty] | 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION | [12 empty] | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
- | [12 empty] | 0 | 0 | 0 | 0
Capital single-year expenditure sub-total | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital Expenditure | 2 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 16021000 | 163938000 | 204440371 | 192200367

## APPROVAL
12. APPROVAL BY THE MAYOR
In line with section 53 of the Municipal Finance Management Act No 56 of 2003 (MFMA), it is a privilege and honor to approve and make public the Service Delivery and Budget implementation Plan (SDBIP) of Makhado Municipality for 2015/2016 financial year. The SDBIP is a contract between the Administration, Council and the Community clearly spelling out how and when the IDP and budget targets for 2015/2016 would be pursued and achieved. It is a management, implementation and monitoring tool that is meant to assist the Mayor, Council, Municipal Manager, Senior Managers and the Community to monitor the municipality’s performance. Makhodo Municipality and its Community have a role to play in achieving the municipality vison that reads "A dynamic hub for socio – economic development by 2025" Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Recommendation by The Municipal Manager: The Municipal Manager hereby recommend for the approval of the SDBIP by the Mayor in line with the above legislation ___________________________ _____________________ Mutshinyali I.P DATE Municipal Manager
Approval by the Mayor The SDBIP 2014/2015 is hereby approved by the Mayor of Makhado Municipality ______________________________ ____________________ Hon Cllr Mutavhatsindi F. D DATE