## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
THIRD QUARTER PERFORMANCE
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER AND LOWER SDBIP)
FOR
2015/2016 FINANCIAL YEAR
AFTER ADJUSTMENT BUDGET

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vison and Mission
3. Departments
4. HIGHER LEVEL SDBIP
4.1. Municipal Transformation and Organisational Development
4.2. Baisc service Delivery
4.3. Local Economic Development
4.4. Municipal Finance Management and Viability
4.5. Good Governance and Public Participation
5. LOWER LEVEL SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. Monthly Revenue and Expenditure
7. Monthly Revenue and Expenditure by Vote
8. Capital Cashflow
9. Capital Cashflow by Vote
10. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1)(c) of MFMA states that 54. (1) On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must— (a) consider the statement or report; (b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan; (c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget; (d) issue any appropriate instructions to the accounting officer to ensure— (i) that the budget is implemented in accordance with the service delivery and budget implementation plan; and (ii) that spending of funds and revenue collection proceed in accordance with the budget; (e) identify any financial problems facing the municipality, including any emerging or impending financial problems; and (f) in the case of a section 72 report, submit the report to the council by 31 January of each year.
In terms of MFMA Circular 13, the SDBIP is a layered plan, with the top layer of the plan dealing with consolidated service delivery targets and in-year deadlines, and linking such targets to top management. Once the top-layer targets are set, the top management is then expected to develop the next (lower) layer of detail of the SDBIP, by providing more detail on each output for which they are responsible for, and breaking up such outputs into smaller outputs and linking these to each middle-level and junior manager. Much of this lower layer detail will not be made public nor tabled in council – whilst the municipal manager has access to such lower layer detail of the SDBIP, it will largely only be the senior manager in charge who will be using such detail to hold middle-level and junior-level managers responsible for various components of the service delivery plan and targets of the municipality. Only the highest layer of information of the SDBIP will be made public or tabled in the council. Such high-level information should also include per ward information, particularly for key expenditure items on capital projects and service delivery – this will enable each ward councilor and ward committee to oversee service delivery in their ward.

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## HIGH LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward/Dept | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | IDP Review | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Draft IDP completed and submitted to Council for adoption by 31 March 2016 | Target achieved | Draft IDP was completed and submitted to Council for adoption by 31 March 2016 | None | None | Council resolutions, Draft IDP, Attendance register, Invitations for strategic plan, IDP Consultation attendance register. | MM
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/4/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2016 | 114 | 135 | Training | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/4/2015 | 30/6/2016 | 3 | Target achieved | 28 | None | None | Proof of attendance | CORP
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2016 | 61 | 75 | Training | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/4/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Proof of attendance | CORP
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Organogram review | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Submit the draft organogram to Council for provisional approval. Consultation with organised labour | Target achieved | Draft organogram submitted to Council for provisional approval. Consultation with organised labour was done | None | None | Minutes and attendance register, Council resolutions, | CORP
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | 3 | 4 | Recruitment in terms of EE Plan | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Appointment letters | CORP
Spatial and Town Planning | Advance Spatial Planning | % achievements of spatial programs indicators/targets per quarter | 100% (10/10) | 100% (16/16) | Spatial Planning | Makhado Municipality | N/A | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (16/16) | Targert achieved | 100% (9/9) | None | None | Activity reports | DEVP
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Makhado Town, Tshikota Township, Vleifontein, Waterval Township, Dzanani township, Vuwani Township, Kutama-Sinthumule Area, Brambos | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 19149 (non cumulaitve) | Target achieved | 19149 (non cumulaitve) | None | None | Proof of collection from the affected stakeholders. | MM and COMM
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2016 | 2 | 3 | Development of Parks | 5047 park,Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 12000000 | 436342.11 | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Approval memo. RFP, appointment letter, Completion certificate | COMM
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2016 | 1047 | 1180 | Electrification of households | Magau, Tshiozwi, Ramantsha, Madodonga,Mamburu, Makushu, Wisagalaza, Sukani, Mamburu, Gogobole, Tshivulana, Ratombo, Fredom, Lusaka, Tshivhuyuni. | Ward 23,25,03 | INCOME | 21824299 | 22199786 | 14928138.28 | 1/7/2015 | 30/6/2016 | 179 | Target achieved | 179 | None | None | Proof of connections to targeted households | MM and TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads upgraded from gravel to tar/paving by 30 June 2016 | 26km | 18.9km | Upgrading of roads | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 79361617 | 71265668.08 | 1/7/2015 | 30/6/2016 | 4.5km | Target achieved | 4.5 km done | None | None | Project progress report, Certificate of completion | TECH
Sports Facilities | Accessible basic and infrastructure services | To upgrade Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Upgrading of Vuwani sports facilities | Makhado Municipality | Ward 3 | MIG | 2492678 | 4492677.57 | 1296760.67 | 1/7/2015 | 30/6/2016 | Completion of concrete pavillion | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Project progress report, handover report | TECH
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | N/A | Planning for Waterval sports facility completed. | Planning for Waterval sports facility. | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 | 0 | 1/7/2015 | 30/6/2016 | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Concrete pavillion completed | None | None | Advertisement copy, appointment letter, design report. | TECH
Building and Construction | Accessible basic and infrastructure services | No of graveyards to be developed by 30 June 2016 | 1 | 10 | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing (Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein, Vuwani, Dzanani) | Ward 35, 25, 1,12,8,27,32,20 | MIG | 26700000 | 370000 | 0 | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Advertisement copy, appointment letter,project progress report, handover report | TECH
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (HIGHER SDBIP)
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | Aministration | Income | 163938800.12 | 169,734,677.34 |  | 1/7/2015 | 30/6/2016 | 70% | Target Achieved | 73% (122946203.60/169,734,677.34) | None | None | Quarterly Financial Report | MM and All Directors
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | Aministration | Income | 112264000 | 112264000 |  | 1/7/2015 | 30/6/2016 | 70% | Target Achieved | 82% (92252303.79/112264000) | None | None | Quarterly Financial Report | MM
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | Aministration | Income | 17000000 | 17000000 |  | 1/7/2015 | 30/6/2016 | 70% | Target Achieved | 68% (11567689.70/17000000) | None | None | Quarterly Financial Report | MM
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Makhado Municipality | Aministration | Income | 1600000 | 1600000 |  | 1/1/2016 | 31/3/2016 | 100% (80000) | Target Achieved | 58% (930418.99/1600000) | None | appoint interns ealier through HR | Expenditure Report | B&T
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | Aministration | Income | 342227123 | 342227123 |  | 1/7/2015 | 30/6/2016 | 70% | Target Not Achieved | 64 % (236713000/370286000 | proprty rates amendment still in prgress and debt over 180 days slow payments from consumers | proprty rates ammendment uploaded on test system of munsoft still resloving programming errors noted | Section 71 report (c1 schedule) | B&T
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governace and Administrative Excellence | # of risk activities cordinated by 30 June 2016 | 13 | 13 | Risk Management activities | Makhado Municipality | Aministration | Income | OPEX | Operational | Operational | 1/7/2015 | 30/6/2016 | 3 | Target achieved | 3 | None | None | Risk Management Register and Reports | MM
Policies and By Laws | Good governace and Administrative Excellence | # of bylaws to be reviewed by 30 June 2016 | 7 | 4 | Reviewing of Municipal By-laws | Makhado Municipality | Aministration | Income | 1/7/2015 | Operational | Operational | 01/07/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Council resolutions, Copies of approved by laws. | CORP
Internal Auditing | Good governace and Administrative Excellence | No of internal audit indicators/ activities/ projects implemented by 30 June 2016 | 9 | 6 | Internal Audit projects | Makhado Municipality | Aministration | Income | OPEX | Operational | Operational | 1/4/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM
Information Technology | Good governace and Administrative Excellence | No of IT projects implimented by 30 June 2016 | 8 | 8 | IT Projects | Civic Center | Aministration | Income | R3000,000 | Operational | Operational | 1/7/2015 | 31/3/2016 | 3 | Target not achieved | 2 | Quotation Committee did not sit for purchase of the laptops, computers, printers and desktops | Document to be signed in the 4th quarter. | Advertisement for RFP | CORP
Council Services | Good governace and Administrative Excellence | # of Council meetings convened by 30 June 2016 | 15 | 6 | Council meetings | Makhado Municipality | Aministration | Income | OPEX | Operational | Operational | 1/7/2015 | 30/6/2016 | 2 | Target achieved | 5 | None | None | Minutes, Attendance register, notice of invitations. | CORP
Communication | Good governace and Administrative Excellence | No of communication indicators/activities/projects implemented by 30 June 2016 | 5 | 5 | Communication projects | Civic Center | Ward 20 | Income | OPEX | Operational | Operational | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP
Public Participation | Good governace and Administrative Excellence | No of public participation indicators/activities/projects implemented by 30 June 2016 | 7 | 7 | Public Participation | Makhado Municipality | All wards | Income | OPEX | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | None | None | Attendance register and Programme | CORP

## LMTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (LOWER SDBIP)
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2016 | 8 | 8 | Quarterly performance reports | Makhado Municipality | 21 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 4 | Target achieved | 4 | None | None | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2016 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% (6/6) | Performance agreements | Makhado Municipality | 21 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% | Target achieved | 100% (6/6) | None | None | Signed Performance Agreements | MM
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2016 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Makhado Municipality | 21 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 (Formal Assessment 2014/2015) | Target achieved | 1 (Formal Assessment 2014/2015) | None | None | Scorecards, Attendance Register | MM
Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2016 | 67 employees appointed | 30 | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Operational | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP
Human Resources and Organizational Development | Invest in human capital | # of employee assistance programmes events conducted by 30 June 2016 | 6 events | 6 events | Employee Assistance Campaigns | Makhado Municipality | 21 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 event | Target achieved | 1 event conducted | None | None | Invitations, attendance registers and close-out report | CORP
Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Development of 3 outstanding HR policies | Makhado Municipality | 21 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Submit the draft policies to LLF for consultation | Target achieved | Draft policies were submitted to LLF for consultation and they were recommended to council. | None | None | Approved 3 policies and the council resolutions (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Award 15 bursaries to qualifying applicants | Target achieved | 19 | None | None | Advert, List of qualifying leaners and Letters of bursary awards | CORP
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | 49 events done in 2014/15 | 43 for 2015/16 | Special Programs | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 12 | Target achieved | 12 | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of application received/(# of application attended to within 90 days). | Targert achieved | 100% (9/9 of application received/(9/9 of application attended to within 90 days). | None | None | Site inspection report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of housing queries attended within 30 days/# of received) | Targert achieved | 100% (25/25 of housing queries attended within 30 days/25/25 of received) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2016 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of building plans assessed/# of building plans received) | Targert achieved | 100% (116/116 of building plans assessed/116/116 of building plans received) | None | None | Building plans register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2016 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Targert achieved | 100% (7/7 of applications processed/7/7 applications received) | None | None | Zoning certificates issued | DEVP
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2016 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Targert achieved | 100% (15/15 of applications processed/15/15 applications received) | None | None | EXCO resolutions | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Targert achieved | 100% (7/7 of application for land use rights inspection conducted within 14 days/7/7 of application received) | None | None | Site inspection report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2016 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Targert achieved | 100% (4/4 of applications processed/4/4 of applications received) | None | None | Copy of occupancy certificates issued | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Targert achieved | 100% (99/99 of applications processed/ 99/99 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Targert achieved | 100% (24/24 of applications processed/24/24 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Targert achieved | 100% (7/7 of applications processed/ 7/7 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% (65/65 of applications processed/ 65/65 of applications received) | None | None | Bookings register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of queries processed/# of queries received) | Target achieved | 100% (1/1 of queries processed/ 1/1 of queries received) | None | None | Correspondence letters and emails. | DEVP
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target achieved | 100% (13/13 of contravention notices issued within 5 days/13/13 of contravention identified) | None | None | Duplicate notices | DEVP
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2016 | 240 | 240 | Routine Inspection | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 60 | Target achieved | Routine inspections conducted | None | None | Inspection form, Register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Target achieved | 100% (57/57 of site inspections conducted within 24 hours/# of site inspections application received) | None | None | Inspection form, Register | DEVP
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2016 (Dzanani) | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming (Dzanani) | Makhado Municipality | 33 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Draft Street Names | Target not achieved | Advert done , non responsive bidders quoted | Non responsive bidders | Re advert done after non responsive bidders quoted | Expenditure Report | DEVP

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Locatio/Departmet | Ward | Funding Source | Budget 15/16 R'000 | Adjusted budget | Expenditure | Start Date | End date | 3rd quarter | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio of Evidence | Dept
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (LOWER SDBIP)
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Community Services - disaster Management Unit | N/A | Income | Operational | Operational | Operational | 2015-01-07 | 30/06/2016 | Update received informkation into the Disaster Management Plan. Draft Disaster Management Plan completed. | Target achieved | Disaster management plan updated | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM
Library Services | Promote community and environmental welfare | To do designs for refurbishment of the library roof by 30 June 2016 | Roof damaged | Designs for Refurbishment of the library building completed | Designs for Refurbishment of library building | Community Services - Library Services Unit | Ward 20 | Income | 1000000 | 200000 | 0 | 2015-01-07 | 30/06/2016 | Planning of designs for the roof | Target achieved | Planning of designs for the roof done | None | None | Project Progress report | TECH
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre completed | Development of | Tshikota | Ward 21 | MIG | 5 000 000.00 - | 5599366.72 | 4985366.72 | 2015-01-07 | 30/06/2016 | Linning of evaporation ponds and waste dosposal cell. Driiling of 2 boreholes (Landfill site) | Target not achieved | Tender advertised done | None | None | Approval memo, Specifications, Advertisement copy, Appointment letter, Project progress report | COMM
Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | N/A | Landfill site rehabilitatation completed. | Rehabilitation of the existing Landfill site (Vondelling) | Makhado Municipality | 21 | INCOME | 4000000 | 3083000 | 2368765.09 | 2015-01-07 | 30/06/2016 | Construction of evaporation ponds and V-drains. | Target not achieved | Construction of evaporation ponds and V-drains not done | The Service provider was not appointed due non responsiveness to the tender. | The project to be done in 2016/2017 financial year. | Project Progress report | TECH
Parks and Recreation | Promote community and environmental welfare | To develop 5047 Park by 30 June 2016 | N/A | Development of 5047 Park completed | Development of 5047 Park | 5047 Park | Ward 20 | INCOME | 700000 | 700000 | 0 | 2015-01-07 | 30/06/2016 | Appointment of service providers. (it was done in the in second quarter) | Target achieved | Service provider appointed done | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
Parks and Recreation | Promote community and environmental welfare | To pay the service provider for development of the N1 recreational park by 30 June 2016 (R436842.11) | N/A | Payment of service provider for Development of N1 recreational park done (R436842.11) | Payment for Development of N1 recreational park | Makhado Municipality | Ward 21 | INCOME | 1000000 | 1000000 | 436842.11 | 2015-01-07 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Proof of payment | COMM
Parks and Recreation | Promote community and environmental welfare | To refurbish and upgrade Civic Centre Park+ Meerkat park by 30 June 2016 | N/A | Refurbishment and Upgrading of Civic Centre Park+Meerkat park completed | Refurbishment and Upgrading of Civic Centre Park and Meerkat Park | Civic Centre Park | Ward 20&21 | INCOME | 500000 | 500000 | 0 | 2015-01-07 | 30/06/2016 | Appointment of service providers. | Target achieved | Service provider has been appointed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
Electricity Provision | Accessible basic and infrastructure services | To connect 50 households at Magau by 30 June 2016 | N/A | 50 households at Magau completed | MAGAU | Magau | Ward 23 | INCOME | 935201.32 (INCOME) 712 000 (INEP) | 1830361.02 (INCOME) 712 000 (INEP) | 663748.45(INCOME) 337190.83(INEP) | 2015-01-07 | 30/06/2016 | Complete MV and LV networks. | Target achieved | MV and LV networks completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 40 households at TSHIOZWI /GOGOBOLE by 30 June 2016 | N/A | 40 households connected at TSHIOZWI /GOGOBOLE | TSHIOZWI & GOGOBOLE | Tshiozwi Gogobole | Ward 23 | INCOME | 2101576 | 2701576 | 888404 | 2015-01-07 | 30/06/2016 | Completion of MV and LV networks. | Target not achieved | MV and LV networks completed at Tshiozwi and still busy at Gogobole | Slow progress | Impose penalties | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 96 houuseholds at Ramantsha/Riverside by 30 June 2016 | N/A | 96 households at Ramahantsha /Riverside completed | RAMANTSHA/RIVERSIDE | RAMANTSHA/RIVERSIDE | Ward 23 | INCOME | 1281962 | 1281962 | 1118480.69 | 2015-01-07 | 31/03/2016 | 96 Service connections completed, Switching on and completion of the project | Target achieved | 97 house connections completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 83 households at Madodonga/Manavhela by 30 June 2016 | N/A | 83 households at Madodonga/Manavhela completed | MADODONGA | MADODONGA | Ward 25 | INCOME | 1681261 | 2231261 | 1611090 | 2015-01-07 | 31/03/2016 | 83 Service connections completed, Switching on and completion of the project | Target achieved | 83 house connections completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 120 households at Mamburu by 30 June 2016 | N/A | 120 households at Mamburu completed | Mamburu | Mamburu | Ward 25 | INEP | 2250000 | 1995012.81 | 794994.61 | 2015-01-07 | 30/06/2016 | Planting of poles. | Target achieved | Poles were planted | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 30 households at Makhushu by 30 June 2016 | N/A | 30 households at Makhushu completed | MAKUSHU | MAKUSHU | Ward 25 | INEP | 490000 | 490000 | 0 | 2015-01-07 | 30/06/2016 | Planting of poles, | Target not achieved | Planting of poles in progress | Delays in submission of designs | To complete the project before the end of the 4th quarter | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To do designs for Vyeboom 2016/2017 electrification projects ) by 30 June 2016 | N/A | Designs for Vyeboom 2016/2017 electrification projects completed | Designs for Vyeboom 2016/2017 electrification projects | Vyeboom village | Ward 3 | INEP | 952500 | 952500 | 921274.47 | 2015-01-07 | 30/06/2016 | Evaluation, Adjudicationa nd appointment of the engineer. | Target achieved | Project was handed over to ESKOM with complete designs | None | To be removed from list of MLM projects | Specifications, Advertisement, appointment letter, Designs, Minutes of of technical forum meeting | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 3km Industrial line by 30 June 2016 | N/A | Upgrading 3km Industrial line | Upgrading 3km Industrial line | Makhado Municipality | Ward 21 | INCOME | 230000 | 230000 | 169579 | 2015-01-07 | 30/06/2016 | Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. | Target not achieved | Poles are delivered hence the following is not done: Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. | Breakdown of pole truck | Truck was repaired and the project is continuing | Designs, Appointment letter for labourers, Project progress report, | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 4.5km Shefeera Line by 30 June 2016 | N/A | Upgrade 4.5km Shefeera Line completed | Upgrade 4.5km Shefeera Line | Makhado Municipality | Ward 21 | INCOME | 600000 | 512999 | 281939.77 | 2015-01-07 | 30/06/2016 | Stringing of conductors. | Target achieved | Stringing of conductors completed | None | None |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To appoint the contractor for upgrade of urban substations by 30 June 2016 | N/A | Appointment of contractor and site handover. | Upgrade Urban Substations | Makhado Municipality | Ward 20 | INCOME | 2500000 | 339839.98 | 298105.25 | 2015-01-07 | 30/06/2016 | Evaluation and adjudication . | Target achieved | Evaluation and adjudication completed | None | None |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 5km Mountain line by 30 June 2016 | N/A | Upgrading 5km Mountain line completed | Upgrading 5km Mountain line | Makhado Municipality | Ward 30 | INCOME | 250000 | 250000 | 202874.51 | 2015-01-07 | 30/06/2016 | Dress and plant poles. | Target not achieved | In the process of delivering poles | Breakdown of pole truck | Truck was repaired |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute 2.2km Beaufort West line by 30 June 2016 | N/A | Upgrade and reroute 2.2km Beaufort West line completed | Upgrade and reroute 2.2km Beaufort West line | Beaufort West line | Ward 30 | INCOME | 1500000 | 1500000 | 0 | 2015-01-07 | 30/06/2016 | Appointment and site handover. | Target achieved | Appointment and site handover completed | None | None | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace oil curcuit breaker by 30 June 2016 | N/A | Replacement of oil curcuit breaker completed | Oil curcuit breaker replacement | Main substation | Ward 21 | INCOME | 400000 | 1044721.95 | 792100 | 2015-01-07 | 30/06/2016 | Appointment of supplier. | Target achieved | Two OCBs were delivered. Await delivery of the 3rd OCB from the manufacturer | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | N/A | Replacement of channel cover completed | Substation channel cover replacements | Makhado Municipality | All wards | INCOME | 0 | 0 | 0 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | N/A | Standby generator installed | Standby (Backup) Electricity Power Generator-Dzanani | Dzanani | 33 | INCOME | 250000 | 250000 | 217777.28 | 2015-01-07 | 31/03/2016 | Appointment of service provider and completion of project. | Target achieved | Project completed | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | % air condtioners replaced by 30 June 2016 (# replaced/# requested) | N/A | 100% Air Conditioners replaced | Air Conditioners | Municipal area | All municipal office | INCOME | 150000 | 450000 | 154406 | 2015-01-07 | 30/06/2016 | 100% | Target achieved | 100% (8/8) | None | None | Orders, job cards, photos, invoices, payment certificates | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | N/A | CT VT Units 11kv & 22kv replaced | CT VT Units 11kv & 22kv | Makhado | All municipal areas | INCOME | 300000 | 0 | 0 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | n/a | Funds re-allocated |  |  | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming B9, T8, A21 and G23/24 by 31 March 2016 | N/A | Low voltage to medium voltage in Rural Farming B9,T8 and A21 upgraded | Low voltage to medium voltage in Rural Farming B9,T8 and A21 | Makhado | All municipal areas | INCOME | 250000 | 658000 | 292276.58 | 2015-01-07 | 30/06/2016 | A21 completed | Target achieved | Completed A21 | None | None | Project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | N/A | Mini Subs replaced | Mini Subs | Makhado | All municipal areas | INCOME | 900000 | 665000 | 665000 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | N/A | MV Cable 95mm 22kV replaced | MV Cable 95mm 22kV | Makhado | All municipal areas | INCOME | 150000 | 136500 | 136500 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH
Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | N/A | Recloser and controllers whole network procured | Recloser and controllers whole network | Makhado | All municipal areas | INCOME | 700000 | 700000 | 0 | 2015-01-07 | 30/06/2016 | Delivery of materilals. | Target not achieved | Delivery of materilals not done. Service privider is appointed and ordered the materials | SP awaiting delivery of material | Follow-up with the supplier and receive the materials before end of 4th quarter. | Specification, orders, delivery notes, progress report, completion certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | N/A | Remote control of switch gear Tshipise & Levubu procured | Remote control of switch gear Tshipise & Levubu | Makhado | All municipal areas | INCOME | 120000 | 180000 | 0 | 2015-01-07 | 30/06/2016 | Appointment of supplier and delivery | Target not achieved | Appointment of supplier done. and delivery of material not done. The materials have been ordered. | Service provider awaiting delivery of material | Follow-up with the supplier and receive the materials before end of 4th quarter. | Specification, advertisement, appointment letter, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Makhado | All municipal areas | INCOME | 300000 | 306740 | 270000 | 2015-01-07 | 31/03/2016 | Project competion and payment certificate | Target achieved | Completed | None | None | Specification, order, delivery note, project progress report, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To constuct Standby quarter perimeter wall by 31 March 2016 | N/A | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Makhado | All municipal areas | INCOME | 60000 | 300000 | 60000 | 2015-01-07 | 31/03/2016 | Plastering and painting | Target not achieved | Plastering and painting not done. | The bricklayer went on pension. | To use experienced service worker with close supervison. | Specification, advertisement, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | N/A | Standby quarter guard room completed | Standby quarter guard room | Makhado | All municipal areas | INCOME | 250000 | 250000 | 0 | 2015-01-07 | 30/06/2016 | Construction of brickwork (internal staff). Wall completion | Target not achieved | Construction of brickwork has not started(internal staff). Wall not completed. | The bricklayer went on pension. | To propose for a service provider | Specification, advertisement, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 471 households at Wisagalaza 2 & Chitasi village by 30 June 2016 | Site establishment | Wisagalaza 2 & Chitasi village 471 households connection completed | Wisagalaza 2 & Chitasi village | Wisagalaza village | 8 | INEP | 7771500 | 8826487.19 | 8065125.24 | 2015-01-07 | 30/06/2016 | Service connections | Target achieved | Service connections completed | None | None | Appointment letter, project progress report, completion certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 87 households at SUKANI by 30 June 2016 | N/A | Site handover to contractor, planting of poles. | SUKANI | SUKANI | Ward 8 | INEP | 1392000 | 1392000 | 0 | 2015-01-07 | 30/06/2016 | Completion of designs. | Target achieved | Designs completed. Site handover done and work in progress | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 102 electricity at TSHIVHULANA by 30 June 2016 | N/A | Tshivulana 102 connections completed | TSHIVHULANA zone 5 | TSHIVHULANA zone 5 | Ward 1 | /INCOME INEP | 1632000 | 0 | 0 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 150 households at Ratombo/ by 30 June 2016 | N/A | Stringing of MV and LV conductors done | RATOMBO | RATOMBO | 32 | INEP /income | 1472000 | 1472000 | 1449104.55 | 2015-01-07 | 30/06/2016 | Planting of poles, | Target achieved | Poles were planted | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 53 households at Freedom and Lusaka (Tshivhuyuni) by 30 June 2016 | N/A | Site handover and planting of poles. | Freedom and Lusaka (Tshivhuyuni) | Freedom and Lusaka (Tshivhuyuni) | 12 | INEP | 1040000 | 1040000 | 0 | 2015-01-07 | 30/06/2016 | Completion of designs. | Target achieved | Designs completed. Site handover done and work in progress | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To electrify Rabali Stadium by 30 June 2016 | N/A | Electrification Rabali Stadium facility completed | Electrification Rabali Stadium | Rabali stadium | Ward32 | Income | 150000 | 140000 | 118453.84 | 2015-01-07 | 31/03/2016 | Appointment of service provider and completion of project. | Target achieved | Completed | None | None | Specifications, Advertisement, Apointment letter, delivery notes, | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgarde Tshikota Access/Pretoriuos Street access road (6.5km) by 30 June 2016 | Gravell road | Tshikota access road/Pretoriuos street upgraded | Upgrading of Tshikota access road/Pretoriuos street upgraded | Makhado Municipality |  | MIG | 1936405 | 1793613.68 | 1793613.68 | 2015-01-07 | 30/09/2015 | N/A | N/A | N/A | N/A | N/A | Project progress report, Completion certificate, handover report | TECH
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To upgrade Magau road (4.5km) phase 2 by 30 June 2016 | Gravell road | Magau road phase 2 completed | Magau road phase 1 | Magau | Ward 23 | MIG | 22000000 | 21848466.41 | 20565864.05 | 2015-01-07 | 31/03/2016 | Surfacing of the road and handing over. | Target achieved | Surfacing of the road done | Handover rescheduled | To handover in the 4th quarter | Project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhulana to Tshilaphala access road (4.5km) by 30 June 2016 | Gravell road | Tshivhulana to Tshilaphala access road constructed to a base level. | Tshivhulana to Tshilaphala access road | Tshivhulana to Tshilaphala |  | MIG | 13976988.13 | 3000000 | 2821564.41 | 2015-01-07 | 30/06/2016 | Site handover and establishment Setting out Roadbed preparation | Target not achieved | Site handover and . Establishment not done Setting out not done Roadbed preparation not done. | Delays in approval by SANRAL | To complete the project in the 2016/2017 financial year | Specifications, advertisement, appointment letter, project progress report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road(6.6km) by 30 June 2016 | Gravell road | Ledig road completed | Ledig road | Ledig | Ward 21 | MIG | 9387156 | 15403183.1 | 14903182.5 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Site establishment report, project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road(3.5km) by 30 June 2016 | N/A | Robert Khoza /Chabani Bungeni road completed | Robert Khoza /Chabani Bungeni road construction | Robert Khoza /Chabani Bungeni road | Ward 13 | MIG | 23000000 | 19689296.81 | 13610364.5 | 2015-01-07 | 30/06/2016 | Construction of bridge structure and deck. Finalising roadbase | Target not achieved | Construction of bridge structure and deck not complete Finalising roadbase is done | Slow progress by the contractor | To strickly monitor the contractor and impose penalties. The roject will be rolled over | Site establishment report, project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road(4.3km) phase 1 by 30 June 2016 | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | Tshivhazwaulu to Rasivhetshela road phase 1 | Makhado Municipality | Ward 4 | MIG | 23811987.67 | 20613816.06 | 17571078.94 | 2015-01-07 | 30/06/2016 | Surfacing of the road and stormwater drains | Target achieved | Surfacing and stormwater drains complete | None | None | Advertisement copy, appointment letter, design report. | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads and bridge projects by 30 June 2016 | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road completed | Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road | Makhado Municipality | Ward 25, 25, 36,30,3,15,12, | MIG | 1 600 000 | 0 | 0 | 2015-01-07 | 30/06/2016 | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Advertisement copy, appointment letter, design report. | TECH
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | N/A | Planning for Waterval sports facility completed. | Planning for Waterval sports facility. | Makhado Municipality | Ward 16 | MIG | 1100000 | 0 | 0 | 2015-01-07 | 30/06/2016 | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Advertisement copy, appointment letter, design report. | TECH
Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Upgrading of Vuwani sports facilities | Makhado Municipality | Ward 3 | MIG | 2492678 | 4492677.57 | 1296760.67 | 2015-01-07 | 30/06/2016 | Completion of concrete pavillion | Target achieved | Concrete pavillion completed | None | None | Project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct 8 graveyards fencing by 30 June 2016 | N/A | Graveyard fencing completed | Graveyard fencing (Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | Ward 35, 25, 1,12,8,27,32,20 | MIG | 2000000 | 2000000 | 0 | 2015-01-07 | 30/06/2016 | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of Contractor done | Insufficient budget for the project | Appoint within available budget | Advertisement copy, appointment letter,project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Fencing Vuwani Cemetery | Vuwani | Ward 3 | Income | 300000 | 300000 | 0 | 2015-01-07 | 30/06/2016 | Advertisement for appointment of Contractors. | Target achieved | Advertisement for appointment of Contractors done. | None | None | Advertisement copy, appointment letter,project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | N/A | Vuwani cemetry Ablution Facility completed | Vuwani Cemetery ( Toilet ) | Vuwani | Ward 3 | Income | 70000 | 70000 | 0 | 2015-01-07 | 30/06/2016 | Advertisement for appointment of Contractors. Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Advertisement for appointment of Contractors done. Evaluation not done Adjudication and Appointment of Contractor not done | Delays in submission of specifications | To speed up the proccess and complete before end of 4th quarter. | Advertisement copy, appointment letter,project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | N/A | Graveyard fencing completed | Fencing grave yard +sliding gate(Dzanani cemetery) | Dzanani township | Ward 35 | Income | 300000 | 300000 | 0 | 2015-01-07 | 30/06/2016 | Setting out and construction of fence Finalisation of the fence | Target not achieved | Setting out and construction of fence Finalisation of the fence not done | Contractor reluctant to start with the project due to under-pricing | Contractor to withdraw from the project and will be replaced. | Advertisement copy, appointment letter,project progress report, handover report | TECH

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets ( | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/1/2016 | 30/6/2016 | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | Target Achieved | Submitted to council: Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | None | None | OPEX | OPEX | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T
Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to council | Draft budget | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/1/2016 | 31/3/2016 | Draft budget tabled to council | Target Achieved | Submitted to council: Draft budget | None | None | OPEX | OPEX | Draft budget and Council Resolution | B&T
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget was submitted to council | Final budget submitted to council | Final budget | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/4/2016 | 31/5/2016 | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Final budget and Council Resolution | B&T
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2015 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/7/2015 | 31/8/2015 | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Copy of Financial statements | B&T
Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Section 71 report submission | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 3 | Target Achieved | 3 | None | None | OPEX | OPEX | Copy of acknowledgement of receipt by Treasuries | B&T
Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Tender adjudication | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Target Achieved | 100% (/19 tenders adjudicated/1 of tenders closed and due for adjudication) | None | None | OPEX | OPEX | Monthly Tender Reports | B&T
Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | Quotations | Makhado Municipality |  | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of quotations processed/# of quotations received) | Target not Achieved | 77% (17/22) | festive season quatations committees did not meet | improved planning on departments so as to avoid bids being advertised in december | OPEX | OPEX | Quotations Report | B&T
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Asset Register | Makhado Municipality | Ward 20 | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Targrt achieved | casptured new acquisitions, Bar coded and captured into the asset register. | None | None | OPEX | OPEX | Schedules of Asset Register movement | B&T

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept
5.4. LOCAL ECONOMIC DEVELOPMENT (L0WER SDBIP)
Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2016 | N/A | Development of Makhado information and recreational centre completed | Makhado N1 Information and Caravan Recreational/Entertainment centre | Makhado Municipality | Ward 20 | Income | 500000 | 100000 |  | 01/01/2016 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Specifications, Appointment letter (contrcator) | DEVP
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2015 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Makhado Municipality | Ward 20 | Income | 159300 | 159300 |  | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Annual Show Report and Audited Financial Statements | DEVP
Local Economic Development | Invest in local economy | # of LED projects supported by 30th June 2016 | 9 | 10 | LED strategy implementation | Makhado Municipality | All wards | Income | Operational | Operational | Operational | 1/7/2015 | 30/9/2016 | 10 | Target achieved | 10 projects are beind supported namely: Transnet/Furniture, Salaunavhe Poultry farm, Nthabalala Agriculture, Phaphama Agricultural, ,Mulima Pfananani, Kutama Clinic Greenery, Zamenkomste, Poultry, Vumatshelo Farming, Thirabeli Agricultural, Tshivhulani Community Garden | N/A | N/A | OPEX | OPEX | LED strategy implementation report | MM and DEVP

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment Budget | Expenditure | Start Date | End date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (LOWER SDBIP)
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of cases attended/# of cases reported) | Target achieved | 100% (1/1) | None | None | Case Register | MM
Public Participation | Good governace and Administrative Excellence | To develop the public participation policy by 31 March 2016 | No policy | Public Participatuion policy approved by Council | Public Participation Policy | Compile Public Participation Policy and submit to Council for approval | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 31/3/2016 | Submit the draft to council. Advertise the policy for public comment. | Target achieved | Draft Public Participation Policy, 2016 was approved by Council Resolution A.9.28.01.16 and under public consultation | None | None | Approved policy Programmes and attendance register Final approve policy and advert for public comment | CORP
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 3o June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 38 wards | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Target achieved | 114 Ward Committee meetings were held | None | None | Minutes, Attendance register, Ward committee quarterly report | CORP
Public Participation | Good governace and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | 2 | 2 | Training of ward committees | Arrange and coordinate training event of all ward committees for at least 2 events | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Approval of the memorandum by MM (2nd training) | Target not achieved | Approval of the memorandum by MM (2nd training) not done | Officials responsible delayed in wrotting the memorandum | To implement the project in the 4th quarter. | Training attendance register; training curriculum | CORP
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 4 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool, Pound, rationalise street trading, hawkers and markets into one bylaw. Street and diverse (public nuisance). | Makhado Municipality |  | Income | 1/7/2015 | OPEX | OPEX | 01/07/2015 | 30/06/2016 | Workshopping of Councillors and Public Participation on draft by laws | Target achieved | Workshopping of Councillors and Public Participation on draft by laws was done | None | None | 4 draft bylaws Provisional approved by Council , newspaper notice, attendance registers for public consultation, Final council resolutions and Promulgation notice for the 4 by laws in the provincial gazzete | CORP
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | OPEX | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | OPEX | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Implementation of the Approved Internal Audit Plan | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of projects executed/# of projects in the action plan) | Target achieved | 100% (4/4) | N/A | N/A | Internal Audit report to Audit and Performance Audit Committee | MM
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | 7 | 7 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | N/A | N/A | Minutes, Attendance register, invitations | MM
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | 4 | 4 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | N/A | N/A | Council resolution, Attendance register | MM
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 2 | 2 | IAA and APAC Assessment report | Organize IAA and APAC Assessment report and submit to council | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Report, Council Resolution | MM
Information Technology | Good governace and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Manual system | Computerized call center system | Upgrade municipal call center | Upgrade municipal call center from manual system to computerized logging, recording and referencing system and audio recording system according to needs of business units Phase 1 2015/2016 - the logging and referencing system Phase 2 - Audio recording system for 2016/2017 | Civic Center |  | Income | R3000,000 | 0 | 0 | 1/7/2015 | 31/3/2016 | Municipal call centre adjusted during adjustment | Municipal call centre adjusted during adjustment | Municipal call centre adjusted during adjustment | Municipal call centre adjusted during adjustment | Municipal call centre adjusted during adjustment | Advertisement for RFP | CORP
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 december 2015 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Increase speed of server output to networks for data transfer between workstations and servers | Civic Center and regional offices |  | Income | R200,000 | 159226 | 159225.99 | 1/7/2015 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Orders, Payment certificate and intallation report | CORP
Information Technology | Good governace and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Phase 1 done | Complete server upgrade project | Upgrade of servers | Complete upgrade of servers - expansion of data centre server | Civic Center |  | income | R200,000 | 148958 | 148957.93 | 1/7/2015 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Appointment letter, Project agreement, installation report and payment certicate | CORP
Information Technology | Good governace and Administrative Excellence | To upgrade the internet dataline by 31 March 2016 | Existing dataline too slow | Internet dataline upgraded | Internet dataline upgrade | Upgarde the internet dataline to optimise speed for offsite backups and internet use. (Changed from Upgrade of TMS) | Civic center |  | Income | R150,000 | R150,000 | 0 | 1/7/2015 | 31/3/2016 | TELKOM complete the upgarde and payment out | Target achieved | TELKOM completed the upgarde and payment was done | None | None | Approved memorandum, TELKOM agrement, Close out report, Proof of payment | CORP
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Replace UPS in server room | Upgrade of server room by removing carpets and workstation equipment | Civic Center |  | Income | R70,000 | 161816 | 145362.23 | 1/7/2015 | 31/3/2016 | Signing off, sign service mantainance plan | Target achieved | Signing off, sign service mantainance plan completed | None | None | Approved memorandumpurchase order, signed service mantainance plan | CORP
Information Technology | Good governace and Administrative Excellence | To procure video editing software by 31 December 2015 | N/A | Procure video editing software | Procure video editing software | Procure Video Editing software suitable for use by business process owner | Civic Center |  | Income | R10,000 | 14500 | 14500 | 1/7/2015 | 2015-01-12 | N/A | N/A | N/A | N/A | N/A | Appointment letter, Installation, report; payment certificates, | CORP
Information Technology | Good governace and Administrative Excellence | To procure ICT office equipment 31 March 2016 | 2014/15 critical needs only | According to needs analysis | Procure ICT office equipment | Procure laptops, computers, printers and desktops according to accurate needs analysis | Civic Center |  | Income | R200,000 | 155500 | 17234.54 | 1/7/2015 | 31/12/2015 | Receive ordered equipments and allocate to users | Target not achieved | Receive ordered equipments and allocate to users not done | Quotation Committee not yet signed off - awaiting to sign off in April 2016 | Document to be signed in the 4th quarter. | Appointment letter, Orders, payment certificates and Asset Register | CORP
Information Technology | Good governace and Administrative Excellence | To procure hand held communication radios 30 September 2015 | N/A | 2 | Hand held communication radios | Procure two (2) hand held communication radios for registry staff to communicate | Civic Center |  | Income | R10,000 | R10,000 | 0 | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Appointment letter, payment certificates, | CORP
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 2 | Target achieved | 5 | None | None | Minutes, Attendance register, notice of invitations. | CORP
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 6 | Target achieved | 8 | None | None | Minutes, Attendance register, notice of invitations. | CORP
Communication | Good governace and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | N/A | 2 | Television sets | Procure and install television sets in the Office of the Speaker and the Office of the Chief Whip | Civic Center |  | Income | R20,000.00 | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP
Communication | Good governace and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | N/A | 2 | Decoders | Procure and install decoders for DSTV in the Office of the Speaker and the Office of the Chief Whip | Civic Center |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Decoders and payment certificates | CORP
Communication | Good governace and Administrative Excellence | To procure 2 X radios of regional broadcasting stations BY 30 June 2016 | N/A | 2 | Radios | Procure radios for regional broadcasting services that also have a recording function | Civic Center |  | Income | R800.00 | 2656 | 1785.6 | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Radios and payment certificates | CORP
Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Reviewed Bathopele service standards | Review the 2014/15 ed Makhado Bathopele Service Standards and submit to Council for approval | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Approved 2015 Batho Pele Service Standards | CORP
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Comprehensive website policy | Develop website policy for approval by Council | Civic Center |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Council approval of policy | CORP
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality |  | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | None | None | Attendance register and Programme | CORP
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Imbizo Feedback Session | Giving Feedback to community on service delivery issues raised during 2014/2015 financial year | Makhado Municipality | All wards | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Attendance register and program | CORP
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework BY 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | Income | Ward 20 | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Approved Stakeholders management Framework and council resolution | CORP
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | Income | Ward 20 | Income | OPEX | OPEX | OPEX | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Approved Communication strategy and council resolution policy and council resolution | CORP

## LSDBIP ANALYSIS
DEPARTMENT | NO OF INDICATOR | TARGET ACHIEVED | TARGET NOT ARCHIEVED | NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Performance Management | 3 | 3 | 0 | 0
Human Resources and Organizational Development | 2 | 2 | 0 | 0
Special Programs | 2 | 2 | 0 | 0
Spatial and Town Planning | 16 | 15 | 1 | 0
TOTAL | 23 | 22 | 1 | 0
|  | 95.65% | 4.545% | 0%
95.65%
BASIC SERVICE DEVELOPMENT
Disaster Management | 1 | 1 | 0 | 0
Library Services | 1 | 1 | 0 | 0
Waste Management | 2 | 2 | 0 | 0
Parks and Recreation | 4 | 3 | 0 | 1
Electricity Provision | 31 | 19 | 7 | 5
Roads, Bridges and Storm water | 6 | 2 | 2 | 3
Sports Facilities | 2 | 2 | 0 | 0
Building and Construction | 4 | 2 | 2 | 0
TOTAL | 51 | 32 | 11 | 9
|  | 62.75% | 21.57% | 17.65%
80.39%
MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Revenue Management | 1 | 1 | 0 | 0
Budget and Reporting | 4 | 2 | 0 | 2
Supply Chain Management | 2 | 1 | 1 | 0
Asset Management | 1 | 1 | 0 | 0
TOTAL | 8 | 5 | 1 | 2
|  | 62.5% | 12.5% | 25%
87.5%
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 3 | 0 | 0 | 3
TOTAL | 3 | 0 | 0 | 3
|  | 0% | 0% | 100%
100%
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Fraud and Anti - Corruption | 1 | 1 | 0 | 0
Public Participation | 7 | 3 | 1 | 3
Policies and By Laws | 1 | 1 | 0 | 0
Internal Auditing | 6 | 3 | 0 | 3
Information Technology | 8 | 2 | 1 | 5
Council Services | 2 | 2 | 0 | 0
Communication | 5 | 0 | 0 | 5
TOTAL | 30 | 12 | 2 | 16
|  | 40% | 40% | 53.33%
93.33%
|  |  | MTOD | 95.65%
|  |  | BSDID | 80.39%
|  |  | LED | 100%
|  |  | MFMV | 100%
|  |  | GGPP | 93.33%
469.4%
93.88%
|  |  | CONVERTED TO INDIVIDUAL PERFORMANCE | 84.10 X 167 / 100
156.8%

## HSDBIP ANALYSIS
DEPARTMENT | NO OF INDICATOR | TARGET ACHIEVED | TARGET NOT ARCHIEVED | NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | 1 | 1 | 0 | 0
Performance Management | 1 | 0 | 0 | 1
Human Resources and Organizational Development | 4 | 2 | 0 | 2
Spatial and Town Planning | 1 | 0 | 1 | 0
TOTAL | 7 | 3 | 1 | 3
|  | 42.86% | 14.29% | 42.86%
85.71%
BASIC SERVICE DEVELOPMENT
Waste Management | 1 | 1 | 0 | 0
Parks and Recreation | 1 | 0 | 0 | 1
Electricity Provision | 1 | 1 | 0 | 0
Roads, Bridges and Storm water | 1 | 1 | 0 | 0
Sports Facilities | 2 | 2 | 0 | 0
Building and Construction | 1 | 0 | 0 | 1
TOTAL | 7 | 5 | 0 | 2
|  | 71.43% | 0% | 28.57%
100%
MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | 4 | 4 | 0 | O
Revenue Management | 1 | 0 | 1 | 0
TOTAL | 5 | 4 | 1 | 0
|  | 80% | 20% | 0%
80%
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 3 | 0 | 0 | 3
TOTAL | 3 | 0 | 0 | 3
|  | 0% | 0% | 100%
100%
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | 1 | 1 | 0 | 0
Policies and By Laws | 1 | 0 | 0 | 1
Internal Auditing | 1 | 0 | 0 | 1
Information Technology | 1 | 0 | 1 | 0
Council Services | 1 | 1 | 0 | 0
Communication | 1 | 0 | 0 | 1
Public Participation | 6 | 2 | 1 | 3
|  | 33.33% | 16.67% | 50%
83.33%
|  | MTOD | 85.71%
|  | BSDID | 100%
|  | LED | 100%
|  | MFMV | 100%
|  | GGPP | 83.33%
469%
93.81%
|  | CONVERTED TO INDIVIDUAL PERFORMANCE | 84.10 X 167 / 100
156.7%