## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
1ST QUARTER REPORT
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER/ORGANISATIONAL LEVEL)
FOR
2016/2017 FINANCIAL YEAR

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vision and Mission
3. Departments
4. Higher Level SDBIP
5. Lower SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc Service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. Monthly Cashflow
7. Monthly Revenue and Expenditure
8. Monthly Capital Expenditure
9. Mothly Expenditure by Vote
10. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1) of MFMA states that On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must—
(a) consider the statement or report;
(b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan;
(c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget;
(d) issue any appropriate instructions to the accounting officer to ensure—
(i) that the budget is implemented in accordance with the service delivery
and budget implementation plan; and
(ii) that spending of funds and revenue collection proceed in accordance
with the budget;

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## ANALYSIS (hidden)
FIRST QUARTER ANALYSIS REPORT 2016/17 FY
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
FIRST QUARTER ANALYSIS REPORT 2016/17
Integrated Development Planning | 1 | 0 | 1 | 0
Performance Management | 4 | 2 | 1 | 1
Human Resources and Organizational Development | 8 | 4 | 1 | 3
Special Programs | 2 | 1 | 1 | 0
Spatial and Town Planning | 21 | 20 | 1 | 0
| 36 | 27 | 5 | 4
TOTAL |  | 75% | 13.89% | 11.11%
86.11%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | 1 | 1 | 0 | 0
Library Services | 1 | 0 | 1 | 0
Waste Management | 3 | 1 | 1 | 1
Parks and Recreational | 5 | 1 | 3 | 1
Protection Services | 1 | 0 | 1 | 0
Electrical Provision | 30 | 20 | 9 | 1
Roads, Bridges and Storm water | 11 | 3 | 8 | 0
Building & Construction | 9 | 6 | 3 | 0
| 61 | 32 | 26 | 3
TOTAL |  | 52.46% | 42.62% | 4.918%
57.38%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL FINANCE AND MANAGEMENT AND VIABILITY
Expenditure management | 4 | 3 | 0 | 1
Revenue Management | 2 | 1 | 0 | 1
Budget and Reporting | 4 | 3 | 0 | 1
Supply Chain Management | 1 | 0 | 0 | 1
Asset Management | 1 | 1 | 0 | 0
| 12 | 8 | 0 | 4
TOTAL |  | 66.67% | 0 | 33.33%
100%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 3 | 1 | 0 | 2
TOTAL | 3 | 1 | 0 | 2
|  | 33.33% | 0% | 66.67%
100%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | 4 | 3 | 0 | 1
Fraud and Anti - Corruption | 1 | 1 | 0 | 0
Policies and By Laws | 3 | 2 | 0 | 1
Public Participation | 7 | 4 | 2 | 1
Internal Auditing | 6 | 2 |  | 4
Information Technology | 11 | 6 | 4 | 1
Council Services | 3 | 3 | 0 | 0
Communication | 3 | 3 | 0 | 0
| 38 | 24 | 6 | 8
TOTAL |  | 63.16% | 15.79% | 21.05%
84.21%
OVERALL PERFORMANCE | 85.4%

## HIGH LEVEL SDBIP
4. HIGHER LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward/Dept | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End Date | 1st Q Target | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | IDP Review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Complete the IDP analysis phase and conduct the IDP representative forum. | Target not achieved | Complete the IDP analysis phase not done and the IDP representative forumnot conducted | Delays in the establishement of the ward committes which had to make inputs on the draft anaylsis | Meesting is scheduled to the second week of November | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2017/2018 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2016/2017 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2017/2018 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2016 | 165 | 135 | Training | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | 70 | Target not achieved | 51 employees trained through WSP | Delays in the appointment of the service provider | Other employees to be trained before end of second quarter | Proof of attendance | CORP | 3
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2016 | 16 | 16 | Training | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Proof of attendance | CORP | 4
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Organogram review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Minutes and attendance register, Council resolutions, | CORP | 5
Human Resources and Organizational Development | Invest in human capital | To review the HR Strategy by 30 June 2016 | HR Strategy in place | HR Strategy reviewed | HR Strategy review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Appointment of facilitator, Development of terms of reference | Target achieved | Appointment of facilitator done, Development of terms of reference done | None | None | Appointment letter, Draft HR Strategy, Approved HR Strategy, Council resolution | CORP | 6
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | 4 | 4 | Recruitment in terms of EE Plan | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Appointment letters | CORP | 7
Spatial and Town Planning | Advance Spatial Planning | % achievements of spatial programs indicators/targets per quarter | 100% (21/21) | 100% (21/21) | Permission to Occupy | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 100% (16/16) | Target achieved | 100% (21/21 achievements of spatial programs indicators/targets per quarter | None | None | Activity reports | DEVP | 8
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Makhado Town, Tshikota Township, Vleifontein, Waterval Township, Dzanani township, Vuwani Township, Kutama-Sinthumule Area, Brambos | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | 2016-01-07 | 30/6/2017 | 19149 (non cumulaitve) | Target achieved | 19149 (non cumulaitve) | None | None | Proof of collection from the affected stakeholders. | MM and COMM | 9
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2017 | 3 | 3 | Development of Parks | 5047 park,Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 0 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Approval memo. RFP, appointment letter, Completion certificate | COMM | 10
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2017 | 1180 | 1100 | Electrification of households | Magau, Tshiozwi, Ramantsha, Madodonga,Mamburu, Makushu, Wisagalaza, Sukani, Mamburu, Gogobole, Tshivulana, Ratombo, Fredom, Lusaka, Tshivhuyuni. | Ward 23,25,03 | INCOME | 21824299 | 10655357 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Proof of connections to targeted households | MM and TECH | 11
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads tarred by 30 June 2017 | 18.9km | 49.9km | Upgrading of roads | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 78199143.67 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Project progress report, Certificate of completion | TECH | 12
Sports Facilities | Accessible basic and infrastructure services | To construct Tshivhuyuni sports and recreational facilities by 30 June 2017 | N/A | Construction of Tshivhuyuni sports and recreational facilities completed | Construction of Tshivhuyuni sports and recreational facilities | Makhado Municipality | Ward 12 | MIG | 600000 | -42376 | 2016-01-07 | 30/6/2017 | Develop terms of ref and submit to SCM |  |  |  |  | Terms of ref, Advert, Designs, Appointment letter for consultants | TECH | 13
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | Aministration | Income | 163938800.12 | 27694053.57 | 2016-01-07 | 30/6/2017 | 10% | Target achieved | 17% Capital budget spent | None | None | Quarterly Financial Report | MM and All Directors | 15
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | Aministration | Income | 112264000 | 13016469.49 | 2016-01-07 | 30/6/2017 | 10% | Target achieved | 16% MIG spent | None | None | Quarterly Financial Report | MM | 16
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | Aministration | Income | 17000000 | 11024714.32 | 2016-01-07 | 30/6/2017 | 10% | Target achieved | 61% INEP spent | None | None | Quarterly Financial Report | MM | 17
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Makhado Municipality | Aministration | Income | 1600000 | 1600000 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Expenditure Report | B&T | 18
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | Aministration | Income | 342227123 | 68296459.88 | 2016-01-07 | 30/6/2017 | 20% | Target achieved | 22% revenue collected | N/A | N/A | Section 71 report (c1 schedule) | B&T | 19
Budget and Reporting | Sound Financial Management and viability | To obtain unqualified audit opinion by 31 December 2015 | Unqualified audit opinion | Unqualified audit opinion obtained | Auditing of financial statements | Makhado Municipality | Aministration | Income | Opeartional | Operational | 2016-01-07 | 31/12/2016 | Develop financial statement and submit to AG | Target achieved | Financial Statements compiled and submitted to AG 31 August 2016 | None | None | AG report | B&T | 14
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created | 800 | 800 | LED job opportunities | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 20
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governace and Administrative Excellence | # of risk activities cordinated by 30 June 2016 | 13 | 13 | Risk Management activities | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 2 | Target achieved | 2 | None | None | Risk Management Register and Reports | MM | 21
Policies and By Laws | Good governace and Administrative Excellence | # of bylaws to be reviewed by 30 June 2016 | 4 | 6 | Reviewing of Municipal By-laws | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Council resolutions, Copies of approved by laws. | CORP | 22
Internal Auditing | Good governace and Administrative Excellence | No of internal audit indicators/ activities/ projects implemented by 30 June 2016 | 6 | 8 | Internal Audit projects | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 23
Information Technology | Good governace and Administrative Excellence | No of IT projects implimented by 30 June 2016 | 8 | 8 | IT Projects | Civic Center | Aministration | Income | R3000,000 | #VALUE! | 2016-01-07 | 30/6/2017 | 2 |  |  |  |  | Advertisement for RFP | CORP | 24
Council Services | Good governace and Administrative Excellence | # of Council meetings convened by 30 June 2016 | 15 | 6 | Council meetings | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 1 | Target achieved | 4 council meeting convened | None | None | Minutes, Attendance register, notice of invitations. | CORP | 25
Communication | Good governace and Administrative Excellence | No of communication indicators/activities/projects implemented by 30 June 2016 | 5 | 5 | Communication projects | Civic Center | Ward 20 | Income | R20,000.00 |  | 2016-01-07 | 30/6/2017 | 2 | Target achieved | 2 communication project achieved | None | None | TVs and payment certificates | CORP | 26
Public Participation | Good governace and Administrative Excellence | No of public participation indicators/activities/projects implemented by 30 June 2016 | 7 | 6 | Public Participation | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 3 |  |  |  |  | Attendance register and Programme | CORP | 27

## LMTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End Date | 1st Q Target | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2016/2017 financial year by 31 May 2017 | IDP review for 2015/2016 was completed and approved by Council before 31 May 2015 | IDP review for 2016/2017 completed and approved by Council by 31 May 2017 | IDP Review | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Complete the IDP analysis phase and conduct the IDP representative forum. | Target not achieved | Complete the IDP analysis phase not done and the IDP representative forum not conducted | Delays in the establishement of the ward committes which had to make inputs on the draft anaylsis | Meeting is scheduled to the second week of November | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | INCOME | Operational | Operational | 1/4/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2017 | 8 | 8 | Quarterly performance reports | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 (Draft Annual Report 2015/2016 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 | Target achieved | 2 (Draft Annual Report 2015/2016 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 developed | None | None | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 3
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2015 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% | Performance agreements | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% | Target achieved | 100% (6/)6) all section 57 managers signed performance agreements | None | None | Signed Performance Agreements | MM | 4
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2015 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 (Annual Assessment 2015/2016) | Target not achieved | 1 (Annual Assessment 2015/2016) not conducted | Familiarising new council with the assesment process | Annual Assessment 2015/2016) to be done during 3rd Quarter | Scorecards, Attendance Register | MM | 5
Human Resources and Organizational Development | Invest in human capital | To fill all (100%) posts in terms of the approved priority list by 30 June 2017 | 25 employees were appointed, 8 interns appointed. | 100% prioritised post filled | Personnel Recruitment | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Submit an item to council for decision regarding the advertised posts. | Target Achieved | An item was submitted to Council regarding decision on the advertised posts. | None | None | Advertisement, Shortlisting reports, Interview reports and Appointment letters, Council resolution | CORP | 6
Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2017 | 6 events | 6 events | Employee Assistance Campaigns | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 events | Target Achieved | 2 events held | None | None | Invitations, attendance registers and close-out report | CORP | 7
Human Resources and Organizational Development | Invest in human capital | To develop 5 outstanding HR policies by 30 June 2017 | No transfer policy, Outdatded EAP, Placement, Standby and Induction Manaual | Transfer policy, EAP policy, Placement policy, Stanby Allowance policy, Induction manual | Review and Development of HR policies | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Development of 3 draft policies | Target Achieved | 3 draft policies were developed (Overtime ,EAP and Inducion manual) | None | None | Council resolutions, Draft and Final policy documents | CORP | 8
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2017 | 10 bursaries were awarded in 15/16 | 15 bursaries awarded | External Bursary Award | Makhado Municipality | INCOME | 450000 | 0 | 1/7/2016 | 30/6/2017 | Establish new bursary committee | Target Achieved | Bursary Committee was established | None | None | Advert, List of qualifying leaners and Letters of bursary awards | CORP | 9
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2017 | 49 events done in 15/16 | 43 events done | Special Programs | Makhado Municipality | INCOME | 600000 | 0 | 1/7/2016 | 30/6/2017 | 17 | Target not Achieved | 7 events were held | Election of the new council | Remaining events to be held during 2nd quarter | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 10
Spatial and Town Planning | Advance Spatial Planning | To purchase Plan Print Machine for Building Section by 31 March 2017 | Old Machine | Plan Print Machine for Building Section purchased | Plan Print Machine | Makhado Municipality | INCOME | 250000 | 0 | 1/7/2016 | 31/12/2016 | Develop Specification and submit to supply chain management unit. | Target Achieved | Develop Specification and submit to supply chain management unit done | None | None | Specifications, Advertisement, Proof purchase | DEVP | 11
Spatial and Town Planning | Advance Spatial Planning | To finalise the extension of Civic Centre by 31 December 2016 | New building | Extension of Civic Centre finalized | Extension of Civic Centre | Makhado Municipality | INCOME | 100000 | 0 | 1/7/2016 | 31/12/2016 | Paving of the surrounding building | Target not Achieved | Paving of the surrounding building not done. Only specification was done | Delay in SCM | To be done in the Second Quarter | Project Report | DEVP | 12
Spatial and Town Planning | Advance Spatial Planning | To finalize the New Disaster centre -Erf 235 30 June 2017 | New building | New Disaster centre -Erf 235 finalized | New Disaster centre -Erf 235 | Makhado Municipality | INCOME | 500000 | 0 | 1/7/2016 | 31/12/2016 | Finalise Roofing | Target Achieved | Finalise Roofing done | None | None | Project Report | DEVP | 13
Spatial and Town Planning | Advance Spatial Planning | To purchase 18 x Aircons for new offices by 31 March 2017 | New building | 18 x Aircons for new offices purchased | 18 x Aircons for new offices | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 31/12/2016 | Purchase aircons needed for 1st quarter | Target Achieved | Purchase aircons needed for 1st quarter done (18) | None | None | Proof of purchase and installation | DEVP | 14
Spatial and Town Planning | Advance Spatial Planning | To purchase 2 x Theodolities for Survey Technician by 31 March 2017 | New | 2 x Theodolities for Survey Technician purchased | 2 x Theodolities for Survey Technician | Makhado Municipality | INCOME | 100.000.00 | 0 | 1/7/2016 | 31/12/2016 | Develop Specification | Target Achieved | Develop Specification done | None | None | Specifications, Advertisement, Delivery note. | DEVP | 15
Spatial and Town Planning | Advance Spatial Planning | Upgrading of Dzanani Traders Market 30 June 2017 | N/A | Upgrading of Dzanani Traders Market | Upgrading of Dzanani Traders Market | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 31/12/2016 | Develop Specification for designs and erection of market stalls | Target Achieved | Develop Specification for designs and erection of market stalls done | None | None | Designs, Specifications, Advertisement, Appointment letter | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | Development of informal business area Ext 12 by 30 June 2017 |  | Informal business area Ext 12 developed by 30 June 2017 | Development of informal business area | Makhado Municipality | INCOME | 3000000 |  | 1/7/2016 | 30/06/2017 | Design the plans internally. Develop specifications for tender advertisement | Target Achieved | Design the plans internally. Develop specifications for tender advertisement | None | None | Designs, Specifications, Advertisement, Appointment letter | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of application received/(# of application attended to within 90 days). | Target Achieved | 100% 40 /40 applications received and attended to. | None | None | Site inspection report, Register of applications | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of housing queries attended within 30 days/# of received) | Target Achieved | 100% (35/35) 35 title deeds issued and 16 correspondences written(100%) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2015 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of building plans assessed/# of building plans received) | Target Achieved | 100% (60/60) 60 Building Plans received and assessed | None | None | Building plans register | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | Target Achieved | 100% (20/20) 20 applications rceived and processed | None | None | Zoning certificates issued | DEVP | 20
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | Target Achieved | 100% (18/18) 18 Category two applications processed(100%) | None | None | EXCO resolutions | DEVP | 21
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Target Achieved | (100%) (9/9) 9 application for land use rights inspection conducted | None | None | Site inspection report, Register of applications | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2015 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achieved | (100%) (7/7) 7 applications received and processed | None | None | Copy of occupancy certificates issued | DEVP | 23
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achieved | 100% (49/49) 49 ervens and Dzanani Township Ext 2 | None | None | Application Assessment Report, Register of applications | DEVP | 24
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Makhado Municipality | INCOME | 1000 000 .00 |  | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target Achieved | (100%) (10/10) 10 applications processed | None | None | Application Assessment Report, Register of applications | DEVP | 25
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achieved | 100% (47/47) 47 applications processed | None | None | Application Assessment Report, Register of applications | DEVP | 26
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of queries processed/# of queries received) | Target Achieved | 100% (1/1) of queries processed | None | None | Correspondence letters and emails. | DEVP | 27
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target Achieved | 100% (6/6) 6 Building Control and (7/7) 7 Town Planning contravention notices issued | None | None | Duplicate notices | DEVP | 28
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2015 | 240 | 240 | Routine Inspection | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 60 routine inspection | Target Achieved | 60 routine inspection done | None | None | Inspection form, Register | DEVP | 29
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Target Achieved | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | None | None | Inspection form, Register | DEVP | 30
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2017 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 30/6/2017 | Proposed names | Target Achieved | Proposed names done | None | None | Expenditure Report | DEVP | 31

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location/Ward | Funding Source | Budget 16/17 R'000 | Expenditure | 1st quarter | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio of Evidence | DEPT | Indicator No
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2017 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Makhado Municipality | INCOME | Operational | Operational | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers | Target achieved | Request letter to sector departments and municipal regional offices done. Requesting information about new buildings and new employees in key positions e.g circuit managers | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 32
Library Services | Promote community and environmental welfare | To refurbish the library roof by 30 June 2017 | Roof damaged | Refurbishment of the library building completed | Refurbish library building | Makhado Municipality | INCOME | 1200000 | 0 | Development of specifications, Advertisement for Contractor | Target not achieved | Terms of refernce developed and submitted to SCM for advertisement | Conveting the tender document to be in line with CIDB standard as requested by SCM | To be advertised in the 2nd quarter | Project Progress report | TECH/COMM | 33
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal by 30 June 2017 | 46637 | 19149 | Waste Management | Ward 22, 23, 24, 25, 26. | INCOME | Operational | Operational | N/A | N/A | N/A | N/A | N/A | Monthly collection reports | COMM | 34
Waste Management | Promote community and environmental welfare | To rehabilitate the existing landfill site by 31 March 2017 | New | Existing Landfill site rehabilitated completed | Rehabilitation of the existing Landfill site | Makhado Municipality | INCOME | 3000000 | 0 | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. | Target not achieved | Write memorandum of approval to MM done. Development of specifications and submit to the BSC done. Advertisement of the tender not done. Evaluation a nd Adjudication of tenders not done. Appointment of a service provider not done. | Delays in supply chain | Advertisement to be done during second quarter | Completion certificate | COMM | 35
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Development of Landfillsite | Makhado Municipality | MIG | 5 000 000.00 - |  | Approval to commence with the project from the MM, Development of specification and submit to SCM. |  |  |  |  | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM | 33 | Rollover project
Parks and Recreation | Promote community and environmental welfare | To develop E59 and E60 Park (Makhado Town) by 30 June 2017 | Development | Development of E59 and E60 Park (Makhado Town) completed | Development of E59 and E60 Park (Makhado Town) | Makhado Municipality | INCOME | 400000 | 0 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Target not achieved | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender not done. | Delays in supply chain | Advertisement to be done during second quarter | Approval memo, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | To develop Dzanani Park next to Shopping Mall by 30 June 2017 | N/A | Development of Dzanani Park next to Shopping Mall completed | Development of Dzanani Park next to Shopping Mall | Makhado Municipality | INCOME | 200000 |  | Approval to commence with the project from the MM. Request for proposal from service providers. |  |  |  |  | Approval memo. RFP, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | Refurnishment and fencing Eltivillas Swimming Pool by 30 June 2017 | N/A | Refurnish and fencing Eltivillas Swimming Pool completed | Refurnish and fencing Eltivillas Swimming Pool | Makhado Municipality | INCOME | 150000 |  | Approval to commence with the project from the MM. Request for proposal from service providers. |  |  |  |  | Approval memo. RFP, appointment letter, Completion certificate | COMM
Parks and Recreation | Promote community and environmental welfare | To refurbish Potgieter Park by 30 June 2017 | Refurbishment | Refurbishment of Potgieter Park completed | Refurbishment of Potgieter Park | Makhado Municipality | INCOME | 300000 | 0 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Target not achieved | Approval to commence with the project from the MM done. Development of specifications and submit to the SCM done. Advertisement of the tender not done. | Delays in supply chain | Advertisement to be done during second quarter | Approval memo, appointment letter, Completion certificate | COMM | 37
Parks and Recreation | Promote community and environmental welfare | To construct Tshikota cemetery ablution facilities by 30 June 2017 | No ablution facilities | Construction of Tshikota cemetery ablution facilities completed | Construction of Tshikota cemetery ablution facilities | Makhado Municipality | INCOME | 200000 | 0 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Target achieved | Approval to commence with the project from the MM done. Development of specifications and submit to the SCM done . Advertisement of the tender done. | None | None | Approval memo, appointment letter, Completion certificate | COMM | 38
Protection Services | Promote community and environmental welfare | To purchase special Garage Roller Door for VTS and 2x 30m long chains |  | Special Garage Roller Door for VTS and 2x 30m long chains | Special Garage Roller Door for VTS and 2x 30m long chains | Makhado Municipality | INCOME | 800000 |  | N/A |  |  |  |  | Specifications, Advertisement, Appointment letter, delivery note | TECH
Parks and Recreation | Promote community and environmental welfare | To pave open Erf 1 -N1 by 30 June 2017 | New | Paving of open Erf 1 -N1 completed | Paving open Erf 1 -N1 | Makhado Municipality | INCOME | 1000000 | 0 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Target not achieved | Approval to commence with the project from the MM done. Development of specifications and submit to the SCM done. Advertisement of the tender not done. | Budget constraints (Insufficient budget) | To be adjusted | Approval memo, appointment letter, Completion certificate | COMM | 39
Protection Services | Promote community and environmental welfare | Establishment of Watervaal Registering Authority by 31 December 2017 | New | Establishment of Watervaal Registering Authority completed | Establishment of Watervaal Registering Authority | Waterval Traffic Station | INCOME | 200000 | 0 | Approval from the MM. Development of specification and submit to supply chain management | Target not achieved | Approval from the MM. Development of specification and submit to supply chain management | The Dept of transport delays on giving the quote to the municipality so that they can pay for the computer to be used in the Waterval station | Follow up letter has been written to the Provincial to request for a quote | Purchase order | COMM | 40
Electricity Provision | Accessible basic and infrastructure services | To replace air conditioner by 30 September 2016 | New | Air Conditioners replaced | Air Conditioners | Makhado | INCOME | 150000 | 0 | Evaluate ,adjudicate and appoint service provider | Target achieved | Evaluate ,adjudicate and appoint service provider done | None | None | Advertisement , Adjudication minutes, appointment letter and Job Cards | TECH | 41
Electricity Provision | Accessible basic and infrastructure services | To purchase CT VT Units 11kv and 22kv by 30 June 2017 | New | CT VT Units 11kv and 22kv | CT VT Units 11kv and 22kv | Makhado | INCOME | 400000 | 0 | Specification, advertisement | Target not achieved | Specification done, advertisement not done | The department is changing the initial specification | The advert to be out by October end |  | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To procure Mini Subs by 31 March 2017 | New | Mini Subs replaced | Mini Subs | Makhado | INCOME | 700000 | 0 | Specification, advertisement | Target achieved | Specification, advertisement done | None | None | Specification, orders, GRV | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | To procure MV Cable 70 mm 11kv by 31 March 2017 | New | MV Cable 70mm 11kV procured | MV Cable 70mm 11kV | Makhado | INCOME | 500000 | 0 | Specification, ,requisition and orders | Target not achieved | Specification, and requisition and orders not done | To ammend the project | To be ammend to ring main units | Specification, orders, GRV | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | To purchase strategic spares by 31 March 2017 | New | Strategic spares | Strategic spares | Makhado | INCOME | 200000 | 0 | Develop specification, | N/A | N/A | N/A | N/A | Specification, orders, GRV | TECH | 45
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2017 | New | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Makhado | INCOME | 5000000 | 0 | Specification,advetisement | Target achieved | Specification,advetisement done | None | None | Specification, orders, GRV | TECH | 46
Electricity Provision | Accessible basic and infrastructure services | To upgrade Shefeera Line by 30 June 2017 | Upgrade | Upgrade Shefeera Line | Upgrade Shefeera Line | Makhado Municipality | INCOME | 300000 | 0 | Specification,advetisement | Target achieved | Specification,advetisement done | None | None | List of Labourer, Completion certificate | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute Beaufort West line by 30 June 2017 | Upgrade | Reroute of Beaufort West line upgraded | Upgrade and reroute Beaufort West line | Beaufort West line | INCOME | 1000000 | 0 | Specification,advetisement and evaluation | Target not achieved | Specification,advetisement and evaluation not done | Delays in SCM process | to be evaluated before the end of the second quarter | Desings , Advertisement, Adjudication minutes and completion certificate | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs 6km by 30 June 2017 | Upgrade | Reroute transmission line 66kV bulk supply to Levubu and Beaufort subs upgraded | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs | Makhado Municipality | INCOME | 8000000 |  | Advertisement for Engineer |  |  |  |  | Advertisement, adjudication minutes and appointment letters and completion certificate | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To upgrade urban substation by 30 June 2017 | Upgrade | Urban substation upgraded | Upgrade urban substation | Makhado Municipality | INCOME | 5000000 | 0 | Complete palisade fencing and renovate substation building. Order switch gear. Lead time for overseas delivery | Target not achieved | Complete palisade fencing not done and renovate substation building done. Order switch gear done. Lead time for overseas delivery | Change of palisade | To re design the specification of palisade fencing | Progress report handover and Completion certificate |  | 49
Electricity Provision | Accessible basic and infrastructure services | Upgrading bulk supply Tshituni 2.5MVA by 30 June 2017 | Upgrade | Upgrading bulk supply Tshituni 2.5MVA | Upgrading bulk supply Tshituni 2.5MVA | Makhado Municipality | INCOME | 3000000 | 89043.86 | Letter of request to Eskom for feasibility quote | Target achieved | Letter of request to Eskom for feasibility quote sent | NB: Amended the project to include the NMD60MVA standards supply upgrade of the main station | To be adjusted | Application letter, and feasibility quate | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To upgrade Mountain line by 30 June 2017 | Upgrade | Mountain line upgraded | Upgrading Mountain line | Makhado Municipality | INCOME | 300000 | 0 | Plant poles ph2 from Levubu road to Roodewal sub | Target not achieved | Plant poles ph2 from Levubu road to Roodewal sub not done | Wrong Interpretation of servitude | To be completed before the end of December | List of Labourer, Completion certificate | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To transform oil purification by |  | transform oil purification | transforming oil purification | Makhado Municipality | INCOME | 350000 | 0
Electricity Provision | Accessible basic and infrastructure services | To replace outdoor Curcuit breaker by 30 June 2017 | New | Outdoor curcuit breaker replaced | Circuit breaker | Makhado | INCOME | 1000000 | 0 | Specification and Advertisement | Target not achieved | Specification done and Advertisement not done | Delays in SCM processes | To be completed before the end of December | Advertisement,Adjudication minutes appointment letter, Completion certificate | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2017 | New | Replacement of channel cover completed | Substation channel cover replacements | Makhado | INCOME | 250000 | 0 | Specification and Advertisement | Target achieved | Specification and Advertisement done | None | None | Advert, evaluation minutes, Purchase order | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | Purification of transformer oil by 30 June 2017 | N/A | Transformer oil purified | Transformer oil | Makhado | INCOME | 350000 | 0 | Specification and Advertisement | Target achieved | Specification and Advertisement done | None | None | Specs, Ads, evaluatiion & adjudication minutes. Appointment letter. Order. | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | To renovate Substation control room by 30 June 2017 | N/A | Substation control room renovated | Substation control room renovations | Makhado Municipality | INCOME | 100000 | 0 | Specification and Advertisement | Target achieved | Specification and Advertisement done | None | None | Advert, evaluation minutes, Purchase order | TECH | 55
Electricity Provision | Accessible basic and infrastructure services | To Service OCB's substation by 30 June 2017 | N/A | Service OCB's | Service OCB's | Makhado Municipality | INCOME | 200000 | 0 | Specification and Advertisement | Target achieved | Specification and Advertisement done | None | None | Advert, evaluation minutes, Purchase order | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To refurbish Transformer in (Levubu) by 30 June 2017 | N/A | Transformer refurbished (Levubu) | Transformer refurbishment (Levubu) | Makhado Municipality | INCOME | 600000 | 0 | Specification and Advertisement | Target achieved | Specification and Advertisement done | None | None | Advert, adjudication minutes, Completion certificate | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | Post connection Own licensed areas by 30 June 2017 | N/A | Post connection Own licensed areas | Post connection Own licensed areas | Makhado Municipality | INCOME | 2000000 | 0 | Appoint contractor and site handover | Target achieved | Appoint contractor and site handover done | None | None | Appointment letter, project progress report, completion certificate | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village connection completed | Wisagalaza 2 & Chitasi village | Wisagalaza village | INEP/ | 7771500 |  | Appointment of contractor's labour, surveying of poleholes, excarvating poleholes |  |  |  |  | Appointment letter, project progress report, completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Tshikhwani/ Rathidili by 30 June 2017 | New Connetion | Tshikhwani/ Rathidili connection completed | Tshikhwani/ Rathidili | Tshikhwani/ Rathidili | INEP/INCOME | 1923404.67 | 827318.16 | Appoint engineer, capacity verification and designs | Target achieved | Appoint engineer, capacity verification and designs done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Maname Paradise by 30 June 2017 | New Connetion | Maname Paradise connection completed | Maname Paradise | Maname Paradise | INEP/INCOME | 961702.34 | 0 | Appoint engineer, capacity verification and designs | Target achieved | Appoint engineer, capacity verification and designs done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ratombo/ by 30 June 2016 | N/A | Ratombo connection completed | Ratombo | RATOMBO | INEP/INCOME | 2181433.9 | 1553244.3 | Energise and completion | Target not achieved | Energise not done and completion done | Community protest | To be energised by the end of December | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Tshiozwi/ Gogobole phase 2 by 30 June 2017 | New Connetion | Tshiozwi/ Gogobole phase 2 completed | Tshiozwi/ Gogobole phase 2 | Tshiozwi/ Gogobole phase 2 | INEP/INCOME | 1748549.6 | 1164283.93 | Appoint contractor. Commence with the project up to the pole pegging | Target achieved | Appoint contractor. Commence with the project up to the pole pegging | None | None | Progress report and Completion certificate | TECH | 62
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 by 30 June 2017 | New Connetion | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 completed | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | INEP/INCOME | 1084100.81 | 942226.48 | Appoint contractor. Commence with the project up to the pole pegging | Target achieved | Appoint contractor. Commence with the project up to the pole pegging done | None | None | Progress report and Completion certificate | TECH | 63
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mammburu phase 2 by 30 June 2017 | New Connetion | Mammburu connection completed | Mammburu | Mammburu | INEP/INCOME | 1866694.95 | 1506269.84 | Energise and completion | Target achieved | Energise and completion | None | None | Progress report and Completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Madabani by 30 June 2017 | New Connetion | Madabani completed | Madabani | Madabani | INEP/INCOME | 961702,34 | 0 | Appoint engineer,capacity verification and design | Target not achieved | Appoint engineer,capacity verification and design | Poor perfomance by service provider | To complete the design by the end of December | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 65
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Sukani Phase 2 by 31 December 2017 | New Connetion | Sukani connection completed | Sukani | SUKANI | INEP/INCOME | 2032214.4 | 852777 | Energise and completion | Target not achieved | Energise and completion | Poor perfomance by service provider | To complete the design by the end of December | Project progress reportcompletion certificate | TECH | 66
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Freedom Lusaka Phase 2 by 30 June 2017 | New Connetion | Freedom Lusaka Phase 2 connection completed | Freedom Lusaka Phase 2 | Freedom Lusaka Phase 2 | INEP | 125241.12 | 1214587.21 | Energise and completion | Target achieved | Energise and completion | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 67
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Manavhela/ Madodonga phase 2 by 30 June 2017 | New Connetion | Manavhela/ Madodonga phase 2 completed | Manavhela/ Madodonga phase 2 | Manavhela/ Madodonga phase 2 | INEP | 285927.84 | 1727109.41 | Appontment of contractor and pole pegging | Target achieved | Appontment of contractor and pole pegging done | None | None | Progress report and Completion certificate | TECH | 68
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mavhunga /Muromani by 30 June 2017 | New Connetion | Mavhunga/ Muromani connection completed | Mavhunga Muromani | Mavhunga Muromani | INEP/INCOME | 141784.9 | 0 | appointment of engineer, capacity verification and designs | Target achieved | appointment of engineer, capacity verification and designs done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 69
Electricity Provision | Accessible basic and infrastructure services | To pay the engineer on the electrification of Vyeboom by 30 September 2017 | Payment | Payment Done | Payment | Vyemboom | INEP | 867542 | 867541.56 | Pay engineer | Target achieved | Payment of the engineer done (R761001.37) | None | None | Payment certificate | TECH | 70
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Revitalization of OK/ Shoprite Traders market project by 31 March 2017 | N/A | Revitalization of OK/ Shoprite Traders market project completed | OK/ Shoprite Traders market revitalization project | Makhado Municipality | MIG | 500000 | 369356.43 | Develop terms of reference for the traders markets | Target achieved | Develop terms of reference for the traders markets done | None | None | Specification, Advert and Designs | TECH | 71
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | Construction of Sereni Themba to Mashamba post office ( phase 3) by 30 June 2017 | Phase 1 and 2 Constructed | Sereni Themba to Mashamba post office ( phase 3) 4.2 km | Sereni Themba to Mashamba post office ( phase 3) | Makhado Municipality | MIG | 11800000 | 606246.04 | Appoint contractors, preliminary requirements and site establishment | Target not achieved | Appoint contractors not done, preliminary requirements and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 72
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Robert khoza street ( Chavani and Bungeni road) by 30 June 2017 | N/A | To construct Robert khoza street ( Chavani and Bungeni road) | To construct Robert khoza street ( Chavani and Bungeni road) | Makhado Municipality | MIG | 9246000 | 8777222.02 | 4.5 access road completed and project handover | Target not achieved | 4.5 access road completed and project handover | Poor perfomance by service provider | To complete the design before the end of December. Service provider penalised | Site establishment report, project progress report, handover report | TECH | 73
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshikwarani to Zamkomste Road - 4.5km by 30 June 2017 | N/A | Tshikwarani to Zamkomste Road - 4.5km completed | Tshikwarani to Zamkomste Road - 4.5km | Makhado Municipality | MIG | 11800000 | 473372.9 | Appoint contrators, preliminary requirement and site establishment | Target not achieved | Appoint contrators, preliminary requirement and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 74
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshirolwe,Matsa to Manyii road P1- 20km by 30 June 2017 | N/A | Tshirolwe,Matsa to Manyii road P1- 20km completed | Tshirolwe,Matsa to Manyii road P1- 20km | Makhado Municipality | MIG | 11800000 | 0 | Appoint contrators, preliminary requirement and site establishment | Target not achieved | Appoint contrators, preliminary requirement and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 75
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Mudimeli bridge by 30 June 2017 | New | Mudimeli bridge completed | Mudimeli bridge | Makhado Municipality | MIG | 11800000 | 421593.9 | Appoint contrators, preliminary requirement and site establishment | Target not achieved | Appoint contrators, preliminary requirement and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 76
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Khunda Roads stormwater 30 June 2017 | New | Khunda Roads stormwater completed | Khunda Roads stormwater | Makhado Municipality | MIG | 11800000 | 1163926.74 | Appoint contrators, preliminary requirement and site establishment | Target not achieved | Appoint contrators, preliminary requirement and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 77
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To contruct Waterval ablution facilities by 30 June 2017 | New | Waterval ablution facilities completed | Waterval ablution facilities | Makhado Municipality | MIG | 11800000 | 0 | Appoint contrators, preliminary requirement and site establishment | Target not achieved | Appoint contrators, preliminary requirement and site establishment not done | Tender readvetise | To appoint before end of December | Site establishment report, project progress report, handover report | TECH | 78
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Tshedza to Vuvha road- 4.3 km by 30 June 2017 | New | Tshedza to Vuvha road- 4.3 km completed | Tshedza to Vuvha road- 4.3 km | Makhado Municipality | INCOME | 3000000 | 0 | Develop specification for rehabilitationof internal street of Makhado | Target achieved | Develop specification for rehabilitationof internal street of Makhado done | None | None | Spec, Advert and completion certificate | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Gombiti,Tshivhuyuni to Mamphagi P1- 15km by 30 June 2017 | New | Gombiti,Tshivhuyuni to Mamphagi P1- 15km completed | Gombiti,Tshivhuyuni to Mamphagi P1- 15km | Hanani, Hlanganani township, Tsianda, Ndouvhada,Vleifontein. | MIG | 2500000 | 0 | Appoint contractors and erect vertical poles | Target not achieved | Appoint contractors done and erect vertical poles not done | Negotiation wirh LIM345 | Only 3 appointed Within Makhado area) | Spec, Advert and completion certificate | TECH | 80
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Xitacini to Jiweni P1 - 6.1km by 30 June 2017 | New | Xitacini to Jiweni P1 - 6.1km completed | Xitacini to Jiweni P1 - 6.1km | Makhado Municipality | MIG | 500000 | 0 | Write memorandum of approval to MM. Development of specifications and submit to the SCM. | Target achieved | Memorandum of approval to MM done. Development of specifications done and submitted to the SCM. | None | None | Spec, advert and completion certificate | TECH | 81
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To rehabilitate of Internal Streets by 30 June 2017 | Gravel | Rehabilitation of Internal Streets completed | Rehabilitation of Internal Streets | Makhado Municipality | MIG | 500000 | 0 | Write memorandum of approval to MM. Development of specifications and submit to the SCM. | Target not achieved | Memorandum of approval to MM not done. Development of specifications not done and submission to the SCM not done. | Financial constraits | To be adjusted | Spec, advert and completion certificate | TECH | 82
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Fencing of graveyards by 30 June 2017 | Development | Fencing of 8 graveyards | Fencing of graveyards | Makhado Municipality | MIG | 800000 | 0 | Write memorandum of approval to MM. Development of specifications and submit to the SCM. | Target achieved | Memorandum of approval to MM done. Development of specifications done and submitted to the SCM done. | None | None | Memo,, Spec and completion certificate | TECH | 83
Building and Construction | Accessible basic and infrastructure services | To develop refuse transfer station for Waterval Region by 30 June 2017 | New | Development of refuse transfer station for Waterval Region | Development of refuse transfer station for Waterval Region | Makhado Municipality | MIG | 500000 | 0 | Develop terms of reference for the Kutama/sinthumule stadium | Target achieved | Develop terms of reference for the Kutama/sinthumule stadium done | None | None | Advertisement copy, appointment letter,project progress report, handover report | TECH | 84
Building and Construction | Accessible basic and infrastructure services | To construct waste Disposal Cell (New landfill ) 30 June 2017 | New | Construction of waste Disposal Cell (New landfill ) | Construction of waste Disposal Cell (New landfill ) | Makhado | INCOME | 300000 | 0 | Specification, advertisement | Target achieved | Specification done, advertisement done | None | None | Advertisement , Appointment letter and completion certificate | TECH | 85
Building and Construction | Accessible basic and infrastructure services | To upgrade Dzanani Transfer Station - Elec+ Guard room by 30 June 2017 | Upgrade | Upgrade Dzanani Transfer Station - Elec+ Guard room | Upgrade Dzanani Transfer Station - Elec+ Guard room | Makhado | INCOME | 150000 | 0 | Develop and submit spec to SCM | Target achieved | Develop and submit spec to SCM done | None | None | Spec, Advert and completion certificate | TECH | 86
Building and Construction | Accessible basic and infrastructure services | Development of Kutama/Sinthumule Stadium by 30 June 2017 | Development | Kutama/Sinthumule Stadium developed | Development of Kutama/Sinthumule Stadium | Makhado | INCOME | 225000 | 0 | Completion of 60m perimeter wall and project handover | Target not achieved | Completion of 60m perimeter wall and project handover not done | Capacity constraits | Adverised for contractor to assist | Specification, advertisement, project progress report | TECH | 87
Building and Maintanance | Accessible basic and infrastructure services | Refurbishment of Caravan Park buildings 30 June 2017 | Refurbishment | Refurbishment of Caravan Park buildings | Refurbishment of Caravan Park buildings | Makhado Municipality | INCOME | 50000 | 0 | Develop and submit spec to SCM | Target not achieved | Develop and submit spec to SCM not done | Project not in the SDBIP for DTS and request for intervention received late in the 1st quarter | To be advertised in the 2nd quarter | Spec, Advert and completion certificate | TECH/ COMM | 88
Building and Maintanance | Accessible basic and infrastructure services | Ablution of Tree Park Facility by 31 March 2017 | New | Ablution of Tree Park Facility | Ablution of Tree Park Facility | Makhado Municipality | INCOME | 900000 | 0 | Develop specification for appointment of a service providr | Target achieved | Develop specification for appointment of a service provider done | None | None | Spec, Advert and completion certificate | TECH | 89
Building and Maintanance | Accessible basic and infrastructure services | To construct Standby quarter perimeter wall by 31 March 2017 | Development | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Makhado Municipality | MIG | 600000 |  | Develop terms of ref and submit to SCM |  |  |  |  | Terms of ref, Advert | TECH | 78
Building and Construction | Accessible basic and infrastructure services | To construct Carport for Employees at Dzanani Traffic by 31 March 2017 | New | Construction for Carport | Construction for Carport | Makhado Municipality | MIG | 4000000 |  | Advertisement for Construction and appointment of contractor |  |  |  |  | Site establishment report, project progress report, handover report | TECH | 79
Building and Construction | Accessible basic and infrastructure services | To remove underground fuel tanks and rehabilitate the soil 30 June 2017 | New | Remove underground fuel tanks and rehabilitate the soil | Remove underground fuel tanks and rehabilitate the soil | Makhado Municipality | MIG | 6054000 |  | Procurementprocess for contractor and appointment of contractor |  |  |  |  | Specifications, advertisement, appointment letter, project progress report | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To construct Industrial Paving of gate VTS - entrance by 30 June 2017 |  | Industrial Paving of gate VTS - entrance comp;le | Industrial Paving of gate VTS - entrance | Makhado Municipality | MIG | 1000000 |  | Advertisement for appointment of Contractors |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 81
Building and Construction | Accessible basic and infrastructure services | Revitalisation of Tshakhuma Fruit Market (Phase 2) by 30 June 2017 |  | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Makhado Municipality | INCOME | 1100000 |  | Advertisement for appointment of Contractors |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To plan Siloam Taxi Rank by 30 June 2017 | New | Siloam Taxi Rank (Planning) | Siloam Taxi Rank(Planning) | Siloam | MIG | 600000 |  | Develop terms of ref and submit to SCM |  |  |  |  | Terms of reference, Advertisement, designs | TECH | 90
Building and Construction | Accessible basic and infrastructure services | Rehabilitation of Street (900m) -Dzanani township 30 June 2017 |  | Street Rehabilitation (900m) -Dzanani township | Street Rehabilitation (900m) -Dzanani township | Dzanani township | MIG | 5750000 |  | Advertisement for appointment of Contractors |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 93
Building and Construction | Accessible basic and infrastructure services | Development of New Waterval Stadium by 30 June 2017 | New | New Waterval stadium developed | Development of New Waterval Stadium | Waterval | MIG | 11100000 |  | Complete earthworks and layer works |  |  |  |  | Progress report and completion certificate | TECH | 94
Building and Construction | Accessible basic and infrastructure services | To construct Civic Centre external wall Painting 30 June 2017 |  | Civic Centre external wall Painting | Civic Centre external wall Painting | Makhado Municipality | INCOME | 300000 |  | Develop spec and submit to SCM |  |  |  |  | Spec, Advert and completion certificate | TECH | 97

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Location | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End date | 1st Q Target | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2017 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | INCOME | 163938800.12 | 27694053.57 | 1/7/2016 | 30/6/2017 | 10% | Target achieved | 20% Capital budget spent (27694053.57) | None | None | Operational | Operational | Quarterly Financial Report | MM and All Directors | 90
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2017 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | INCOME | 112264000 | 13016469.49 | 1/7/2016 | 30/6/2017 | 10% | Target achieved | 10% MIG budget spent (13016469.49) | None | None | Operational | Operational | Quarterly Financial Report | MM | 91
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2017 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | INCOME | 17000000 | 11024714.32 | 1/7/2016 | 30/6/2017 | 10% | Target achieved | 69% INEP budget spent (11024714.32 | None | None | Operational | Operational | Quarterly Financial Report | MM | 92
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2017 | 100% | 100% | FMG | Makhado Municipality | INCOME | 1600000 | 404996 | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Expenditure Report | B&T | 93
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2017 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | INCOME | 342227123 | 68296459.88 | 1/7/2016 | 30/6/2017 | 20% | Target achieved | 72% revenue collected. (68296459.88) | None | None | Operational | Operational | Section 71 report (c1 schedule) | B&T | 94
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2017 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Makhado Municipality | INCOME | Operational | Operational | 2017-01-01 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 95
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2017 | Final budget was submitted to Council | Final budget submitted to Council | Final budget | Makhado Municipality | INCOME | Operational | Operational | 2017-01-01 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Final budget and Council Resolution | B&T | 96
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Makhado Municipality | INCOME | Operational | Operational | 2016-01-07 | 31/8/2016 | Financial statements compiled and submitted to AG | Target achieved | Financial Statements compiled and submitted to AG 31 August 2016 | None | None | Operational | Operational | Copy of Financial statements | B&T | 97
Budget and Reporting | Sound financial management and viability | # of section 71 reports submitted to Treasury within 10 days after the end of the month by 30 June 2017 | 12 | 12 | Section 71 report submission | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 3 | Target achieved | 3 Section 71 report were submitted to Treasury | None | None | Operational | Operational | Copy of acknowledgement of receipt by Treasuries | B&T | 98
Supply Chain Management | Sound financial management and viability | To review the Supply Chain Management policy by 30 June 2017 | 2014/ 15 Supply Chain Management policy was reviewed and amended | Supply Chain Management policy reviewed | Supply Chain Management policy | Makhado Municipality | INCOME | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Council Resolution | B&T | 99
Asset Management | Sound financial management and viability | % of new acquisitions updated into the Asset Register by 30 June 2017 | 100% | 100% | Updting of Asset Register | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% | Monthly Reconcilliations | Updating the assets register | None | None | OPEX | OPEX | Schedules of Asset Register movement | B&T | 100

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 1st Q Target | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
5.4. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 101
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2016 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Makhado Municipality | Income | 1200000 |  | 1/7/2016 | 30/9/2016 | Host official opening and the Three Days Makhado Annual Show. | Target achieved | Host official opening and the Three Days Makhado Annual Show done. | None | None | Annual Show Report and Audited Financial Statements | DEVP | 102
Local Economic Development | Invest in local economy | # of LED projects supported 30th June 2014 | 9 | 6 | Poverty Alleviation | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/9/2017 | N/A | N/A | N/A | N/A | N/A | LED strategy implementation report | MM and DEVP | 103

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17R'000 | Expenditure | Start Date | End date | 1st Q Target | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No | Indicator No
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate Stategic and operational Risk Assessment and review and approval of risk and fraud management policies by 30 June 2017 | Strategic and Operational Risk Assessment Report developed / coordinated and 6 policies, plans and strategies reviewed and approved | 7 risk activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Attendance register, Minutes and Programme | MM | 114 | 104
Risk Management | Good governace and Administrative Excellence | Coordinate quarterly Strategic and Operational monitoring risk report 30 June 2017 | 4 quarterly Strategic and Operational monitoring risk report Coordinated | 4 activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Develop Quarterly Strategic Monitoring Risk Report, | Target achieved | Quarterly Strategic Monitoring Risk Report was developed, | None | None | Strategic Monitoring Risk Report | MM | 115 | 105
Risk Management | Good governace and Administrative Excellence | Coordinate Risk Management Committee meetings 30 June 2017 | 4 Risk Management Committee meetings held | 4 activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Cordinate 1 Risk Management Committee meeting | Target achieved | Risk Management Committee meeting was held on the 19 August 2016 | None | None | Minutes and Attendance register | MM | 116 | 106
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2017 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of cases attended/# of cases reported) | Target achieved | No case reported in the 1st quarter | None | None | Case Register | MM | 117 | 107
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2017 | 7 by laws reviewed | 6 by laws reviewed | Reviewing of Municipal By-laws | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Development of the 6 draft policies | Target achieved | 7 policies were approved and 4 draft policies developed | None | None | 6 draft policies Council resolution Invitations, attendance registers, Final council resolutions and Promulgation notice for by laws | CORP | 120 | 108
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 September 2016 | 4 by laws reviewed | 1 by law reviewed | Review of the following by laws: Rules of Order | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | Submit reviewed Rules of Order to Council and promulgate in Limpopo Provincial Gazette after approval by Council | Target achieved | Reviewed Rules of Order to Council and promulgate in Limpopo Provincial Gazette after approval by Council done | None | None | Reviewed Rules of Order, Council Resolution, Provincial Gazette Promulgation | CORP |  | 109
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2017 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM | 121 | 110
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2017 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 122 | 111
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2017 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Internal Audit report to Audit and Performance Audit Committee | MM | 123 | 112
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2017 | 7 | 7 | Audit and Performance Audit Committee | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Minutes, Attendance register, invitations | MM | 124 | 113
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2017 | 4 | 4 | Audit and Performance Audit Committee Reports | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of projects executed/# of projects in the action plan) | Target achieved | 100% (3/3) | None | None | Council resolution, Attendance register | MM | 125 | 114
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 September 2016 | 1 | 1 | IAA and APAC Assessment report | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 | Target achieved | 2 | None | None | Report, Council Resolution | MM | 126 | 115
Information Technology | Good governace and Administrative Excellence | Implement automisation of municipal call centre by 30 June 2017 | Manual system | Computerized call center system | Implement automisation of municipal call centre | Civic Center | INCOME | 500000 | 0 | 1/7/2016 | 30/6/2017 | 1 | Target achieved | 1 | None | None | Specifications, Advert, Apointment letter, Project report | CORP | 127 | 116
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 30 June 2017 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Civic Center and regional offices | INCOME | 125896.47 | 125896.47 | 1/7/2016 | 30/6/2017 | 1 | Target achieved | 1 | None | None | Orders, Payment certificate and intallation report | CORP | 128 | 117
Information Technology | Good governace and Administrative Excellence | To install server harddrive 30 June 2017 | Phase 1 done | Server harddrive installed | Server harddrive | Civic Center | INCOME | 150000 | 0 | 1/7/2016 | 30/6/2017 | Compile specification, call for quatationt | Target not achieved | Compile specification not done, call for quatation not done | There is only one IT administrator in the section the dept transfer other administration funtion to admin section | To be compiled during 2nd Quarter | Appointment letter, Project agreement, installation report and payment certicate | CORP | 129 | 118
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2016 | Unacceptable standard of server room | Acceptable server room conditions | Upgrade server room | Civic Center | INCOME | 50000 | 0 | 1/7/2016 | 31/12/2016 | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business | Target not achieved | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business not done | There is only one IT administrator in the section the dept transfer other administration funtion to admin section | Memorandum will be submitted during 2nd quarter | Approved memorandum, Written propoal, wayforward outcomes | CORP | 130 | 119
Information Technology | Good governace and Administrative Excellence | To install telephone and computer network infrastructure new offices Civic Center by 31 December 2016 | New offices Civic Center | Network infrastructure new offices Civic Center | Network infrastructure new offices Civic Center | Makhado Municipality | INCOME | 230000 | 136064.4 | 1/7/2016 | 31/12/2016 | Link of telephone and computer services between Civi centre and new building | Target achieved | Linking of telephone and computer services between Civi centre and new building done | None | None | Installation report |  | 140 | 120
Information Technology | Good governace and Administrative Excellence | To procure and install the new VEEAM backup server by 30 June 2017 | Only two telephone points | New VEEAM backup server function | VEEAM backup server | Makhado Municipality | INCOME | 150000 | 0 | 1/7/2016 | 30/06/2017 | Compile specification, call for quatation | Target achieved | Specification done, call for quatation done | None | None | Specifications, Apointment letter, Project report |  | 150 | 121
Information Technology | Good governace and Administrative Excellence | To add extra telephone points at Municipal Stores complex by 31 March 2017 | N/A | Add extra telephone points at Municipal Stores complex | Telephone points at Municipal Stores complex | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 31/03/2017 | Compile specification, call for quatation from the existing service provider | Target not achieved | Specification done, call for quatation from the existing service provider not done | There is only one IT administrator in the section the dept transfer other administration funtion to admin section | To be compiled during 2nd Quarter | Specifications, Apointment letter, Project report |  | 151 | 122
Information Technology | Good governace and Administrative Excellence | To Implement MCGICTP in the policy 31 March 2017 | No ICT strategy | Implementation MCGICTP, 2015 | Implementation MCGICTP, 2015 | Makhado Municipality | INCOME | 500000 | 0 | 1/7/2016 | 31/03/2017 | Complile specification and call for tender for specicizide services | Target achieved | Specification done and call for tender for specizide services done | None | None | Specifications, Apointment letter, Approved ICT Strategy |  | 152 | 123
Information Technology | Good governace and Administrative Excellence | To purchase laptops, computers and printers by 31 March 2017 | New equipment | ICT equipment purchased | Purchase of ICT equipment | Makhado Municipality | INCOME | 60000 |  | 1/7/2016 | 31/03/2017
Information Technology | Good governace and Administrative Excellence | Upgrade VIP HR ESS Software (for employee leave application apart from existing VIP Leave module) | Upgrade | ESS Software (for employee leave application apart from existing VIP Leave module) | ESS Software (for employee leave application apart from existing VIP Leave module) | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 31/03/2017 | Call for quatation from existing service provider and get approval to MM | Target achived | Call for quatation from existing service provider done and approval to MM done | None | None | Quotations, Delivery note, Approved memo |  |  | 124
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Civic Center | INCOME | 200000 | 0 | 1/7/2015 | 31/03/2017 | Call for quatation from existing service provider and get approval to MM | Target not achieved | Call for quatation from existing service provider done and approval to MM not done | Financial constraits | To be adjusted | Approval by MM, Project report | CORP | 153 | 125
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 | Target achieved | 4 council meeting held | None | None | Minutes, Attendance register, notice of invitations. | CORP | 156 | 126
Communication | Good governace and Administrative Excellence | To review BathoPele Service Standards by 31 December 2016 | 1 | BathoPele Service Standards reviewed | Bathopele service standards | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 6 | Target achieved | 6 executive meeting held | None | None | Minutes, Attendance register, notice of invitations. | CORP | 157 | 127
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 |  | Council approved website policy | Comprehensive website policy | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 31/12/2017 | Distribute for comments of all departments | Target achieved | Distribution for comments of all departments done | None | None | Approved 2015 Batho Pele Service Standards | CORP | 158 | 128
Communication | Good governace and Administrative Excellence | Revamp municipal website | Upgrade | Municipal website revamped | Revamp municipal website | Civic Center | INCOME | Operational | Operational | 1/7/2015 | 31/12/2017 | Submit to Council for approval | Target achieved | Submission of website policy to Council for approval done | None | None | Council approval of policy | CORP | 159 | 129
Public Participation | Good governace and Administrative Excellence | To review the public participation by 31 March 2017 | Public Participation policy | Public Participation policy reviewed | Public Participation Policy | Civic Center | INCOME | 60000 | #NAME? | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Attendance register, Memo and Order request | CORP |  | 130
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 30 June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Compile public participation policy and submit to Council for approval of Draft Policy | Target achieved | Public participation policy compiled and submitted to Council for approval of Draft Policy | None | None | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 118 | 131
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Target not achieved | 114 ward committee meetings not coordinated and submission of quarterly ward committees' report to Council not done. | New Ward committees are being established | Launch of the ward Committee to be launch during second quarter | Minutes, Attendance register, Ward committee quarterly report | CORP | 119 | 132
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 September 2016 | 1 | 1 | Imbizo Feedback Session | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 mbizo to be held | Target achieved | 1 imbizo held | None | None | Attendance register and Programme | CORP | 160 | 133
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework by 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/08/2017 | 1 imbizo feedback session to held | Target achieved | 1 imbizo session held | None | None | Attendance register and program | CORP | 170 | 134
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Income | INCOME | Operational | Operational | 1/7/2015 | 30/08/2017 | Reviewing makhado stakeholder framework | Target achieved | Makhado Stakeholder framework reviewed | None | None | Approved Stakeholders management Framework and council resolution | CORP | 180 | 135
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Income | INCOME | Operational | Operational | 1/7/2015 | 30/06/2016 | 1 | Target not achieved | Communication stratergy not reviewed | The review pends due to the launch of new Ward commitees | Communication stratergy to be reviewed before the end of December | Approved Communication strategy and council resolution policy and council resolution | CORP | 190 | 136

## MCASHFLOW
LIM344 Makhado - Supporting Table SA30 Budgeted monthly cash flow
MONTHLY CASH FLOWS | Budget Year 2016/17 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Cash Receipts By Source | [12 empty] | 1
Property rates | 4019000 | 3969134 | 3807555 | 4026963 | 4211807 | 4133077.37 | 4144606.63 | 4216500.12 | 4152171.64 | 3223000 | 5668578 | 7419607.24 | 52992000 | 56278000 | 59598000
Property rates - penalties & collection charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - electricity revenue | 24487000 | 24757501 | 24576285 | 22612339 | 23553934 | 21094567.23 | 23815687.76 | 24686897.5 | 26402779.42 | 39907349 | 39180349 | 11143561.4416 | 306218250.3516 | 330287004.8293 | 356247563.4089
Service charges - water revenue | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - sanitation revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - refuse revenue | 408000 | 624554 | 762767 | 738842 | 627840 | 620673.35 | 674000.29 | 519782.08 | 623205.03 | 837618 | 943618 | 963100.25 | 8344000 | 7500000 | 7943000
Service charges - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment | 51000 | 36831 | 27862 | 36351 | 27160 | 28611.85 | 21929.68 | 2939.76 | 9243.13 | 55147 | 60058 | 121500.58 | 478634 | 510223.844 | 543898.6177
Interest earned - external investments | 100000 | 107438 | 395418 | 451352 | 177646 | 115712.03 | 163166.02 | 109927.9 | 373177 | 245088 | 184500 | 1611385.05 | 4034810 | 4284968.22 | 4537781.345
Interest earned - outstanding debtors | 2589000 | 0 | 0 | 0 | 0 |  |  |  | 2761823 | 2548000 | 2470401 | 2531508.0746 | 12900732.0746 | 13701000 | 12231000
Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 149396.9442 | 1777396.9442 | 1887595.5547 | 1998963.6924
Licences and permits | 786000 | 832709 | 717757 | 871846 | 792332 | 1451457.37 | 1150622.61 | 903177.28 | 884895.14 | 1035000 | 1574025 | 1158346.4808 | 12158167.8808 | 12911974.2894 | 13673780.7725
Agency services | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfer receipts - operational | 122316600 |  | 0 |  | 96105900 |  |  |  | 72807500 | 0 | 0 | 0 | 291230000 | 305515000 | 323340000
Other revenue | 203000 | 289551 | 441003 | 248327 | 156162 | 1152642 | 81083.92 | 22182.69 | 481259.83 | 757000 | 758900 | 1541888.56 | 6133000 | 6515118 | 6899509
Cash Receipts by Source | 155107600 | 30765718 | 30876647 | 29134020 | 125800781 | 28744741.2 | 30199096.91 | 30609407.33 | 108644054.19 | 48756202 | 50988429 | 26640294.6213 | 696266991.2513 | 739390884.7374 | 787013496.8365
Other Cash Flows by Source
Transfer receipts - capital | 31017640 | 0 | 4000000 | 0 | 5000000 | 32017640 | 2000000 | 0 | 27310640 | 0 | 0 | 80 | 101346000 | 113765000 | 122142000
Contributions recognised - capital & Contributed assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58000000 | 58000000 | 65000000 | 58000000
Proceeds on disposal of PPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Short term loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Borrowing long term/refinancing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase (decrease) in consumer deposits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (Increase) in non-current debtors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) other non-current receivables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) in non-current investments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cash Receipts by Source | 186125240 | 30765718 | 34876647 | 29134020 | 130800781 | 60762381.2 | 32199096.91 | 30609407.33 | 135954694.19 | 48756202 | 50988429 | 84640374.6213 | 855612991.2513 | 918155884.7374 | 967155496.8365
Cash Payments by Type
Employee related costs | 20886432 | 20269445 | 20802101 | 20145566 | 20575780 | 41593611.32 | 20114841.27 | 20026035.57 | 20796805.66 | 19366578 | 19156557 | 18321519.7227 | 262055272.5427 | 279809086.3481 | 298765913.3062
Remuneration of councillors | 1806324 | 1785053 | 1785808 | 1785833 | 1779162 | 1778267 | 2488505.2 | 1878623.47 | 1877452.09 | 2712682 | 2712682 | 4331593.7 | 26721985.46 | 28539080.47 | 30479737.95
Finance charges | 700000 | 307500 | 205230 | 185600 | 1864927 | 639073 | 433000.41 | 319400.41 | 473441.46 | 845000 | 815000 | 738827.72 | 7527000 | 7994000 | 8465000
Bulk purchases - Electricity | 18003793.34 | 18311400.67 | 17194530.67 | 19138053 | 18003793.3333 | 17612210 | 18043938.58 | 20041819.26 | 20938800.08 | 22756886 | 25756065 | 29341061.981 | 245142351.9143 | 261027000 | 281909000
Bulk purchases - Water & Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted services | 1485583 | 2118911 | 2208868 | 775621 | 1548053 | 720689 | 1157890 | 2567098 | 1176890 | 1267896 | 1567895 | 2202450 | 18797844 | 19963310.328 | 21121182.327
Transfers and grants - other municipalities | [11 empty] | 0
Transfers and grants - other | [11 empty] | 0
Other expenditure | 15021880 | 11779768 | 13712836 | 13243593 | 15331512 | 12080288 | 10065462.07 | 12819141.24 | 10834956 | 12445224 | 14589900 | 8403630.43 | 150328190.74 | 163185033.06 | 175645968.73
Cash Payments by Type | 57904012.34 | 54572077.67 | 55909373.67 | 55274266 | 59103227.3333 | 74424138.32 | 52303637.53 | 57652117.95 | 56098345.29 | 59394266 | 64598099 | 63339083.5537 | 710572644.657 | 760517510.2061 | 816386802.3132
Other Cash Flows/Payments by Type
Capital assets | 13994688 | 12392021 | 10668326 | 11400539 | 13942979 | 13675705 | 9298282.45 | 12181912.85 | 11504516 | 10967348 | 9262883 | 10986799.7 | 140276000 | 186460000 | 158272000
Repayment of borrowing | 0 | 0 |  | 719000 | 27037 | 27037 | 0 | 0 | 722017 | 0 |  | 304909 | 1800000
Other Cash Flows/Payments |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cash Payments by Type | 71898700.34 | 66964098.67 | 66577699.67 | 67393805 | 73073243.3333 | 88126880.32 | 61601919.98 | 69834030.8 | 68324878.29 | 70361614 | 73860982 | 74630792.2537 | 852648644.657 | 946977510.2061 | 974658802.3132
NET INCREASE/(DECREASE) IN CASH HELD | 114226539.66 | -36198380.67 | -31701052.67 | -38259785 | 57727537.6667 | -27364499.12 | -29402823.07 | -39224623.47 | 67629815.9 | -21605412 | -22872553 | 10009582.3676 | 2964346.5942 | -28821625.4687 | -7503305.4767
Cash/cash equivalents at the month/year begin: | 64617657.17 | 178844196.83 | 142645816.16 | 110944763.49 | 72684978.49 | 130412516.1567 | 103048017.0367 | 73645193.9667 | 34420570.4967 | 102050386.3967 | 80444974.3967 | 57572421.3967 | 64617657.17 | 67582003.7642 | 38760378.2955
Cash/cash equivalents at the month/year end: | 178844196.83 | 142645816.16 | 110944763.49 | 72684978.49 | 130412516.1567 | 103048017.0367 | 73645193.9667 | 34420570.4967 | 102050386.3967 | 80444974.3967 | 57572421.3967 | 67582003.7642 | 67582003.7642 | 38760378.2955 | 31257072.8188
References
1. Note that this section of Table SA 30 is deliberately not linked to Table A4 because timing differences between the invoicing of clients and receiving the cash means that the cashflow will differ from budgeted revenue, and similarly for budgeted expenditure. However for the MTREF it is now directly linked to A7.

## MREX
LIM344 Makhado - Supporting Table SA25 Budgeted monthly revenue and expenditure
Description | Budget Year 2016/17 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Revenue By Source
Property rates | 4019000 | 3969134 | 3807555 | 4026963 | 4211807 | 4133077.37 | 4144606.63 | 4216500.12 | 4152171.64 | 3223000 | 5668578 | 7419607.24 | 52992000 | 56278000 | 59598000
Property rates - penalties & collection charges | [11 empty] | 0 | 0 | 0 | 0
Service charges - electricity revenue | 24487000 | 24757501 | 24576285 | 22612339 | 23553934 | 21094567.23 | 23815687.76 | 24686897.5 | 26402779.42 | 39907349 | 39180349 | 11143561.4416 | 306218250.3516 | 330287004.8293 | 356247563.4089
Service charges - water revenue | [11 empty] | 0 | 0 | 0 | 0
Service charges - sanitation revenue | [11 empty] | 0 | 0 | 0 | 0
Service charges - refuse revenue | 408000 | 624554 | 762767 | 738842 | 627840 | 620673.35 | 674000.29 | 519782.08 | 623205.03 | 837618 | 943618 | 963100.25 | 8344000 | 7500000 | 7943000
Service charges - other | [11 empty] | 0 | 0 | 0 | 0
Rental of facilities and equipment | 51000 | 36831 | 27862 | 36351 | 27160 | 28611.85 | 21929.68 | 2939.76 | 9243.13 | 55147 | 60058 | 121500.58 | 478634 | 510223.844 | 543898.6177
Interest earned - external investments | 100000 | 107438 | 395418 | 451352 | 177646 | 115712.03 | 163166.02 | 109927.9 | 373177 | 245088 | 184500 | 1611385.05 | 4034810 | 4284968.22 | 4537781.345
Interest earned - outstanding debtors | 2589000 | 0 | 0 | 0 | 0 |  |  |  | 2761823 | 2548000 | 2470401 | 2531508.0746 | 12900732.0746 | 13701000 | 12231000
Dividends received | [11 empty] | 0 | 0 | 0 | 0
Fines | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 148000 | 149396.9442 | 1777396.9442 | 1887595.5547 | 1998963.6924
Licences and permits | 786000 | 832709 | 717757 | 871846 | 792332 | 1451457.37 | 1150622.61 | 903177.28 | 884895.14 | 1035000 | 1574025 | 1158346.4808 | 12158167.8808 | 12911974.2894 | 13673780.7725
Agency services | [11 empty] | 0 | 0 | 0 | 0
Transfers recognised - operational | 122316600 |  | 0 |  | 96105900 |  |  |  | 72807500 | 0 | 0 | 0 | 291230000 | 305515000 | 323340000
Other revenue | 203000 | 289551 | 441003 | 248327 | 156162 | 1152642 | 81083.92 | 22182.69 | 481259.83 | 757000 | 758900 | 1541888.56 | 6133000 | 6515118 | 6899509
Gains on disposal of PPE | [11 empty] | 0 | 0 | 0 | 0
Total Revenue (excluding capital transfers and contributions) | 155107600 | 30765718 | 30876647 | 29134020 | 125800781 | 28744741.2 | 30199096.91 | 30609407.33 | 108644054.19 | 48756202 | 50988429 | 26640294.6213 | 696266991.2513 | 739390884.7374 | 787013496.8365
Expenditure By Type
Employee related costs | 20886432 | 20269445 | 20802101 | 20145566 | 20575780 | 41593611.32 | 20114841.27 | 20026035.57 | 20796805.66 | 19366578 | 19156557 | 18321519.7227 | 262055272.5427 | 279809086.3481 | 298765913.3062
Remuneration of councillors | 1806324 | 1785053 | 1785808 | 1785833 | 1779162 | 1778267 | 2488505.2 | 1878623.47 | 1877452.09 | 2712682 | 2712682 | 4331593.7 | 26721985.46 | 28539080.47 | 30479737.95
Debt impairment | 600000 | 639600 | 681813.6 | 726813.2976 | 774782.9752 | 825918.6516 | 880429.2826 | 938537.6153 | 1000481.0979 | 1066512.8503 | 1136902.6985 | 728207.931 | 10000000 | 10580000 | 11194000
Depreciation & asset impairment | 7600000 | 8101600 | 8636305.6 | 9206301.7696 | 9813917.6864 | 10461636.2537 | 11152104.2464 | 11888143.1267 | 12672760.5731 | 13509162.7709 | 14400767.5138 | 8235300.4594 | 125678000 | 136757000 | 136757000
Finance charges | 700000 | 307500 | 205230 | 185600 | 1864927 | 639073 | 433000.41 | 319400.41 | 473441.46 | 845000 | 815000 | 738827.72 | 7527000 | 7994000 | 8465000
Bulk purchases | 18003793.34 | 18311400.67 | 17194530.67 | 19138053 | 18003793.3333 | 17612210 | 18043938.58 | 20041819.26 | 20938800.08 | 22756886 | 25756065 | 29341061.981 | 245142351.9143 | 261027000 | 281909000
Other materials | [11 empty] | 0 | 0 | 0 | 0
Contracted services | 1485583 | 2118911 | 2208868 | 775621 | 1548053 | 720689 | 1157890 | 2567098 | 1176890 | 1267896 | 1567895 | 2202450 | 18797844 | 19963310.328 | 21121182.327
Transfers and grants | [11 empty] | 0 | 0 | 0 | 0
Other expenditure | 15021880 | 11779768 | 13712836 | 13243593 | 15331512 | 12080288 | 10065462.07 | 12819141.24 | 10834956 | 12445224 | 14589900 | 8403439.69 | 150328000 | 163185000 | 175646000
Loss on disposal of PPE | [11 empty] | 0 | 0 | 0 | 0
Total Expenditure | 66104012.34 | 63313277.67 | 65227492.87 | 65207381.0672 | 69691927.995 | 85711693.2253 | 64336171.0591 | 70478798.692 | 69771586.9609 | 73969941.6212 | 80135769.2122 | 72302401.2041 | 846250453.917 | 907854477.1461 | 964337833.5832
Surplus/(Deficit) | 89003587.66 | -32547559.67 | -34350845.87 | -36073361.0672 | 56108853.005 | -56966952.0253 | -34137074.1491 | -39869391.362 | 38872467.2291 | -25213739.6212 | -29147340.2122 | -45662106.5829 | -149983462.6658 | -168463592.4087 | -177324336.7467
Transfers recognised - capital | 31017640 | 0 | 4000000 | 0 | 5000000 | 32017640 | 2000000 | 0 | 27310640 | 0 |  | 285 | 101346205 | 113765661 | 122141327
Contributions recognised - capital | [11 empty] | 0 | 0 | 0 | 0
Contributed assets | 50000000 | [10 empty] | 8000000 | 58000000 | 65000000 | 58000000
Surplus/(Deficit) after capital transfers & contributions | 170021227.66 | -32547559.67 | -30350845.87 | -36073361.0672 | 61108853.005 | -24949312.0253 | -32137074.1491 | -39869391.362 | 66183107.2291 | -25213739.6212 | -29147340.2122 | -37661821.5829 | 9362742.3342 | 10302068.5913 | 2816990.2533
Taxation | [11 empty] | 0 | 0 | 0 | 0
Attributable to minorities | [11 empty] | 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate | [11 empty] | 0 | 0 | 0 | 0
Surplus/(Deficit) | 170021227.66 | -32547559.67 | -30350845.87 | -36073361.0672 | 61108853.005 | -24949312.0253 | -32137074.1491 | -39869391.362 | 66183107.2291 | -25213739.6212 | -29147340.2122 | -37661821.5829 | 9362742.3342 | 10302068.5913 | 2816990.2533
References
1. Surplus (Deficit) must reconcile with Budgeted Financial Performance
check | [12 empty] | 0 | 0 | 0

## MCAPEX
LIM344 Makhado - Supporting Table SA28 Budgeted monthly capital expenditure (municipal vote)
Description | Ref | Budget Year 2016/17 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Multi-year expenditure to be appropriated | 1
Vote 1 - EXECUTIVE AND COUNCIL |  | 8215000 | 7338000 | 7293000 | 8847000 | 8484000 | 5309000 | 7834000 | 7087000 | 6560000 | 7295000 | 7299000 | 8360000 | 89921000 | 94315000 | 97142000
Vote 2 - WASTE MANAGEMENT | [12 empty] | 0 | 0 | 0 | 0
Vote 3 - ROAD TRANSPORT | [12 empty] | 0 | 0 | 0 | 0
Vote 4 - WATER | [12 empty] | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | 3400000 | 3156700 | 3200000 | 3100000 | 3299000 | 3689000 | 3159999 | 3300000 | 3400000 | 2700000 | 1700000 | 2945301 | 37050000 | 76330000 | 58730000
Vote 6 - CORPORATE SERVICES |  | 350000 | 100500 | 175500 | 350000 | 474000 | 159000 | 250000 | 212000 | 200000 | 230000 | 19500 | 34500 | 2555000 | 2065000 | 400000
Vote 7 - PLANNING AND DEVELOPMENT |  | 150000 | 10500 | 80500 | 203500 | 379000 | 39000 | 134000 | 130000 | 100000 | 220000 | 95500 | 18000 | 1560000 | 6000000 | 0
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | 550000 | 40500 | 450500 | 870000 | 664000 | 40500 | 551000 | 541000 | 500000 | 250000 | 95500 | 1817000 | 6370000 | 7350000 | 1600000
Vote 9 - HOUSING | [12 empty] | 0 | 0 | 0 | 0
Vote 10 - OTHER |  | 2000 | 1500 | 1000 | 1000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 1000 | 1900 | 20000 | 0 | 0
Vote 11 - SPORTS AND RECREATION | [12 empty] | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY |  | 265000 | 20500 | 200000 | 571000 | 374000 | 59500 | 251000 | 233000 | 205000 | 270000 | 52500 | 298500 | 2800000 | 400000 | 400000
Capital multi-year expenditure sub-total | 2 | 12932000 | 10668200 | 11400500 | 13942500 | 13676000 | 9298000 | 12181999 | 11504600 | 10967000 | 10967000 | 9263000 | 13475201 | 140276000 | 186460000 | 158272000
Single-year expenditure to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL | [12 empty] | 0 | 0 | 0 | 0
Vote 2 - WASTE MANAGEMENT | [12 empty] | 0 | 0 | 0 | 0
Vote 3 - ROAD TRANSPORT | [12 empty] | 0 | 0 | 0 | 0
Vote 4 - WATER | [12 empty] | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY | [12 empty] | 0 | 0 | 0 | 0
Vote 6 - CORPORATE SERVICES | [12 empty] | 0 | 0 | 0 | 0
Vote 7 - PLANNING AND DEVELOPMENT | [12 empty] | 0 | 0 | 0 | 0
Vote 8 - COMMUNITY AND SOCIAL SERVICES | [12 empty] | 0 | 0 | 0 | 0
Vote 9 - HOUSING | [12 empty] | 0 | 0 | 0 | 0
Vote 10 - OTHER | [12 empty] | 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION | [12 empty] | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY | [12 empty] | 0 | 0 | 0 | 0
0 | [12 empty] | 0 | 0 | 0 | 0
0 | [12 empty] | 0 | 0 | 0 | 0
0 | [12 empty] | 0 | 0 | 0 | 0
Capital single-year expenditure sub-total | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital Expenditure | 2 | 12932000 | 10668200 | 11400500 | 13942500 | 13676000 | 9298000 | 12181999 | 11504600 | 10967000 | 10967000 | 9263000 | 13475201 | 140276000 | 186460000 | 158272000
References
1. Table should be completed as either Multi-Year expenditure appropriation or Budget Year and Forward Year estimates
2. Total Capital Expenditure must reconcile to Budgeted Capital Expenditure
check | [13 empty] | 0 | 0 | 0

## MREXBYVOTE
LIM344 Makhado - Supporting Table SA26 Budgeted monthly revenue and expenditure (municipal vote)
Description | Budget Year 2016/17 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2016/17 | Budget Year +1 2017/18 | Budget Year +2 2018/19
Revenue by Vote
Vote 1 - EXECUTIVE AND COUNCIL | 32900000 | 35071400 | 37386112.4 | 39853595.8184 | 42483933.1424 | 45287872.7298 | 48276872.33 | 51463145.9038 | 54859713.5334 | 58480454.6266 | 62340164.632 | 12869387.2743 | 521272652.3906 | 562627356.8388 | 601117050.0103
Vote 2 - WASTE MANAGEMENT | 450000 | 479700 | 511360.2 | 545109.9732 | 581087.2314 | 619438.9887 | 660321.962 | 703903.2114 | 750360.8234 | 799884.6378 | 852677.0238 | 164168.4296 | 7118012.4813 | 7559329.2552 | 8005329.6812
Vote 3 - ROAD TRANSPORT | 789000 | 841074 | 896584.884 | 955759.4863 | 1018839.6124 | 1086083.0269 | 1157764.5066 | 1234176.9641 | 1315632.6437 | 1402464.3982 | 1495027.0485 | 1683815.6333 | 13876222.204 | 14736547.9806 | 15606004.3115
Vote 4 - WATER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY | 12780000 | 13623480 | 14522629.68 | 15481123.2389 | 16502877.3726 | 17592067.2792 | 18753143.7197 | 19990851.2052 | 21310247.3847 | 22716723.7121 | 24216027.4771 | 34964483.0467 | 232453654.1162 | 247039780.6714 | 261615127.731
Vote 6 - CORPORATE SERVICES | 3500000 | 3731000 | 3977246 | 4239744.236 | 4519567.3556 | 4817858.801 | 5135837.4819 | 5474802.7557 | 5836139.7376 | 6221324.9603 | 6631932.4077 | 2090019.1804 | 56175472.9162 | 59658352.237 | 63178195.0189
Vote 7 - PLANNING AND DEVELOPMENT | 33000 | 35178 | 37499.748 | 39974.7314 | 42613.0636 | 45425.5258 | 48423.6105 | 51619.5688 | 55026.4604 | 58658.2068 | 62529.6484 | 13379.0959 | 523327.6597 | 555773.9746 | 1111548.3031
Vote 8 - COMMUNITY AND SOCIAL SERVICES | 5000 | 5330 | 5681.78 | 6056.7775 | 6456.5248 | 6882.6554 | 7336.9107 | 7821.1468 | 8337.3425 | 8887.6071 | 9474.1892 | 20365.1771 | 97630.111 | 103683.1779 | 207366.9458
Vote 9 - HOUSING | 3000 | 3198 | 3409.068 | 3634.0665 | 3873.9149 | 4129.5933 | 4402.1464 | 4692.6881 | 5002.4055 | 5332.5643 | 5684.5135 | 12901.6959 | 59260.6563 | 62934.8169 | 125870.1059
Vote 10 - OTHER | [11 empty] | 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION | [11 empty] | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY | 2678000 | 2854748 | 3043161.368 | 3244010.0183 | 3458114.6795 | 3686350.2483 | 3929649.3647 | 4189006.2228 | 4465480.6335 | 4760202.3553 | 5074375.7108 | 5781911.4028 | 47165010.0041 | 50089240.6243 | 53044505.8211
Total Revenue by Vote | 53138000 | 56645108 | 60383685.128 | 64369008.3464 | 68617362.8973 | 73146108.8485 | 77973752.0325 | 83120019.6667 | 88605940.9647 | 94453933.0684 | 100687892.6509 | 57600430.9358 | 878741242.5393 | 942432999.5767 | 1004010997.929
Expenditure by Vote to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL | 6500000 | 6929000 | 7386314 | 7873810.724 | 8393482.2318 | 8947452.0591 | 9537983.895 | 10167490.832 | 10838545.227 | 11553889.2119 | 12316445.8999 | 4761034.1126 | 105205448.1933 | 111728185.9813 | 223456372.3756
Vote 2 - WASTE MANAGEMENT | 1500000 | 1599000 | 1704534 | 1817033.244 | 1936957.4381 | 2064796.629 | 2201073.2065 | 2346344.0382 | 2501202.7447 | 2666282.1258 | 2842256.7461 | 949416.0335 | 24128896.206 | 25624887.7707 | 51249775.8955
Vote 3 - ROAD TRANSPORT | 1200000 | 1279200 | 1363627.2 | 1453626.5952 | 1549565.9505 | 1651837.3032 | 1760858.5652 | 1877075.2305 | 2000962.1957 | 2133025.7007 | 2273805.3969 | 8350269.2037 | 26893853.3417 | 28561272.2489 | 57122544.9107
Vote 4 - WATER | 1280000 | 1364480 | 1454535.68 | 1550535.0349 | 1652870.3472 | 1761959.7901 | 1878249.1362 | 2002213.5792 | 2134359.6755 | 2275227.414 | 2425392.4234 | 559356.8434 | 20339179.9239 | 21600209.0792 | 43200418.8664
Vote 5 - ELECTRICITY | 17890000 | 19070740 | 20329408.84 | 21671149.8234 | 23101445.7118 | 24626141.1288 | 26251466.4433 | 27984063.2285 | 29831011.4016 | 31799858.1541 | 33898648.7923 | 30357056.4365 | 306810989.9603 | 325833271.3378 | 345057434.4057
Vote 6 - CORPORATE SERVICES | 2500000 | 2665000 | 2840890 | 3028388.74 | 3228262.3968 | 3441327.715 | 3668455.3442 | 3910573.3969 | 4168671.2411 | 4443803.5431 | 4737094.5769 | 3401006.9537 | 42033473.9079 | 44639549.2902 | 47273282.6983
Vote 7 - PLANNING AND DEVELOPMENT | 3300000 | 3517800 | 3749974.8 | 3997473.1368 | 4261306.3638 | 4542552.5838 | 4842361.0544 | 5161956.884 | 5502646.0383 | 5865820.6768 | 6252964.8415 | 2664458.9507 | 53659315.3301 | 56986192.8806 | 60348378.2606
Vote 8 - COMMUNITY AND SOCIAL SERVICES | 450000 | 479700 | 511360.2 | 545109.9732 | 581087.2314 | 619438.9887 | 660321.962 | 703903.2114 | 750360.8234 | 799884.6378 | 852677.0238 | 1027102.4758 | 7980946.5276 | 8475765.2123 | 8975835.3598
Vote 9 - HOUSING | [11 empty] | 0 | 0 | 0 | 0
Vote 10 - OTHER | 1700000 | 1812200 | 1931805.2 | 2059304.3432 | 2195218.4299 | 2340102.8462 | 2494549.6341 | 2659189.9099 | 2834696.444 | 3021786.4093 | 3221224.3123 | 2932711.1751 | 29202788.7039 | 31013361.6036 | 32843149.9382
Vote 11 - SPORTS AND RECREATION | 900000 | 959400 | 1022720.4 | 1090219.9464 | 1162174.4629 | 1238877.9774 | 1320643.9239 | 1407806.4229 | 1500721.6468 | 1599769.2755 | 1705354.0477 | 4888197.921 | 18795886.0245 | 19961230.958 | 21138943.5845
Vote 12 - BUDGET AND TREASURY | 12800000 | 13644800 | 14545356.8 | 15505350.3488 | 16528703.4718 | 17619597.901 | 18782491.3624 | 20022135.7923 | 21343596.7546 | 22752274.1404 | 24253924.2337 | 21030321.0331 | 218828551.8383 | 241361922.0523 | 89996338.7583
Total Expenditure by Vote | 50020000 | 53321320 | 56840527.12 | 60592001.9099 | 64591074.036 | 68854084.9223 | 73398454.5272 | 78242752.526 | 83406774.1927 | 88911621.2895 | 94779788.2946 | 80920931.1392 | 853879329.9574 | 915785848.4148 | 980662475.0536
Surplus/(Deficit) before assoc. | 3118000 | 3323788 | 3543158.008 | 3777006.4365 | 4026288.8613 | 4292023.9262 | 4575297.5053 | 4877267.1407 | 5199166.772 | 5542311.7789 | 5908104.3563 | -23320500.2034 | 24861912.5818 | 26647151.1619 | 23348522.8754
Taxation | [11 empty] | 0 | 0 | 0 | 0
Attributable to minorities | [11 empty] | 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate | [11 empty] | 0 | 0 | 0 | 0
Surplus/(Deficit) | 3118000 | 3323788 | 3543158.008 | 3777006.4365 | 4026288.8613 | 4292023.9262 | 4575297.5053 | 4877267.1407 | 5199166.772 | 5542311.7789 | 5908104.3563 | -23320500.2034 | 24861912.5818 | 26647151.1619 | 23348522.8754
References
1. Surplus (Deficit) must reconcile with Budgeted Financial Performance

## APPROVAL (hidden)
10. APPROVAL BY THE MAYOR
In line with section 53 of the Municipal Finance Management Act No 56 of 2003 (MFMA), it is a privilege and honor to approve and make public the Service Delivery and Budget implementation Plan (SDBIP) of Makhado Municipality for 2016/2017 financial year. The SDBIP is a contract between the Administration, Council and the Community clearly spelling out how and when the IDP and budget targets for 2016/2017 would be pursued and achieved. It is a management, implementation and monitoring tool that is meant to assist the Mayor, Council, Municipal Manager, Senior Managers and the Community to monitor the municipality’s performance. Makhodo Municipality and its Community have a role to play in achieving the municipality vison that reads "A dynamic hub for socio – economic development by 2025" Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Recommendation by The Municipal Manager: The Municipal Manager hereby recommend for the approval of the SDBIP by the Mayor in line with the above legislation ___________________________ _____________________ Mutshinyali I.P DATE Municipal Manager
Approval by the Mayor The SDBIP 2016/2017 is hereby approved by the Mayor of Makhado Municipality ______________________________ ____________________ Hon Cllr Mutavhatsindi F. D DATE