## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
MID YEAR PERFORMANCE ASSESSMENT REPORT
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
FOR
2015/2016 FINANCIAL YEAR

## TABLE OF CONTENT
TABLE OF CONTENT
1. Strategic Map, Vison and Mission
2. Legislation
3. Municipal Transformation and Organisational Development
4. Baisc service Delivery
5. Municipal Finance Management and Viability
6. Local Economic Development
7. Good Governance and Public Participation
8. Recommendations

## VIS MISS STRA MAP
1. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## LEGISLATION
2. INTRODUCTION AND LEGISLATION
This report is compiled in terms of MFMA, Section 72. (1) The accounting officer of a municipality must by 25 January of each year— (a) assess the performance of the municipality during the first half of the financial year, taking into account— (i) the monthly statements referred to in section 71 for the first half of the financial year; (ii) the municipality’s service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the service delivery and budget implementation plan; (iii) the past year’s annual report, and progress on resolving problems identified in the annual report; and (iv) the performance of every municipal entity under the sole or shared control of the municipality, taking into account reports in terms of section 88 from any such entities; and (b) submit a report on such assessment to— (i) the mayor of the municipality; (ii) the National Treasury; and (iii) the relevant provincial treasury. (2) The statement referred to in section 71(1) for the sixth month of a financial year may be incorporated into the report referred to in subsection (1)(b) of this section. (3) The accounting officer must, as part of the review— (a) make recommendations as to whether an adjustments budget is necessary; and (b) recommend revised projections for revenue and expenditure to the extent that this may be necessary.

## Analysis
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | 1 | 1 | 0 | 0
Performance Management | 4 | 3 | 0 | 1
Human Resources and Organizational Development | 6 | 2 | 3 | 1
Special Programs | 2 | 1 | 0 | 1
Spatial and Town Planning | 16 | 14 | 2 | 0
| 29 | 21 | 5 | 3
|  | 72% | 17% | 10%
83%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster management | 1 | 1 | 0 | 0
Library services | 1 | 0 | 1 | 0
Waste management | 3 | 0 | 2 | 1
Parks and recreational | 3 | 0 | 3 | 0
Electrical provision | 31 | 12 | 14 | 5
Roads | 8 | 4 | 3 | 1
Sports facilities | 3 | 0 | 3 | 0
Building & construction | 4 | 0 | 4 | 0
| 54 | 17 | 30 | 7
|  | 31% | 56% | 23%
55%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL FINANCE AND MANAGEMENT AND VIABILITY
Expenditure management | 4 | 1 | 2 | 1
Revenue Management | 2 | 1 | 0 | 1
Budget and Reporting | 4 | 1 | 0 | 3
Supply Chain Management | 2 | 1 | 1 | 0
Asset Management | 1 | 1 | 0 | 0
| 13 | 5 | 3 | 5
|  | 38% | 23% | 38%
77%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 4 | 0 | 0 | 4
100%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | 1 | 1 | 0 | 0
Fraud and Anti - Corruption | 1 | 1 | 0 | 0
Public Participation | 3 | 3 | 0 | 0
Policies and By Laws | 1 | 1 | 0 | 0
Internal Auditing | 9 | 5 | 2 | 2
Information Technology | 8 | 3 | 4 | 1
Council Services | 2 | 2 | 0 | 0
Communication | 5 | 3 | 0 | 2
| 30 | 19 | 6 | 5
|  | 63% | 20% | 17%
80%
AVERAGE PERFORMANCE
|  | QUARTER 1 | QUARTER 2
MTOD |  | 86% | 83%
BSD | BSD | 79% | 55%
MFMV | LED | 100% | 77%
LED |  | 75% | 100%
GGPP | GGPP | 82% | 80%
TOTAL |  | 422% | 395%
|  | 84.4% | 79%
ORGANISATIONAL PERFORMANCE
| QUARTER 1 |  | QUARTER 2
| TARGET | ACTUAL PERFORMANCE NOTE | TARGET | ACTUAL PERFORMANCE NOTE
CAPITAL BUDGET | 10% | 19% | 40% | 38%
INEP | 10% | 20% | 40% | 45%
MIG | 10% | 27% | 40% | 35%

## MTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for Improvements | Portfolio Of Evidence | Dept | INDICATOR NO
3. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2015 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2016, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2016 | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Conduct Strategic Planning session and compile the IDP strategic chapter | Target achieved | Conduct Strategic Planning session done and compile the IDP strategic chapter done | None | None | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Collect information from departments, Develop a draft SDBIP, Submit to departments for inputs, Incorporate inputs and submit to council for approval by 31 March 2015. Submit to the Mayor for signature, Submit to council for noting. | Makhado Municipality | Income | Operational | Operational | 1/4/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2015 | 8 | 8 | Quarterly performance reports | Develop a reporting template and send to departments, Receive completed template and consolidate into one report. Organise SDBIP Management meeting to consider the report. Submit the report to Council for approval. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 (First Quarter SDBIP performance Report 2015/2016) | Target achieved | 1 (First Quarter SDBIP performance Report 2015/2016) done | None | None | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 3
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2015 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% | Performance agreements | Develop draft performance agreements. Engage the relevant Section 57 Managers. Submit the final performance agreement to Municipal Manager for signing. Submit the signed agreement to MEC for Cooperative Governance Human Settlement and Traditional Affairs. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% | Target achieved | 100% (6/6) | None | None | Signed Performance Agreements | MM | 4
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2015 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Write a memorandum for approval of panel members and dates. Invite the participate Conduct assessment and compile assessment report. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 (Informal Assessment 2014/2015) | Target achieved | 1 (Informal Assessment 2014/2015) done | None | None | Scorecards, Attendance Register | MM | 5
Human Resources and Organizational Development | Invest in human capital | % of municipalities budget actual spent on implementing the WSP 2015/2016 | New Indicator | 0.31% (2596927.18/835130000) | Training inline with the WSP | Spending of budgt on training of employees and councillors | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Section 71 reports | CORP | 6
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Draft Organogram 2015/2016 | Approved Organogram by may 2016 | Organogram review | Reviewing of organizational structure | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Invite inputs from departments regarding the new organogram | Target achieved | Invite inputs from departments regarding the new organogram | None | None | Invitations to the depts, Minutes and attendance register, Council resolutions, | CORP | 7
Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2015 | 67 employees appointed | 30 | Personnel Recruitment | Personnel Recruitment as per priority list | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Shortlisting and appoint of the 1st bench post (10) | Target not achieved | Shortlisting and appoint of the 1st bench post (10) not done | 53 posts advertised in Q1. No short listing of applicants were done due to the verbal moratorium on filling of vacancies made by the MEC for LG TARGET NOT ACHIEVED | Appealed to the MEC and awaiting outcome | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP | 8
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | New Indicator | 8 | Recruitment in terms of EE Plan | Appoint personel at the three highest level following the EE Plan | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Appointment letters | CORP | 9
Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2016 | 6 events | 6 events | Employee Assistance Campaigns | Orgnanize and present Employee Assistance campaigns for all staff in all regions | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 event | Target achieved | 1 event conducted | None | None | Invitations, attendance registers and close-out report | CORP | 10
Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Development of 3 outstanding HR policies | Compile Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy and submit to Council for approval- then implement | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Submit the draft policies to Council for provisional approval | Target not achieved | Submission of the draft policies to Council for provisional approval not done | None | Leave Policy will be submitted in Q3 to the LLF | Approved 3 policies and the council resolutions (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP | 11
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | 15 awards of bursary | Makhado Municipality | Income | 450000 | R0,00 | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Advert, List of qualifying leaners and Letters of bursary awards | CORP | 12
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | 49 events done in 2014/15 | 43 for 2015/16 | Special Programs | Organize and conduct the special programs undertaken in the different desks of the Special Programs Unit | Makhado Municipality | Income | 1250000 | R0,00 | 1/7/2015 | 30/6/2016 | 8 | Target achieved | 8 | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 13
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Application received, Site visits, Stand demarcated and compile a report | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of application received/(# of application attended to within 90 days). | Target not achieved | 100% (# of application received/(# of application attended to within 90 days). | Due to the implementation of SPLUMA applications are no longer submitted to COGHSTA for approval | We are finalising the municiaplity by-law which will be used to approve the PTO application | Site inspection report, Register of applications | DEVP | 14
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Receive housing queries and attend to them in a form of meetings or written correspondence | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of housing queries attended within 30 days/# of received) | Target achieved | 100% 16 (16/16) of housing queries attended within 30 days/# of received) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 15
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2015 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Response to applicant in writing | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of building plans assessed/# of building plans received) | Target achieved | 100% 160 (160 /160) of building plans assessed/160 of building plans received) | None | None | Building plans register | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Target achieved | 100% 9 (9/9) of applications processed/# applications received) | None | None | Zoning certificates issued | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Target achieved | 100% 23 (23/23) of applications processed/# applications received) | None | None | EXCO resolutions | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Target achieved | 100% 21 (21/21) of application for land use rights inspection conducted within 14 days/# of application received) | None | None | Site inspection report, Register of applications | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2015 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% 12 (12/12) of applications processed/# of applications received) | None | None | Copy of occupancy certificates issued | DEVP | 20
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% 4 (4/4) of applications processed/# of applications received) | None | None | Application Assessment Report, Register of applications | DEVP | 21
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% 16 (16/16) of applications processed/# of applications received) | None | None | Application Assessment Report, Register of applications | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% 2 (2/2) of applications processed/# of applications received) | None | None | Application Assessment Report, Register of applications | DEVP | 23
Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Receive application, Send to MM for approval, Notify the applicants to go and pay, After receiving the proof of payment a venue is booked. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target achieved | 100% 28 (28/28) of applications processed/# of applications received) | None | None | Bookings register | DEVP | 24
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Receive complaints, Liaise with the commissioner and complainant, Arrange a meeting if need | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of queries processed/# of queries received) | Target achieved | 100% (# of queries processed/# of queries received) | None | None | Correspondence letters and emails. | DEVP | 25
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Conduct inspection, Upon identifying a contravention a notice is issued | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target achieved | 100% (# of contravention notices issued within 5 days/# of contravention identified) | None | None | Duplicate notices | DEVP | 26
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2015 | 240 | 240 | Routine Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 60 | Target not achieved | 39 | More inspection report has been conducted which affect the routine inspection | Target to be adjusted during the next financiual year | Inspection form, Register | DEVP | 27
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Target achieved | 100% 122 (122/122) of site inspections conducted within 24 hours/# of site inspections application received) | None | None | Inspection form, Register | DEVP | 28
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2015 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Conduct public consultation on street names. Compile a list of street names for approval by Council. | Makhado Municipality | Income | 50000 | R0,00 | 1/7/2015 | 30/6/2016 | Consultations on proposed names. | Target achieved | Consultations on proposed names done. | None | None | Expenditure Report | DEVP | 29

## BSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location/Ward | Funding Source | Budget 15/16 R'000 | Expenditure | 2nd quarter | Performance Remarks | Actual Performance Notes | Progress Made | Challenges | Measures for Improvements | Portfolio of Evidence | Dept | INDICATOR NO
4. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers. Receiving information form stakeholders. Update received informkation into the Disaster Management Plan. Draft Disaster Management Plan completed. Submission of the Disaster Management Plan to the IDP Manager for submission to Council | Makhado Municipality | Income | N/A | N/A | Receiving information from stakeholders. | Target achieved | Information from stakeholders was received. |  | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 30
Library Services | Promote community and environmental welfare | To Refurbish the library roof by 30 June 2016 | Roof dameged | Refurbishment of the library building completed | Refurbish library building | Development of specifications, Advertisement for Contractor. Evaluation, Adjudication and Appointment of Contractor. Construction of roof. Finalisation of the roof and handing over | Makhado Municipality | Income | 1000000 | R0,00 | Evaluation, Adjudication and Appointment of Contractor | Target not achieved | Evaluation not done, Adjudication not done and Appointment of Contractor not done |  | None adherence to procurement plan |  | Project Progress report | TECH | 31
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Coolection of waste in all the villages in ward 22, 23, 24, 25 and 26 | Wrad 22, 23, 24, 25, 26. | Income | Operational | Operational | n/a | n/a | n/a |  | n/a | n/a | Monthly collection reports | MM and COMM | 32
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Landfillsite and recycling centre | Approval to commence with the project from the MM, Development of specification and submit to SCM. Advertisent for tendering. Evaluation, Adjudication and appointment of a service provider. Development of designs and drawings, Construction of 1 x evaporation ponds (excavation, levelling, linning) | Makhado Municipality | MIG | 5 000 000.00 - | 436842.11 | Advertisent for tendering. Evaluation, Adjudication and appointment of a service provider. | Target not achieved | Advertisent for tendering not done. Evaluation not done, Adjudication not done and appointment of a service provider not done. | the specification committee approved specification | Delay in advertising by SCM unit | Follow up with SCM to speed up the process | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM | 33
Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | N/A | Landfill site rehabilitated ompleted | Rehabilitation of the existing Landfill site (Vondelling) | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. Seek quotation for levelling and caping waste with soil and complete the process. Installation of leachete collection pipes. Construction of leachete collection dam. | Makhado Municipality | INCOME | 4000000 | 1851783.11 | Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. Seek quotation for levelling and caping waste with soil and complete the process. | Target not achieved | Advertisement of the tender not done. Evaluation and Adjudication of tenders not done. Appointment of a service provider not done. | Seek quotation for levelling is done and caping waste with soil is done and completion of the process is not yet done. Specification for tendering is approved by the specification committee. | Delay in advertising by SCM unit | Follow up with SCM to speed up the process | Geotechnical report | TECH | 34
Parks and Recreation | Promote community and environmental welfare | To development of 5047 Park by 30 June 2016 | N/A | Development of 5047 Park completed | Development of 5047 Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Makhado Municipality | INCOME | 700000 | 0 | Appointment of service providers | Target not achieved | Appointment of service providers not done | Specification for tendering is approved by the specification committee. | Delay in advertising by SCM unit | Follow up with SCM to speed up the process | Approval memo. RFP, appointment letter, Completion certificate | COMM | 35
Parks and Recreation | Promote community and environmental welfare | To develop the N1 recreational park by 30 June 2016 | N/A | Development of N1 recreational park completed | Development of N1 recreational park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park |  |  | 300000 | 436842.11 | Appointment of service providers | Target not achieved | Appointment of service providers not done | Specification for tendering is approved by the specification committee. | Delay in advertising by SCM unit | Follow up with SCM to speed up the process | Approval memo. RFP, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat by | N/A | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat completed | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Makhado Municipality | `+++++++++++++++++ | 500000 | R0,00 | Appointment of service providers | Target not achieved | Appointment of service providers not done | Specification for tendering is approved by the specification committee. | Delay in advertising by SCM unit | Follow up with SCM to speed up the process | Approval memo. RFP, appointment letter, Completion certificate | COMM | 37
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Magau/Makhitha/Tshikodobo/Zamekomste by 30 June 2016 | N/A | MAGAU/Makhitha/Tshikodobo/Zamekomste connection completed | MAGAU | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, switching on and completion of the project | Makhado Municipality | INCOME | 935201.32 | 611451.45 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Target achieved | Site handover done, appointment of labour done, Surveying of pole holes done, excavating the pole holes done, dresing and planting of poles done, stringing of conductors done |  | none | none | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 38
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at MAGULULE by 30 June 2016 | N/A | TSHIOZWI /GOGOBOLE connection completed | TSHIOZWI & GOGOBOLE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on. Completion of the project | Makhado Municipality | INCOME | 2101576 | 176000 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Target achieved | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors |  | none | none | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 39
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ramantsha by 30 June 2016 | N/A | Ramahantsha /Riverside connection completed | RAMANTSHA/RIVERSIDE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | Makhado Municipality | INCOME | 1281962 | 644387.8 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Target achieved | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors |  | none | none | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 40
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Madodonga/Manavhela by 30 June 2016 | N/A | Madodonga/Manavhela connection completed | MADODONGA | Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | Makhado Municipality | INCOME | 1681261 | 1392455 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Target achieved | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors |  | none | none | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 41
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mamburu by 30 June 2016 | N/A | Mamburu connection completed | Mamburu | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication. Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. Excavating the pole holes dresing and planting of poles, stringing of conductors. Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate | Makhado Municipality | INEP | 2250000 | R0,00 | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target not achieved | Appointment of engineer is done and contractor done, Site handover to contractor not done, site establishment not done, appointment of labour not done, Surveying of pole holes not done. |  | Delay in terms of design by the engineer | The completion designs to be completed by the end of December | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Makhushu by 30 June 2016 | N/A | Makhushu connection completed | MAKUSHU | Development specification for contractor, materials and works, Approval of specification, advertisement, evaluation, adjudication and appointment. Site handover to the contractor, site establishment, appointmnet of labour, survying pole holes, excavating poleholes, dress and plant pole holes and string of conductors. Service connections. Switching on and completion of the project | Makhado Municipality | INEP | 490000 | R0,00 | Site handover to the contractor, site establishment, appointmnet of labour, survying pole holes, excavating poleholes, dress and plant pole holes and string of conductors | Target not achieved | Site handover to the contractor, site establishment, appointmnet of labour, survying pole holes, excavating poleholes, dress and plant pole holes and string of conductors |  | Delay in terms of design by the engineer | The completion designs to be completed by the end of December | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | Designs for 2016/2017 electrification projects ) by 30 June 2016 | N/A | Designs for 2016/2017 electrification projects completed | Designs for 2016/2017 electrification projects | Development of specification for engineer, approval of specs, Advertisement. Evaluation, Adjudicationa nd appointment of the engineer.Completion of designs, designs approval by ESKOM, technical electrification forum meeting. | Makhado Municipality | INEP | 952500 | 952500 | Development of specification for engineer, approval of specs, Advertisement | Target not achieved | Development of specification for engineer, approval of specs, Advertisement |  | The project has been amended to become the elecrItification of VYEBOOM project | Adjudication , appointment done and designs appoved by Eskom | Specifications, Advertisement, appointment letter, Designs, Minutes of of technical forum meeting | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | To upgrade Industrial line by 30 June 2016 | N/A | Upgrading Industrial line | Upgrading Industrial line | Planning and designs, appointment of labour, procurement of PPE, prepare alternative supply, bush clearing phase 1, pegging phase 1, excavating of pole holes for phse 1. Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. bush clearing phase 2, pegging phase 2, excavating pole holes phase 2.Dress and plant poles phase 2, strining of conductors phase 2, closing spans phase 2 | Makhado Municipality | INCOME | 250000 | 132729.47 | Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply | Target not achieved | Excavation of poles and and delivey of poles done |  | Breadown of truck to deliver the poles | The truck has been serviced | Designs, Appointment letter for labourers, Project progress report, | TECH | 45
Electricity Provision | Accessible basic and infrastructure services | To upgrade Shefeera Line by 30 June 2016 | N/A | Upgrade Shefeera Line | Upgrade Shefeera Line | Upgrade Shefeera Line. Appointment of labour, procurement of PPE, bush clearing and mpegging. Excavating pole holes, dress and plant poles. Stringing of conductors, closing spans | Makhado Municipality | INCOME | 600000 | 142236.99 | Excavating pole holes, dress and plant poles | Target achieved | Excavating pole holes done, dress and plant poles done |  | None | None |  | TECH | 46
Electricity Provision | Accessible basic and infrastructure services | To upgrade Urban Substations by 30 June 2015 | N/A | Upgrade Urban Substations | Upgrade Urban Substations | Upgrade Urban Substations. Completion of upgarde designs, contractor specification compilation. Advertisent for tendering. Evaluation. Adjudication and appointment of contractor.Procurement of upgrade equipment fo Stubb street substation | Makhado Municipality | INCOME | 2500000 | 211621.21 | Advertisent for tendering. Evaluation | Target achieved | Advertisent for tendering. Evaluation |  | None | None |  | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To upgrade Mountain line by 30 June 2016 | N/A | Upgrading Mountain line | Upgrading Mountain line | Planning and designs, appointment of labour, procurement of PPE, bush clearing and, pegging, excavating of pole holes. Dress and plant poles, stringing of conductors. closing spans, pegging, exate pole holes. Dress and plant poles, strining of conductors, closing spans | Makhado Municipality | INCOME | 250000 | 153767.21 | Dress and plant poles, stringing of conductors | Target not achieved | Dress and plant poles done, stringing of conductors not done |  | Breadown of truck to deliver the poles | The truck has been serviced |  | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute Beaufort West line by 30 June 2016 | N/A | Upgrade and reroute of Beaufort West line completed | Upgrade and reroute Beaufort West line | Surveying of the pole holes and excavating pole holes | Beaufort West line | INCOME | 1500000 | R0,00 | Adjudication, appointment and site handover | Target not achieved | Adjudication done, appointment and site handover not done |  | Non adherence to procurement plan | To speed up the process of appointing the contractor by January 2016. | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH | 49
Electricity Provision | Accessible basic and infrastructure services | To replace oil curcuit breaker by 30 June 2016 | N/A | Replacement of oil curcuit breaker completed | Oil | Replace oil curcuit breaker |  | INCOME | 400000 | 42700 | Evaluation and adjudication | Target achieved | Evaluation done and adjudication done |  | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | N/A | Replacement of channel cover completed | Substation channel cover replacements | Replacement of channel cover |  | INCOME | 200000 | R0,00 | Adjudication and appointment of service provider | Target not achieved | Adjudication not done and appointment of service provider not done |  | The received bids were non responsive | To re-advetisement the project by third quarter | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | N/A | Standby generator installed | Standby (Backup) Electricity Power Generator-Dzanani | Installation of standby generator | Dzanani | INCOME | 250000 | 217777.28 | Evaluation and adjudication | Target achieved | Evaluation done and adjudication done |  | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To replace air conditioner by 30 Septemeber 2015 | N/A | Air Conditioners replaced | Air Conditioners | Replacement of air conditioner | Makhado | INCOME | 150000 | 128768 | N/A | N/A | N/A | N/A | N/A | N/A | Orders and project progress report | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | N/A | CT VT Units 11kv & 22kv replaced | CT VT Units 11kv & 22kv | Replacement of CT VT Units 11kv & 22kv | Makhado | INCOME | 300000 | R0,00 | Adjudication and appointment of service provider | Target not achieved | Adjudication not done and appointment of service provider not done |  | Non adherence to procurement plan | To speed up the process of appointing the contractor by third quarter. | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming Bravo 9 and A21 by 31 March 2016 | N/A | Low voltage to medium voltage in Rural Farming Bravo 9 and A21 upgraded | Low voltage to medium voltage in Rural Farming Bravo 9 and A21 | Ugrading Low voltage to medium voltage , Bravo 9 and A21 | Makhado | INCOME | 250000 | 248887.52 | Closing span, LV voltage inatallation and proct competion. Planning, bush clearing, pagging . | Target achieved | Closing span, LV voltage inatallation and proct competion. Planning, bush clearing, pagging done |  | None | None | Project progress report | TECH | 55
Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | N/A | Mini Subs replaced | Mini Subs | Replacement of Mini Subs | Makhado | INCOME | 900000 | 665000 | Delivery of materials | Target achieved | Delivery of materials done |  | None | None | Specification, orders, delivery notes | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | N/A | MV Cable 95mm 22kV replaced | MV Cable 95mm 22kV | Replacement of MV Cable 95mm 22kV | Makhado | INCOME | 150000 | 136500 | Delivery of materials | Target achieved | Delivery of materials done |  | None | None | Specification, orders, delivery notes | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | N/A | Recloser and controllers whole network procured | Recloser and controllers whole network | Procure, supply and delivery of recloser and controllers whole network | Makhado | INCOME | 700000 | R0,00 | Appointment of service providers and delivery of materilals | Target achieved | Appointment of service providers and delivery of materilals done | None | None | None | Specification, orders, delivery notes, progress report, completion certificate | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | N/A | Remote control of switch gear Tshipise & Levubu procured | Remote control of switch gear Tshipise & Levubu | Procure, supply and delivery of remote control of switch gear Tshipise & Levubu | Makhado | INCOME | 120000 | R0,00 | Evaluation and adjudication | Target achieved | Evaluation and adjudication done | None | None | None | Specification, advertisement, appointment letter, payment certificate | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Replacement of Ring Main Units 11 kV (RMU) | Makhado | INCOME | 300000 | 270000 | Delivery of materials (manufacturing | Target achieved | Delivery of materials (manufacturing done | None | None | None | Specification, order, delivery note, project progress report, payment certificate | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To constuct Standby quarter perimeter wall by 31 March 2016 | N/A | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Construction of standby quarter perimeter wall | Makhado | INCOME | 60000 | 60000 | Construction of break work (internal staff | Target not achieved | Construction of break work (internal staff |  | Inssufficient budget for the construction of project | Budget to be adjusted | Specification, advertisement, project progress report | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | N/A | Standby quarter guard room completed | Standby quarter guard room | Construction of standby quarter guard room | Makhado | INCOME | 25000 | R0,00 | Construction of break work (internal staff | Target not achieved | Construction of break work (internal staff |  | Inssufficient budget for the construction of project | Budget to be adjusted | Specification, advertisement, project progress report | TECH | 62
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village connection completed | Wisagalaza 2 & Chitasi village | Electricity connections | Wisagalaza village | INEP/ | 7771500 | 8026487.19 | Dress and planting of poles, stringing of conductors | Target achieved | Dress and planting of poles done, stringing of conductors done |  | None | None | Appointment letter, project progress report, completion certificate | TECH | 63
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at SUKANI by 30 June 2016 | N/A | SUKANI connection completed | SUKANI | Electricity connections | SUKANI | INEP | 1392000 | R0,00 | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target not achieved | Appointment of engineer is done and contractor done, Site handover to contractor not done, site establishment not done, appointment of labour not done, Surveying of pole holes not done. |  | Delay in terms of design by the engineer | The completion designs to be completed by the end of December | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at TSHIVHULANA by 30 June 2016 | N/A | TSHIVHULANA connection completed | TSHIVHULANA zone 5 | Electricity connections | TSHIVHULANA zone 5 | /INCOME INEP | 1632000 | R0,00 | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target not achieved | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. Project cancelled |  | The project was prioritised by Eskom | Money for the project to be transferred to another project | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 65
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ratombo/ by 30 June 2016 | N/A | RATOMBO connection completed | RATOMBO | Electricity connections | RATOMBO | INEP /income | 1472000 | R0,00 | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target not achieved | Appointment of engineer is done and contractor done, Site handover to contractor not done, site establishment not done, appointment of labour not done, Surveying of pole holes not done. |  | Delay in terms of design by the engineer | The completion designs to be completed by the end of December 2015 | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 66
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at MUKONDENI by 30 June 2016 | N/A | MUKONDENI connection completed | MUKONDENI & Freedom Lusaka | Electricity connections | MUKONDENI & Freedom Lusaka | INEP | 1040000 | R0,00 | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target not achieved | Appointment of engineer is done and contractor done, Site handover to contractor not done, site establishment not done, appointment of labour not done, Surveying of pole holes not done. |  | Delay in terms of design by the engineer | The completion designs to be completed by the end of December 2015 | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 67
Electricity Provision | Accessible basic and infrastructure services | Electrification Rabali Stadium by 30 June 2016 | N/A | Electrification Rabali Stadium facility completed | Electrification Rabali Stadium | Electrification Rabali Stadium | Makhado Municipality | Income | 150000 | 118453.84 | Evaluation, adjudication and appointment | Target achieved | Evaluation done , adjudication done and appointment done |  | None | None | Specifications, Advertisement, Apointment letter, delivery notes, | TECH | 68
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshikota access road by 30 June 2016 | Gravell road | Tshikota upgrading of streets and Pretorius completed | Completion of Tshikota upgrading of streets and Pretorius | Tshikota upgrading of streets and Pretorius | Makhado Municipality | MIG | 1936405 | 1793613.68 | N/A | N/A | N/A | N/A | N/A | N/A | Project progress report, handover report | TECH | 69
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To upgrade Magau road phase 2 by 30 June 2016 | Gravell road | Magau road phase 2 completed | Magau road phase 1 | Magau road phase 1 | Makhado Municipality | MIG | 22000000 | 18476550.73 | Completion of the bridge and Completion of roadbed. | Target achieved | Completion of the bridge done and Completion of roadbed done. |  | None | None | Project progress report, Completion certificate, handover report | TECH | 70
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhulana to Tshilaphala access road by 30 June 2016 | Gravell road | Tshivhulana to Tshilaphala access road constructed to a base level. | Tshivhulana to Tshilaphala access road | Tshivhulana to Tshilaphala access road | Makhado Municipality | MIG | 13976988.13 | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of Contractor. |  | None | None | Specifications, advertisement, appointment letter, project progress report | TECH | 71
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road by 30 June 2016 | Gravell road | Ledig road completed | Ledig road | Ledig road construction | Makhado Municipality | MIG | 9387156 | 14903182.78 | Surfacing and Handover | Target achieved | Surfacing done and Handover done |  | None | None | Project progress report, handover report | TECH | 72
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road by 30 June 2016 | N/A | Robert Khoza /Chabani Bungeni road completed | Robert Khoza /Chabani Bungeni road construction | Robert Khoza /Chabani Bungeni road | Makhado Municipality | MIG | 23000000 | 11273617.78 | Bridge foundation (extension), Base construction, site drainage structures construtcion | Target not achieved | Bridge foundation done (extension), Base construction done, site drainage structures construtcion not done |  | Prioritisation of acivities on site | Site drainage structures construtcion to be completed during third quarter | Site establishment report, project progress report, handover report | TECH | 73
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road phase 1 by 30 June 2016 | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | Tshivhazwaulu to Rasivhetshela road phase 1 | Tshivhazwaulu to Rasivhetshela road phase 1 | Makhado Municipality | MIG | 23811987.67 | 13949274.91 | Completion of the bridge and Completion of roadbed. | Target achieved | Completion of the bridge done and Completion of roadbed done. |  | None | None | Site establishment report, project progress report, handover report | TECH | 74
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct a new bridge at Mudimeli by 2018 | N/A | Mudimeli bridge completed by 2018 | Mudimeli bridge | Construction of Mudimeli bridge | Makhado Municipality | MIG | 5 758 786. - | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Evaluation not done, Adjudication not done and Appointment of Contractor not done. |  | Constraints in MIG allocation | Design and planning of bridge in the current financial year | Specifications, advertisement, appointment letter, project progress report | TECH | 75
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads abd bridge projects by 30 June 2016 | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access roaGombiti,Tshivhuyuni,Muwaweni to Mphage road completed | Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access roaGombiti,Tshivhuyuni,Muwaweni to Mphage road | Planning of new road/bridges | Makhado Municipality | MIG | 1 600 000 | R0,00 | Evaluation, Adjudication and Appointment of Consulting Engineers. | Target not achieved | Evaluation not done, Adjudication not done and Appointment of Consulting Engineers not done. |  | Non adherence to procurement plan | Appointment of consulting engineers by February 2016 | Advertisement copy, appointment letter, design report. | TECH | 76
Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Upgrading of Vuwani sports facilities | Upgrading of Vuwani sports facilities | Makhado Municipality | MIG | 2492678 | 3195916.9 | Construction of roof and handing over | Target not achieved | Construction of roof not done and handing over not done |  | Delay of construction due to public protest | the project is in progress and to be completed in third quarter | Project progress report, handover report | TECH | 77
Sports Facilities | Accessible basic and infrastructure services | To construct concrete palisade by 30 June 2016 | N/A | Provision of concrete palisade Waterval completed | Construction of concrete palisade at Waterval stadium | Construction of concrete palisade at Waterval stadium | Makhado Municipality | MIG | 800000 | R0,00 | Evaluation, Adjudication and Appointment of Consulting Engineers. | Target not achieved | Evaluation, Adjudication and Appointment of Consulting Engineers. |  | The scope of work has been changed planning and desings for the next financial year | The scope of work for the planning and desings has advertised | Advertisement copy, appointment letter, design report. | TECH | 78
Sports Facilities | Accessible basic and infrastructure services | To construct ablution facility by 30 June 2016 (Waterval Stadium) | N/A | Provision of Waterval stadium ablution facility completed | Construction of ablution facility at Waterval stadium | Construction of ablution facility at Waterval stadium | Makhado Municipality | MIG | 300000 | R0,00 | Evaluation, Adjudication and Appointment of Consulting Engineers. | Target not achieved | Evaluation not done, Adjudication and Appointment of Consulting Engineers not done. |  | The scope of work has been changed planning and desings for the next financial year | The scope of work for the planning and desings has advertised | Advertisement copy, appointment letter, design report. | TECH | 79
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing | Makhado Municipality 2 per region | MIG | 2000 000.00 | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Evaluation, Adjudication and Appointment of Contractornot done. |  | Non adherence to procurement plan | Advertisement done and the appointment of contractors by February 2016 | Advertisement copy, appointment letter,project progress report, handover report | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Fencing Vuwani Cemetery | Fencing Vuwani Cemetery | Makhado Municipality | Income | 300000 | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Evaluation, Adjudication and Appointment of Contractor. |  | Non adherence to procurement plan | Advertisement done and the appointment of contractors by February 2016 | Advertisement copy, appointment letter,project progress report, handover report | TECH | 81
Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | N/A | Vuwani cemetry Ablution Facility completed | Vuwani Cemetery ( Toilet ) | Vuwani Cemetry ( Toilet ) | Makhado Municipality | Income | 70000 | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Evaluation, Adjudication and Appointment of Contractor. |  | Non adherence to procurement plan | Advertisement of the project done | Advertisement copy, appointment letter,project progress report, handover report | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | N/A | Graveyard fencing completed | Fencing grave yard +sliding gate(Dzanani cemetery) | Fencing grave yard +sliding gate(Dzanani cemetery) | Dzanani township | Income | 300000 | R0,00 | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Evaluation, Adjudication and Appointment of Contractor. |  | Non adherence to procurement plan | Advertisement of the project done | Advertisement copy, appointment letter,project progress report, handover report | TECH | 83

## MFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Project Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End date | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for Improvements | Portfolio Of Evidence | Dept | INDICATOR NO
5. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Capture spending on capital project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 163938800.12 | 98074257.78 | 1/7/2015 | 30/6/2016 | 40% | Target not achieved | 38% R 62,734,172 capital budget spent | None | None | Quarterly Financial Report | MM and All Directors | 84 | 7539142
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Capture spending on MIG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 112264000 | 78973790 | 1/7/2015 | 30/6/2016 | 40% | Target achieved | 45% R 50,591,325.80 MIG spent | None | None | Quarterly Financial Report | MM | 85 | 5690000
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Capture spending on INEP project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 17000000 | 8947761.66 | 1/7/2015 | 30/6/2016 | 40% | Target not achieved | 35% R 6,000,000 INEP spent | None | None | Quarterly Financial Report | MM | 86 | 0.75473
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Capture spending on FMG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 1600000 | 625115.9 | 1/1/2016 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Expenditure Report | B&T | 87
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Collection of payment for services such as electricity, property rates, refuse removal | Makhado Municipality | Income | 342227123 | 78740467.6 | 1/7/2015 | 30/6/2016 | 45% | Target achieved | 89% of revenue collected | None | None | Section 71 report (c1 schedule) | B&T | 88
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Send the policies for inputs by other department. Present the draft review to management. Submit to council for approval. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 89
Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to council | Draft budget | Collect budget from departments, Consolidate the budget, Present the draft to management, Submit to Council for approval | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Draft budget and Council Resolution | B&T | 90
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget was submitted to council | Final budget submitted to council | Final budget | Take the draft budget for public participation with the IDP. Incorporate inputs and submit the budget for final approval | Makhado Municipality | Income | Operational | Operational | 1/4/2016 | 31/5/2016 | N/A | N/A | N/A | N/A | N/A | Final budget and Council Resolution | B&T | 91
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Compile the financial statement. Review the compiled financial statement. Present to management meeting. Submit to AG for auditing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 31/8/2015 | N/A | N/A | N/A | N/A | N/A | Copy of Financial statements | B&T | 92
Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Section 71 report submission | Compile the section 71 report. Submit to treasury within 10 days after month end. Submit to council for approval. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 3 | Target achieved | 5 section 71 reports were compiled and submitted to treasury within 10 days after month end. | None | None | Copy of acknowledgement of receipt by Treasuries | B&T | 93
Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Tender adjudication | Set date for adjudication committee. Adjudicate tenders within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Target achieved | 100%(14 bids were finalised within 90 days | None | None | Monthly Tender Reports | B&T | 94
Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | Quotations | Set date for quotation committee. Assess the quotation within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of quotations processed/# of quotations received) | Target not achieved | 87% (# of quotations processed/# of quotations received) | Delays in getting quots from service providers | Increase number of service providers when inviting quotations | Quotations Report | B&T | 95
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Asset Register | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Target achieved | Acquisitions done, Bar code captured into the asset register. Capture the expense of the project in progress. | None | None | Schedules of Asset Register movement | B&T | 96

## LED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for Improvements | Portfolio Of Evidence | Dept | INDICATOR NO
6. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Community works programme, Expanded public works programme, Community projects | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 97
Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2015 | N/A | Development of Makhado information and recreational centre completed | Makhado N1 Information and Caravan Recreational/Entertainment centre | Advertisement of the project. Evaluation and Adjudication, Appointment of a contractor. | Makhado Municipality | Income | 500000 | 436842 | 01/01/2016 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, Appointment letter (contractor) | DEVP | 98
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2014 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Identify the officials to serve Host Makhado annual show | Makhado Municipality | Income | 159300 | 1171872 | 1/7/2015 | 30/9/2016 | N/A | N/A | N/A | N/A | N/A | Annual Show Report and Audited Financial Statements | DEVP | 99
Local Economic Development | Invest in local economy | # of LED projects supported 30th June 2014 | 9 | 6 | LED Strategy | Community works programme, Transnet/Furniture, Rural Farmers (tractor landing), Salaunavhe Poultry farm, Local Builder Training (NHBRC), Dzanani Informal traders facility | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/9/2016 | N/A | N/A | N/A | N/A | N/A | LED strategy implementation report | MM and DEVP | 100

## GGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End date | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for Improvements | Portfolio Of Evidence | Dept | INDICATOR NO
7. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate 13 risk management activities by 30 June 2016 | 13 activities were cordinated | 13 risk activities cordinated | Risk Management project | Facilitate and coordinate risk management meetings | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 3 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Operational Risk Assessment Report developed, Risk Management Committee Meeting held) | Target achieved | 3 risk activities were done (Develop Quarterly Strategic Monitoring Risk Report were conducted, Operational Risk Assessment Report developed, Risk Management Committee Meeting was held) | None | None | Attendance register, Minutes and Programme | MM | 101
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 100% (# of cases attended/# of cases reported) | Target achieved | 100% (1/1) | None | None | Case Register | MM | 102
Public Participation | Good governace and Administrative Excellence | To develop the public participation by 31 March 2016 | No policy | Public Participatuion policy approved by Council | Public Participation Policy | Compile Public Participation Policy and submit to Council for approval | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 31/3/2016 | Conduct public consultation of the draft public participation policy | Target achieved | Conduct public consultation of the draft public participation policy was done | None | None | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 103
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 3o June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 38 wards | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Target achieved | 114 ward committee meetings coordinated and quarterly ward committees' report was to Council. | None | None | Minutes, Attendance register, Ward committee quarterly report | CORP | 104
Public Participation | Good governace and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | 2 | 2 | Training of ward committees | Arrange and coordinate training event of all ward committees for at least 2 events | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | Training of 38 ward committees Compile a close out report (1st training) | Target achieved | Training of 38 ward committees Compile a close out report (1st training) was not conducted | None | None | Training attendance register; training curriculum | CORP | 105
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 6 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool Quarry Pound Street and diverse Financial Hawkers and Market | Makhado Municipality | Income | OPEX | Operational | 01/07/2015 | 30/06/2016 | Submit the 6 draft 6 policies to Council for provisional approval | Target achieved | Submit the 6 draft 6 policies to Council for provisional approval | None | None | 6 draft policies Council resolution Invitations, attendance registers, Final council resolutions and Promulgation notice for by laws | CORP | 106
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality | Income | OPEX | Operational | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM | 107
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality | Income | OPEX | Operational | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 108
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Implementation of the Approved Internal Audit Plan | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 100% (# of projects executed/# of projects in the action plan) | Target achieved | 100% (1/1) | None | None | Internal Audit report to Audit and Performance Audit Committee | MM | 109
Internal Auditing | Good governace and Administrative Excellence | % implementation of the AG(SA) action plan by 30 June 2016 | 80% | 100% | AG(SA) action plan | Implementation of the AG(SA) action plan | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 100% (# of queries resolved/# of queries in the action plan) | Target not achieved | 52% of queries resolved/# of queries in the action plan) |  | Intervention continous operation clean audit activities. | Progress report | All departments | 110
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | 7 | 7 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 2 | Target achieved | 2 | None | None | Minutes, Attendance register, invitations | MM | 111
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | 4 | 4 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | None | None | Council resolution, Attendance register | MM | 112
Internal Auditing | Good governace and Administrative Excellence | # of Audit Steering Committee meetings held by 30 June 2016 | 8 | 8 | Audit Steering Committee | Organize Audit Steering Committee meetings | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 2 | Target achieved | 2 | None | None | Minutes, Attendance register, invitations | MM | 113
Internal Auditing | Good governace and Administrative Excellence | # of OPCA meetings held by 30 June 2016 | 6 | 6 | Operation Clean Audit (OPCA) | Organize OPCA meetings | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 2 | Target not achieved | 2 | Meeting were not held due to the fact that the process was suspended because of audit steering committee meetings | to be reviewed during adjustment | Minutes, Attendance register, invitations | MM | 114
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 2 | 2 | IAA and APAC Assessment report | Organize IAA and APAC Assessment report and submit to council | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | To be reviewed during adjustment | To be reviewed during adjustment | Report, Council Resolution | MM | 115
Information Technology | Good governace and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Manual system | Computerized call center system | Upgrade municipal call center | Upgrade municipal call center from manual system to computerized logging, recording and referencing system and audio recording system according to needs of business units Phase 1 2015/2016 - the logging and referencing system Phase 2 - Audio recording system for 2016/2017 | Civic Center | Income | R3000,000 | R0,00 | 1/7/2015 | 31/3/2016 | Evaluation of RFP and decide whether to appoint a service provider or not | Target not achieved | Evaluation of RFP and decide whether to appoint a service provider or not | The non progress is failure to come to a solid conclusion on what features the software for a recording and logging call center system must be vis a vis the business process which comprise of multiple disciplines. Senior Managers to advise the way forward on proposal of Call Centre System to suit their business processes' needs. However this call center system needs to be compared to other systems. | Bytes Integrated System to propose their call center system in the 3rd Quarter. The way forward be concluded in Q3 and quotations be called accordingly - PROJECT CONTINUES TO Q3 | Advertisement for RFP | CORP | 116
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 december 2015 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Increase speed of server output to networks for data transfer between workstations and servers | Civic Center and regional offices | Income | R200,000 | 159225.99 | 1/7/2015 | 31/3/2016 | Install the networks hubs, switching and commissioning of the project | Target achieved | Installation of the networks hubs, switching and commissioning of the project is done | None | None | Orders, Payment certificate and intallation report | CORP | 117
Information Technology | Good governace and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Phase 1 done | Complete server upgrade project | Upgrade of servers | Complete upgrade of servers - expansion of data centre server | Civic Center | income | R200,000 | 148957.93 | 1/7/2015 | 31/3/2016 | Install the expansion data server and commissioning according to the project agreement with the service provider | Target achieved | Install the expansion data server and commissioning according to the project agreement with the service provider | None | None | Appointment letter, Project agreement, installation report and payment certicate | CORP | 118
Information Technology | Good governace and Administrative Excellence | To upgrade the internet dataline by 31 March 2016 | Existing dataline too slow | Internet dataline upgraded | Internet dataline upgrade | Upgarde the internet dataline to optimise speed for offsite backups and internet use. (Changed from Upgrade of TMS) | Civic center | Income | R150,000 | R0,00 | 1/7/2015 | 31/3/2016 | Official order to TELKOM and commissioning of upgrade | Target achieved | Official order to TELKOM and commissioning of upgrade | None | None | Approved memorandum, TELKOM agrement, Close out report, Proof of payment | CORP | 119
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Upgrade server room | Upgrade of server room by removing carpets and workstation equipment | Civic Center | Income | R70,000 | R0,00 | 1/7/2015 | 31/3/2016 | Evaluate PINACLE AFRAC'S proposal and decide on the wayforward | Target not achieved | Evaluate PINACLE AFRAC'S proposal and decide on the way forward not done | Core function of UPS is functioning - Monitor online card is yet to be installed - the SP has not yet been paid | None (Closure report will be processed in December 2015 to add as evidence - online cared was delivered on 10 December 2015 for commissioning - still under monitoring) | Approved memorandum, Written propoal, wayforward outcomes | CORP | 120
Information Technology | Good governace and Administrative Excellence | To procure video editing software by 31 December 2015 | N/A | Procure video editing software | Procure video editing software | Procure Video Editing software suitable for use by business process owner | Civic Center | Income | R10,000 | R0,00 | 1/7/2015 | 2015-01-12 | Award, procure and install | Target not achieved | Award, procure and install not done | None | None | Appointment letter, Installation, report; payment certificates, | CORP | 121
Information Technology | Good governace and Administrative Excellence | To procure ICT office equipment 31 March 2016 | 2014/15 critical needs only | According to needs analysis | Procure ICT office equipment | Procure laptops, computers, printers and desktops according to accurate needs analysis | Civic Center | Income | R200,000 | 5263.04 | 1/7/2015 | 31/12/2015 | Evaluation of service providers sauced through SCM and appointment. Determine the institutional need and place order with the appointed service provider | Target not achieved | Evaluation of service providers sauced through SCM and appointment. Determine the institutional need and place order with the appointed service provider not done | Technical specifications were not in order; the survey of needs are kept by Snr ICT Officer and can be made available on request; a further challenge is that SCM is forbidding that we standardize equipment to be HP while ICT Gov Comt approved that we standardize | Requested SCM to call for tenders / quotations a new. Procurement will proceed in Q3 according to identified priorities and per quotation basis. Postpone IMP Committee meeting to January 2016 | Appointment letter, Orders, payment certificates and Asset Register | CORP | 122
Information Technology | Good governace and Administrative Excellence | To procure hand held communication radios 30 September 2015 | N/A | 2 | Hand held communication radios | Procure two (2) hand held communication radios for registry staff to communicate | Civic Center | Income | R10,000 | R0,00 | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Appointment letter, payment certificates, | CORP | 123
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 Council meeting was held | None | None | Minutes, Attendance register, notice of invitations. | CORP | 124
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 6 | Target achieved | Six (6) Executive Committee meetings were held during Q2 | None | None | Minutes, Attendance register, notice of invitations. | CORP | 125
Communication | Good governace and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | N/A | 2 | Television sets | Procure and install television sets in the Office of the Speaker and the Office of the Chief Whip | Civic Center | Income | R20,000.00 | 18144 | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP | 126
Communication | Good governace and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | N/A | 2 | Decoders | Procure and install decoders for DSTV in the Office of the Speaker and the Office of the Chief Whip | Civic Center | Income | OPEX | Operational | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | Decoders and payment certificates | CORP | 127
Communication | Good governace and Administrative Excellence | To procure 2 X radios of regional broadcasting stations BY 30 June 2016 | N/A | 2 | Radios | Procure radios for regional broadcasting services that also have a recording function | Civic Center | Income | R800.00 | 1785.6 | 1/7/2015 | 30/9/2015 | Procure radios for regional broadcasting services | Target achieved | Two transistor radios procured and delivered on 26 October 2015 in Communications office | None | None | Radios and payment certificates | CORP | 128
Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Reviewed Bathopele service standards | Review the 2014/15 ed Makhado Bathopele Service Standards and submit to Council for approval | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | Submit reviewed Service Standards to Council for approval | Target achieved | Service Standards was reviewed and submited to Council for approval | None | None | Approved 2015 Batho Pele Service Standards | CORP | 129
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Comprehensive website policy | Develop website policy for approval by Council | Civic Center | Income | OPEX | Operational | 1/7/2015 | 30/9/2015 | Implement website policy | Target achieved | Website policy was implemented | None | None | Council approval of policy | CORP | 130
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 | None | None | Attendance register and Programme | CORP | 131
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Imbizo Feedback Session | Giving Feedback to community on service delivery issues raised during 2014/2015 financial year | Makhado Municipality | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Attendance register and program | CORP | 132
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework BY 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | Income | Income | OPEX | Operational | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Approved Stakeholders management Framework and council resolution | CORP | 133
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | Income | Income | OPEX | Operational | 1/7/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Approved Communication strategy and council resolution policy and council resolution | CORP | 134

## RECOMMENDATIONS
8. RECOMMENDATIONS
After conducting the service delivery assessment, the following recommendations are made that:
1. The SDBIP targets be adjusted
2. The SDBIP be adjusted in line with the AG-SA findings
3. The Budget of the Municipality be adjusted to cater for the shortfalls
4. That the purchase of small items that was not done be completely adjusted
MUNICIPAL MANAGER
IP MUTSHINYALI DATE