## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
ADJUSTED SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
FOR
2016/2017 FINANCIAL YEAR
THIRD QUARTER PERFORMANCE REPORT

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vision and Mission
3. Departments
4. Higher Level SDBIP
5. Lower SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. Monthly Cashflow
7. Monthly Revenue and Expenditure
8. Monthly Capital Expenditure
9. Mothly Expenditure by Vote
10. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1) of MFMA states that On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must—
(a) consider the statement or report;
(b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan;
(c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget;
(d) issue any appropriate instructions to the accounting officer to ensure—
(i) that the budget is implemented in accordance with the service delivery
and budget implementation plan; and
(ii) that spending of funds and revenue collection proceed in accordance
with the budget;

## ANALYSIS (hidden)
THIRD QUARTER ANALYSIS REPORT 2016/17 FY
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
THIRD QUARTER ANALYSIS REPORT 2016/17
Integrated Development Planning | 1 | 1 | 0 | 0
Performance Management | 5 | 4 | 0 | 1
Human Resources and Organizational Development | 11 | 9 | 1 | 1
Special Programs | 2 | 1 | 0 | 1
Spatial and Town Planning | 21 | 15 | 4 | 2
| 40 | 30 | 5 | 5
TOTAL |  | 75% | 12.5% | 12.5%
87.5%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | 1 | 1 | 0 | 0
Library Services | 1 | 0 | 1 | 0
Waste Management | 1 | 1 | 0 | 0
Parks and Recreational | 2 | 1 | 1 | 0
Protection Services | 1 | 0 | 1 | 0
Electrical Provision | 30 | 17 | 6 | 7
Roads, Bridges and Storm water | 10 | 2 | 6 | 2
Building & Construction | 9 | 9 | 0 | 0
| 55 | 31 | 15 | 9
TOTAL |  | 56.36% | 27.27% | 16.36%
72.73%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL FINANCE AND MANAGEMENT AND VIABILITY
Expenditure management | 4 | 1 | 2 | 1
Revenue Management | 2 | 2 | 0 | 0
Budget and Reporting | 3 | 2 | 0 | 1
Supply Chain Management | 1 | 1 | 0 | 0
Asset Management | 1 | 1 | 0 | 0
| 11 | 7 | 2 | 2
TOTAL |  | 63.64% | 18.18% | 18.18%
81.82%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 3 | 0 | 0 | 3
TOTAL | 0 | 0 | 0 | 3
100%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | 3 | 1 | 1 | 1
Fraud and Anti - Corruption | 1 | 1 | 0 | 0
Public Participation
Internal Auditing | 6 | 3 | 0 | 3
Information Technology | 9 | 4 | 3 | 2
Council Services | 2 | 1 | 0 | 0
Communication | 3 | 1 | 0 | 2
Public Participation | 6 | 3 | 0 | 0
| 30 | 14 | 4 | 8
TOTAL |  | 46.67% | 13.33% | 26.67%
73.33%
OVERALL PERFORMANCE
MTOD |  | 88
BSD |  | 73
LED |  | 100
MFMV |  | 82
GGPP |  | 73
416
83.2%

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## HIGH LEVEL SDBIP
4. HIGHER LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward/Dept | Funding Source | Budget 16/17 R'000 | Adjusted Budget | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | NO
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2016/2017 financial year by 31 May 2017 | IDP review for 2015/2016 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2017 | IDP Review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | IDP representative forum. Draft IDP completed and submitted to Council for adoption by 31 March 2016 | Target achieved | IDP representative forum was conducted. Draft IDP completed and submitted to Council for adoption by 31 March 2016 | None | None | Council resolutions, Draft IDP, Attendance register, Invitations for strategic plan, IDP Consultation attendance register. | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget 30 June 2017 | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Human Resources and Organizational Development | Invest in human capital | # of people trained through WSP by 30 June 2017 | 151 | 151 | Training | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | 10 | Target achieved | 76 | None | None | Proof of attendance | CORP | 3
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2017 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Organogram review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Consultation with organised labour | Target achieved | Inputs from departments regarding the new organogram received and comments were concolidated | None | None | Minutes and attendance register, Council resolutions, | CORP | 4
Human Resources and Organizational Development | Invest in human capital | To review the HR Strategy by 30 June 2017 | HR Strategy in place | HR Strategy reviewed | HR Strategy review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Consultation of the draft with trade unions. Consultation of the draft with LLF | Target achieved | Information sharing with stakeholders held during March 2017. Consultation with management done | None | None | Appointment letter, Draft HR Strategy, Approved HR Strategy, Council resolution | CORP | 5
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan by 30 June 2017 | 4 | 4 | Recruitment in terms of EE Plan | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Appointment letters | CORP | 6
Spatial and Town Planning | Advance Spatial Planning | % achievements of spatial programs indicators/targets per quarter by 30 June 2017 | 100% (16/16) | 100% (16/16) | Permission to Occupy | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 100% (16/16) | Target Achieved | 100% (27/27) 27 Permission to occupy applications attended) | None | None | Activity reports | DEVP | 7
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | % household with access to refuse removal by 30 June 2017 | 46637 | 13.3% (15481 | Waste Management | All wards | All wards | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | 13.3% (15481 | Target achieved | 13.3% (15481 | None | None | IDP document | MM and COMM | 8
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal by 30 June 2017 | 46637 | 15481 | Waste Management | Makhado Municipality | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | 2016-01-07 | 30/6/2017 | 15481 (non cumulaitve) | Target achieved | 15481 (non cumulaitve) | None | None | Proof of collection from the affected stakeholders. | MM and COMM | 9
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2017 | 3 | 3 | Development of Parks | Makhado Municipality | 20 & 21 | INCOME | 12000000 |  | 2016-01-07 | 30/6/2017 | N/A |  |  |  |  | Approval memo. RFP, appointment letter, Completion certificate | COMM | Taken out during budget adjustment
Electricity Provision | Accessible basic and infrastructure services | % of households with access to electricity by 30 June 2017 | 93% | 93.3% | Electrification of households | Makhado Municipality | Ward 23,25,03 | Income | 21824299 | 16000000 | 1/7/2016 | 30/6/2017 | 179 | Target achieved | 179 | None | None | Proof of connections to targeted households | MM and TECH | 10
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2017 | 1180 | 1100 | Electrification of households | Makhado Municipality | Ward 23,25,03 | INCOME | 21824299 | 16000000 | 2016-01-07 | 30/6/2017 | 179 | Target achieved |  | None | None | Proof of connections to targeted households | MM and TECH | 11
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads tarred by 30 June 2017 | 18.9km | 14.8 (Adjusted Budget constrainst) | Upgrading of roads | Makhado Municipality | Ward 23, 21, 13,04 | MIG | 78199143.67 | 136817564.45 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Project progress report, Certificate of completion | TECH | 12
Sports Facilities | Accessible basic and infrastructure services | To construct Tshivhuyuni sports and recreational facilities by 30 June 2017 | N/A | Construction of Tshivhuyuni sports and recreational facilities completed | Construction of Tshivhuyuni sports and recreational facilities | Makhado Municipality | Ward 12 | MIG | 600000 |  | 2016-01-07 | 30/6/2017 | Appoint consultant and complete designs |  |  |  |  | Terms of ref, Advert, Designs, Appointment letter for consultants | TECH
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Financial Statements | Sound Financial Management and viability | To obtain unqualified audit opinion by 31 December 2017 | Unqualified audit opinion | Unqualified audit opinion obtained | Auditing of financial statements | Makhado Municipality | Aministration | Income | Opeartional | Opeartional | 2016-01-07 | 31/12/2016 | N/A | N/A | N/A | N/A | N/A | AG report | B&T | 13
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2017 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | Aministration | Income | 163938800.12 | 199126314.45 | 2016-01-07 | 30/6/2017 | 70% | Target not Achieved | 36% | Re advertisemnet of the MIG projects delay the process | Appointment letter has been issued and construction on the process | Quarterly Financial Report | MM and All Directors | 14
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2017 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | Aministration | Income | 112264000 | 136817564.45 | 2016-01-07 | 30/6/2017 | 70% | Target not Achieved | 33.42% | Re advertisemnet of the MIG projects delay the process | Appointment letter has been issued and construction on the process | Quarterly Financial Report | MM | 14
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2017 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | Aministration | Income | 17000000 | 16000000 | 2016-01-07 | 30/6/2017 | 70% | Target Achieved | 84.02% | None | None | Quarterly Financial Report | MM | 16
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2017 | 100% | 100% | FMG | Makhado Municipality | Aministration | Income | 1600000 | 1600000 | 2016-01-07 | 30/6/2017 | 100% (80000) | N/A | N/A | N/A | N/A | Expenditure Report | B&T | 17
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2017 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | Aministration | Income | 342227123 | 719929000 | 2016-01-07 | 30/6/2017 | 70% | Target Achieved | 76% | None | None | Section 71 report (c1 schedule) | B&T | 18
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created by 30 June 2017 | 600 | 800 | LED job opportunities | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 19
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governace and Administrative Excellence | # of risk activities cordinated by 30 June 2017 | 13 | 13 | Risk Management activities | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Risk Management Register and Reports | MM | 20
Policies and By Laws | Good governace and Administrative Excellence | # of by laws to be reviewed by 30 June 2016 | 4 | 6 | Reviewing of Municipal By-laws | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A |  |  |  |  | Council resolutions, Copies of approved by laws. | CORP
Internal Auditing | Good governace and Administrative Excellence | No of internal audit indicators/ activities/ projects implemented by 30 June 2017 | 6 | 6 | Internal Audit projects | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 21
Information Technology | Good governace and Administrative Excellence | No of IT projects implemented by 30 June 2017 | 8 | 9 | IT Projects | Civic Center | Aministration | Income | R3000,000 | 2227200.04 | 2016-01-07 | 30/6/2017 | 3 | Target achieved | 3 | NA | NA | Advertisement for RFP | CORP | 22
Council Services | Good governace and Administrative Excellence | # of Council meetings convened by 30 June 2017 | 15 | 6 | Council meetings | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 2 | Target achieved | 3 | NA | NA | Minutes, Attendance register, notice of invitations. | CORP | 23
Communication | Good governace and Administrative Excellence | No of communication indicators/activities/projects implemented by 30 June 2017 | 5 | 3 | Communication projects | Civic Center | Ward 20 | Income | R20,000.00 | 80000 | 2016-01-07 | 30/6/2017 | N/A | NA | NA | NA | NA | TVs and payment certificates | CORP | 24
Public Participation | Good governace and Administrative Excellence | No of public participation indicators/activities/projects implemented by 30 June 2017 | 6 | 6 | Public Participation | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | NA | NA | NA | NA | Attendance register and Programme | CORP | 25

## LMTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17 R'000 | Adjusted Budget | Expenditure | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | No
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2016/2017 financial year by 31 May 2017 | IDP review for 2015/2016 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2017 | IDP Review | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | IDP representative forum. Draft IDP completed and submitted to Council for adoption by 31 March 2016 | Target achieved | IDP representative forum was conducted. Draft IDP completed and submitted to Council for adoption by 31 March 2016 | None | None | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget 30 June 2017 | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | Income | Operational | Operational | Operational | 1/4/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Performance Management | Good governance and administrative excellence | To benchmark with two municipalities for implementation of PMS system by 30 June 2017 | No electonic PMS system | Electonic system purchased | Benchmarking | Makhado Municipality | Income | Operational | 1600000 | 0 | 1/4/2016 | 30/6/2017 | Benchmark with two municipalities decide on the method of procurement and implement. Develop the process plan and consult with LLF | Target achieved | Benchmark with two municipalities decide on the method of procurement and implement. Develop the process plan and consult with LLF | None | None | Benchmarking report and documents from municipality and appointment letter. | MM | 3
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2017 | 8 | 8 | Quarterly performance reports | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 4 (Mid Year Budget and Performance Assessment Report 2016/2017 in terms of section 72 MFMA, Draft and Final Annual Report 2015/2016, Oversight Report 2014/2015) | Target achieved | 4 (Mid Year Budget and Performance Assessment Report 2016/2017 in terms of section 72 MFMA, Draft and Final Annual Report 2015/2016, Oversight Report 2014/2015) done | None | None | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 4
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 September 2016 (# of managers with signed performance agreements/# of managers appointed) | 100% (6/6) | 100% | Performance agreements | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/09/2016 | 100% (6/6) | Target achieved | 100% (6/6) All Section 57 Managers signed performance agreements | None | None | Signed Performance Agreements | MM | 5
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conducted by 30 June 2017 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 (Formal Assessment 2014/2015) 1 (Informal Assessment 2014/2015) | Target achieved | 1 (Formal Assessment 2014/2015) 1 (Informal Assessment 2014/2015) conducted | None | None | Scorecards, Attendance Register | MM | 6
Human Resources and Organizational Development | Invest in human capital | % posts filled in terms of the approved priority list by 30 June 2017 | 30 employees appointed | 100% prioritised post filled | Personnel Recruitment | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 10% (16/97 post filled) | Target not achieved | 10% (16/97 post filled) not filled | Process is time consuming due to number of applications received; not all posts can be filled due to affordability | Interviews scheduled for April and May 2017 | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP | 7
Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2017 | 6 events | 6 events | Employee Assistance Campaigns | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 event | Target achieved | 1 event done | None | None | Invitations, attendance registers and close-out report | CORP | 8
Human Resources and Organizational Development | Invest in human capital | To develop outstanding HR policies by 30 June 2017 | No transfer policy, Outdated Placement, Standby | (4) Transfer policy, Placement policy, Standby and Allowance policy | Review and Development of HR policies | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | Submit the policies (Transfer policy, Placement policy, Standby Allowance and Overtime policy) to LLF | Target achieved | The drafts of the Transfer policy, Placement policy, Standby Allowance and Overtime policy were submitted to the LLF Committee. | None | None | LLF and Council resolutions, Draft and Final policy documents | CORP | 9
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2017 | 135 | 135 | Training | Makhado Municipality | Income | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | 50 | Target achieved | 76 | None | N one | Proof of attendance | CORP | 10
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2017 | 16 | 16 | Training | Makhado Municipality | Income | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | N/A | Target achieved | 16 | None | None | Proof of attendance | CORP | 11
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2017 | Organogram 2015/2016 was approved | Approved Organogram by June 2017 | Organogram review | Makhado Municipality | Income | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | Invite inputs from departments regarding the new organogram | Target achieved | Inputs from departments regarding the new organogram received and comments were concolidated | None | None | Minutes and attendance register, Council resolutions, | CORP | 12
Human Resources and Organizational Development | Invest in human capital | To review the HR Strategy by 30 June 2017 | HR Strategy in place | HR Strategy reviewed | HR Strategy review | Makhado Municipality | Income | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | Information sharing with stakeholders. Consultation with management | Target achieved | Information sharing with stakeholders held during March 2017. Consultation with management done | None | None | Appointment letter, Draft HR Strategy, Approved HR Strategy, Council resolution | CORP | 13
Special Programs | Promote community and environmental welfare | # of qualified leaners awarded bursaries by 30 June 2017 | 10 | 15 | External Bursary Award | Makhado Municipality | Income | 450000 | 450000 | 136602.68 | 1/7/2016 | 30/06/2017 | N/A | NA | NA | None | None | Advert and Letters of bursary awards | CORP | 14
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2017 | 48 events done in 2015/2016 | 49 for 2016/2017 | Special Programs | Makhado Municipality | Income | 600000 | 600000 | 166710.69 | 1/7/2016 | 30/6/2017 | 12 | Target achieved | 16 | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 15
Spatial and Town Planning | Advance Spatial Planning | To purchase Plan Print Machine for Building Section by 31 March 2017 | Old Machine | Plan Print Machine for Building Section purchased | Plan Print Machine | Makhado Municipality | INCOME | 250000 | 250000 | -600000 | 1/7/2016 | 31/12/2016 | Appointment of service provider. Supply of machine | Target not achieved | Tender awaiting adjudication | Delay in appointment of the Service Provider.The project has been transferred to ICT section as it has been agreed that all IT related equipmnets will be purchased by Corporate Department. | The service provider will be appointed during the last quarter | Specifications, Advertisement, Proof R22 | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | To finalise the extension of Civic Centre by 31 December 2016 | New building | Extension of Civic Centre finalized | Extension of Civic Centre | Makhado Municipality | INCOME | 100000 | 390000 | 117430.45 | 1/7/2016 | 31/12/2016 | N/A | N/A | N/A | N/A | N/A | Project Report | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | To finalize the New Disaster centre -Erf 235 30 June 2017 | New building | New Disaster centre -Erf 235 finalized | New Disaster centre -Erf 235 | Makhado Municipality | INCOME | 500000 | 500000 | 273375 | 1/7/2016 | 30/06/2017 | Tilling,glazing,installation of doors | Target not achieved | Tilling complete,Glazing complete and external doors installed | Tilling partially done,glazing partially done and external doors installed. | Follow up with Technical Services for the completion of outstanding matters | Project Report | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | To purchase 18 x Aircons for new offices by 31 March 2017 | New building | 18 x Aircons for new offices purchased | 18 x Aircons for new offices | Makhado Municipality | INCOME | 200000 | 280900 | 269790 | 1/7/2016 | 31/03/2016 | Purchase aircons needed for 3rd quarter | Target achieved | All Aircons purchased and installed during second quarter | None | None | Proof of purchase and installation | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | To purchase 2 x Theodolities for Survey Technician by 31 March 2017 | New | 2 x Theodolities for Survey Technician purchased | 2 x Theodolities for Survey Technician | Makhado Municipality | INCOME | 100.000.00 | 50000 | Operational | 1/7/2016 | 31/03/2016 | Supply of theodolite | Project cancelled | Project cancelled | Funds used to fund other capital projects | Cancell purchasing of theodolites completely until new posts are filled. | Specifications, Advertisement, Delivery note. | DEVP | 20 | Project cancelled
Spatial and Town Planning | Advance Spatial Planning | Upgrading of Dzanani Traders Market 30 June 2017 | N/A | Upgrading of Dzanani Traders Market | Upgrading of Dzanani Traders Market | Makhado Municipality | INCOME | 200000 | 200000 | Operational | 1/7/2016 | 30/6/2017 | Appointment and commencement with designs | Target not achieved | Project cancelled. Designs to be done during 17/18 financial year | Project relocated to DTS | Project will be implemented by Technical Services Department | Designs, Specifications, Advertisement, Appointment letter | DEVP | 21 | Project cancelled
Spatial and Town Planning | Advance Spatial Planning | Development of informal business area Ext 12 by 30 June 2017 |  | Informal business area Ext 12 developed by 30 June 2017 | Development of informal business area | Makhado Municipality | INCOME | 3000000 |  |  | 1/7/2016 | 30/06/2017 | Appointment and commencement with construction |  |  |  |  | Designs, Specifications, Advertisement, Appointment letter | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival by 30 June 2017 | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of application received/(# of application attended to within 90 days). | Target Achieved | 100% (27/27) 27 Permission to occupy applications attended) | None | None | Site inspection report, Register of applications | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % housing queries attended to within 30 days after receival by 30 June 2017 | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of housing queries attended within 30 days/# of received) | Target achieved | 100% (23/23) 23 title deeds issued) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 23
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2017 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of building plans assessed/# of building plans received) | Target Achived | 100% (33/33) 33 Building Plans approved | Outstanding debt on clients account. Plan submitted not complying with the land use rights | Clients are advised to pay their account and apply for rezoning through T.P section | Building plans register | DEVP | 24
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2017 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | Target Achieved | 100% (15/15) 15 application processed) | N/A | N/A | Zoning certificates issued | DEVP | 25
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2017 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | Target achieved | 100% (3) 3 matters attended by MPT and (11) 11 applications approved by Authorised Official | N/A | N/A | EXCO resolutions | DEVP | 26
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days by 30 June 2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Target Achieved | 100% (5/5) 5 applications attended | N/A | N/A | Site inspection report, Register of applications | DEVP | 27
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2017 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achived | 100% (6) 6applications Issued | N/A | N/A | Copy of occupancy certificates issued | DEVP | 28
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achieved | 100% (19/19) 19 ervens attended) | N/A | N/A | Application Assessment Report, Register of applications | DEVP | 29
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Makhado Municipality | INCOME | 1000 000 .00 | 1000 000 .00 | #VALUE! | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Target Achieved | 100%(14/14)/14 sites demarcated) | N/A | N/A | Application Assessment Report, Register of applications | DEVP | 30
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | Target Achieved | 5 items considered by Exco | None | None | Application Assessment Report, Register of applications | DEVP | 31
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of queries processed/# of queries received) | Target Achieved | 1 Land Claims matter attended | N/A | N/A | Correspondence letters and emails. | DEVP | 32
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification by 30 June 2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target Achieved | 100% (25 issued) | N/A | N/A | Duplicate notices | DEVP | 33
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2017 | 240 | 240 | Routine Inspection | Makhado Municipality | INCOME | Operational | Operational |  | 1/7/2016 | 30/6/2017 | 60 |  |  |  |  | Inspection form, Register | DEVP | 29 | To be deleted
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours by 30 June 2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Target Achived | 100% | N/A | N/A | Inspection form, Register | DEVP | 34
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2017 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Makhado Municipality | INCOME | 200000 | 29100 | 28140 | 1/7/2016 | 30/6/2017 | Draft Street Names | Target not achieved | Tender lapsed | Awaiting re-advertisement of tender.The tender is supposed to be advertised for the second time as the first tender advert has lapsed. | Tender to be re-advertised.Follow up with Finance Department on when the tender will be advertised. | Expenditure Report | DEVP | 35 | Adjustment

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location/Ward | Funding Source | Budget 16/17 R'000 | Adjusted Budget | Expenditure | Start Date | End Date | 3rd quarter | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio of Evidence | DEPT | Indicator No
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2017 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | Update received information into the Disaster Management Plan. Draft Disaster Management Plan completed. | Target achieved | Update received information into the Disaster Management Plan done. Draft Disaster Management Plan completed. | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 36
Library Services | Promote community and environmental welfare | To remove the old library roof by 30 June 2017 | Roof damaged | Removal of the library roof completed | Remove library roof | Makhado Municipality | INCOME | 1200000 | 1200000 | Operational | 1/7/2016 | 30/6/2017 | Re-advertisement of tender | Target not achieved | Construction of roof not done | All received bids were not eligible for awarding | Tender re-advertisement | Project Progress report | TECH/COMM | 37
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal by 30 June 2017 | 46637 | 12787 | Waste Management | Ward 22, 23, 24, 25, 26. | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 12787 (Non Cumulative) | Target achieved | 12787 (Non Cumulative) | None | None | Monthly collection reports | COMM | 38
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal in extended rural area by 30 June 2017 | 6362 | 6362 | Waste Management |  | INCOME | Operational | Operational |  | 1/7/2016 | 30/6/2017 | 6362 (Non Cumulative) |  |  |  |  | Monthly collection reports | COMM | 34
Waste Management | Promote community and environmental welfare | To rehabilitate the existing landfill site by 31 March 2017 | New | Existing Landfill site rehabilitated completed | Rehabilitation of the existing Landfill site | Makhado Municipality | INCOME | 3000000 | 2300000 |  | 1/7/2016 | 31/03/2017 | Caping of waste with soil Appointment of a service provider. |  |  |  |  | Completion certificate | COMM | 35 | Taken out during budget adjustment
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Development of Landfillsite | Makhado Municipality | MIG | 5 000 000.00 - |  |  |  |  | Development of designs and drawings (Geotechnical report) |  |  |  |  | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM | 33 | Rollover project
Parks and Recreation | Promote community and environmental welfare | To develop E59 and E60 Park (Makhado Town) by 30 June 2017 | Development | Development of E59 and E60 Park (Makhado Town) completed | Development of E59 and E60 Park (Makhado Town) | Makhado Municipality | INCOME | 400000 | Operational | Operational | 1/7/2016 | 30/6/2017 | Project removed during budget adjustment | Target not achieved | Taken out during budget adjustment | Taken out during budget adjustment | Taken out during budget adjustment | Approval memo, appointment letter, Completion certificate | COMM | 39 | Taken out during budget adjustment
Parks and Recreation | Promote community and environmental welfare | To develop Dzanani Park next to Shopping Mall by 30 June 2017 | N/A | Development of Dzanani Park next to Shopping Mall completed | Development of Dzanani Park next to Shopping Mall | Makhado Municipality | INCOME | 200000 |  |  |  |  | Development of the park in line with the proposal |  |  |  |  | Approval memo. RFP, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | Refurnishment and fencing Eltivillas Swimming Pool by 30 June 2017 | N/A | Refurnish and fencing Eltivillas Swimming Pool completed | Refurnish and fencing Eltivillas Swimming Pool | Makhado Municipality | INCOME | 150000 |  |  |  |  | Development of the park in line with the proposal |  |  |  |  | Approval memo. RFP, appointment letter, Completion certificate | COMM
Parks and Recreation | Promote community and environmental welfare | To refurbish Potgieter Park by 30 June 2017 | Refurbishment | Refurbishment of Potgieter Park completed | Refurbishment of Potgieter Park | Makhado Municipality | INCOME | 300000 |  |  | 1/7/2016 | 30/6/2017 | Project removed during budget adjustment |  |  |  |  | Approval memo, appointment letter, Completion certificate | COMM | 37 | Taken out during budget adjustment
Parks and Recreation | Promote community and environmental welfare | To construct Tshikota cemetery ablution facilities by 31 March 2017 | No ablution facilities | Construction of Tshikota cemetery ablution facilities completed | Construction of Tshikota cemetery ablution facilities | Makhado Municipality | INCOME | 200000 | 200000 | 169900 | 1/7/2016 | 30/6/2017 | Construction of ablution facilities completed | Target achieved | Construction of ablution facilities completed | None | None | Approval memo, appointment letter, Completion certificate | COMM | 40
Protection Services | Promote community and environmental welfare | To purchase special Garage Roller Door for VTS and 2x 30m long chains |  | Special Garage Roller Door for VTS and 2x 30m long chains | Special Garage Roller Door for VTS and 2x 30m long chains | Makhado Municipality | INCOME | 800000 |  |  | 1/7/2016 | 30/6/2017 | N/A |  |  |  |  | Specifications, Advertisement, Appointment letter, delivery note | TECH
Parks and Recreation | Promote community and environmental welfare | To pave open Erf 1 -N1 by 30 June 2017 | New | Paving of open Erf 1 -N1 completed | Paving open Erf 1 -N1 | Makhado Municipality | INCOME | 1000000 |  |  | 1/7/2016 | 30/6/2017 | Project removed during budget adjustment |  |  |  |  | Approval memo, appointment letter, Completion certificate | COMM | 39 | Adjusted
Protection Services | Promote community and environmental welfare | Establishment of Watervaal Registering Authority by 30 June 2017 | New | Establishment of Watervaal Registering Authority completed | Establishment of Watervaal Registering Authority | Waterval Traffic Station | INCOME | 200000 | 200000 | Operational | 1/7/2016 | 31/12/2017 | Project removed during budget adjustment | Project removed during budget adjustment | Project removed during budget adjustment | Project removed during budget adjustment | Project removed during budget adjustment | Purchase order | COMM | 41 | Project removed during budget adjustment
Electricity Provision | Accessible basic and infrastructure services | To replace air conditioners by 30 June 2017 | New | Air Conditioners replaced | Air Conditioners | Makhado | INCOME | 150000 | 150000 | 87082 | 1/7/2016 | 30/09/2017 | Appointment of service provider | Target achieved | Appointment of service provider was done | None | None | Advertisement , Adjudication minutes, appointment letter and Job Cards | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To purchase CT VT Units 11kv and 22kv by 30 June 2017 | New | CT VT Units 11kv and 22kv purchased | CT VT Units 11kv and 22kv | Makhado | INCOME | 400000 | 400000 | Operational | 1/7/2016 | 30/06/2017 | Specifications considered by the BSC and advertisement of tender. | Target not achieved | Appointment of service provider not done. Tender evaluated | SCM delays | Award and complete in 4th quarter | Advertisement , Adjudication minutes, appointment letter and Job Cards | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | To procure Mini Substation by 31 March 2017 | New | Mini Subs replaced | Mini Subs | Makhado | INCOME | 700000 | 257000 | 257000 | 1/7/2016 | 31/03/2017 | Delivery of materials | Target achieved | Delivery of materials done | None | None | Specification, orders, GRV | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | To procure MV Cable 70 mm 11kv by 31 March 2017 | New | MV Cable 70mm 11kV procured | MV Cable 70mm 11kV | Makhado | INCOME | 500000 | 0 |  | 1/7/2016 | 31/03/2017 | Project removed during budget adjustment | Target not achieved | Taken out during budget adjustment | Taken out during budget adjustment | Taken out during budget adjustment | Specification, orders, GRV | TECH | 45 | Taken out during budget adjustment
Electricity Provision | Accessible basic and infrastructure services | To purchase strategic spares by 31 March 2017 | New | Strategic spares | Strategic spares | Makhado | INCOME | 200000 | 0 | 0 | 1/7/2016 | 30/06/2017 | Project removed during budget adjustment | Target not achieved | Taken out during budget adjustment | Taken out during budget adjustment | Taken out during budget adjustment | Specification, orders, GRV | TECH | 46 | Taken out during budget adjustment
Electricity Provision | Accessible basic and infrastructure services | To deliver material to replace Ring Main Units 11 kV ( RMU) by 30 June 2017 | New | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Makhado | INCOME | 5000000 | 1443000 | 0 | 1/7/2016 | 31/03/2017 | Evaluation and Adjudication of tenders. Appointment of a service provider. | Target achieved | Appointment of a service provider done. | None | None | Specification, orders, GRV | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To upgrade Shefeera Line by 30 June 2017 | Upgrade | Shefeera Line Upgraded | Upgrade Shefeera Line | Makhado Municipality | INCOME | 300000 | 300000 | 0 | 1/7/2016 | 30/06/2017 | Excavating pole holes, dress and plant poles | Target not achieved | Excavating pole holes, dress and plant poles not done. Service provider appointed | SCM delays | Complete project in the 4th quarter | List of Labourer, Completion certificate | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute Beaufort West line by 30 June 2017 | Upgrade | Reroute of Beaufort West line upgraded | Upgrade and reroute Beaufort West line | Beaufort West line | INCOME | 1000000 | 1000000 | 0 | 1/7/2016 | 30/06/2017 | Appointment of service provider and site handover | Target achieved | Appointment of service provider and site handover done | None | None | Desings , Advertisement, Adjudication minutes and completion certificate | TECH | 49
Electricity Provision | Accessible basic and infrastructure services | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs 6km by 30 June 2017 | Upgrade | Reroute transmission line 66kV bulk supply to Levubu and Beaufort subs upgraded | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs | Makhado Municipality | INCOME | 8000000 |  |  |  |  | Appointment of the cotractor, Site handover |  |  |  |  | Advertisement, adjudication minutes and appointment letters and completion certificate | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To upgrade urban substation by 30 June 2017 | Upgrade | Materials delivered | Upgrade urban substation | Makhado Municipality | INCOME | 5000000 | 5000000 | 356797.36 | 1/7/2016 | 30/06/2017 | Evaluation, adjudication and award tender | Target achieved | Await delivery of material | None | None | Progress report handover and Completion certificate | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To upgrade bulk supply Tshituni (2.5MVA) by 30 June 2017 | Upgrade | Site handover | Upgrading bulk supply Tshituni (2.5MVA) | Makhado Municipality | INCOME | 3000000 | 3000000 | 0 | 1/7/2016 | 30/06/2017 | Develop specification and advertise tender | Target achieved | Approval of budget quote done. Emergency project | None | None | Application letter, and feasibility quate | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To upgrade Mountain line by 30 June 2017 | Upgrade | Mountain line upgraded | Upgrading Mountain line | Makhado Municipality | INCOME | 300000 | 300000 | Operational | 1/7/2016 | 30/06/2017 | Project removed during budget adjustment | N/A | Amended | N/A | N/A | List of Labourer, Completion certificate | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To transform oil purification by |  | transform oil purification | transforming oil purification | Makhado Municipality | INCOME | 350000 |  |  | 1/7/2016 | 30/06/2017
Electricity Provision | Accessible basic and infrastructure services | To replace outdoor Curcuit breaker by 30 June 2017 | New | Evaluate, adjudicate and award tender. | Circuit breaker | Makhado Municipality | INCOME | 1000000 | 1000000 | 0 | 1/7/2016 | 30/06/2017 | N/A | Target not achieved | Evaluation, adjudication and appointment of a service provider not done. | SCM delays | Award and complete in 4th quarter | Advertisement,Adjudication minutes appointment letter, Completion certificate | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2017 | New | Replacement of channel cover completed | Substation channel cover replacements | Makhado Municipality | INCOME | 250000 | 250000 | 0 | 1/7/2016 | 30/06/2017 | Issuing of purchase order | Target not achieved | Issuing of purchase order not done | All received bids were not eligible for awarding | Tender re-advertisement | Advert, evaluation minutes, Purchase order | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | Purification of transformer oil by 30 June 2017 | N/A | Transformer oil purified | Transformer oil | Makhado Municipality | INCOME | 350000 | 350000 | 0 | 1/7/2016 | 30/06/2017 | Readvertisement and Evaluation | Target achieved | Readvertisement and Evaluation done. Service provider appointed | None | None | Specs, Ads, evaluatiion & adjudication minutes. Appointment letter. Order. | TECH | 55
Electricity Provision | Accessible basic and infrastructure services | To renovate Substation control room by 30 June 2017 | N/A | Substation control room renovated | Substation control room renovations | Makhado Municipality | INCOME | 100000 | 100000 | 64361.2 | 1/7/2016 | 30/06/2017 | Issuing of purchase order | Target achieved | Issuing of purchase order done | None | None | Advert, evaluation minutes, Purchase order | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To Service OCB's substation by 30 June 2017 | N/A | Service OCB's | Service OCB's | Makhado Municipality | INCOME | 200000 | 200000 | 0 | 1/7/2016 | 30/06/2017 | Evaluationa nd Adjudication of tenders. Appointment of a service provider. | Target achieved | Appointment of a service provider done. | None | None | Advert, evaluation minutes, Purchase order | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | To refurbish Transformer in (Levubu) by 30 June 2017 | N/A | Transformer refurbished (Levubu) | Transformer refurbishment (Levubu) | Makhado Municipality | INCOME | 600000 | 800000 | 0 | 1/7/2016 | 30/06/2017 | Appointment of service provider | Target achieved | Appointment of service provider done | None | None | Advert, adjudication minutes, Completion certificate | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | Post connection Own licensed areas by 30 June 2017 | N/A | Post connection Own licensed areas | Post connection Own licensed areas | Makhado Municipality | INCOME | 2000000 | 3000000 | 2203277.62 | 1/7/2016 | 30/06/2017 | Stringing MV & LV | Target achieved | Stringing MV & LV done. Project completed (Makushu) | None | None | Appointment letter, project progress report, completion certificate | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village connection completed | Wisagalaza 2 & Chitasi village | Wisagalaza village | INEP/ | 7771500 |  |  | 1/7/2016 | 30/06/2017 | Service connections |  |  |  |  | Appointment letter, project progress report, completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To design electricity network at Tshikhwani/ Rathidili by 30 September 2016 | Design | Tshikhwani/ Rathidili designs completed | Tshikhwani/ Rathidili | Tshikhwani/ Rathidili | INEP | 1663485.12 | 259919.55 | 827318.16 | 1/7/2016 | 30/09/2016 | N/A | N/A | N/A | N/A | N/A | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To design electricity network at Maname Paradise by 31 March 2017 | Design | Maname Paradise designs completed | Maname Paradise | Maname Paradise | INEP | 831742.56 | 129959.78 | 0 | 1/7/2016 | 31/03/2017 | Designs approval | Target achieved | Designs approval done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ratombo by 30 September 2016 | New Connection | Ratombo (200) connection completed | Ratombo | Ratombo | INEP /income | 1708852.9 | 472581 | 1553244.3 | 1/7/2016 | 30/09/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 62
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Tshiozwi/ Gogobole phase 2 by 31 March 2017 | New Connection | Tshiozwi/ Gogobole phase 2 (199) completed | Tshiozwi/ Gogobole phase 2 | Tshiozwi/ Gogobole phase 2 | INEP | 1512259.2 | 2986290.5 | 1252126.83 | 1/7/2016 | 30/06/2017 | Energising and completion certificate | Target achieved | Energising and completion certificate done | None | None | Progress report and Completion certificate | TECH | 63
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 by 31 March 2017 | New Connection | Magau/ Makhitha/Tshikodobo/ Zamekomste (123) phase 2 completed | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | INEP | 146500.11 | 1846500.11 | 1037444.43 | 1/7/2016 | 30/06/2017 | Energising and completion certificate | Target achieved | Energising and completion certificate done | None | None | Progress report and Completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mamburu phase 2 by 31 March 2017 | New Connection | Mamburu phase 2 (186) connection completed | Mammburu | Mammburu | INEP | 354435.75 | 0 | 1506269.84 | 1/7/2016 | 30/06/2017 | Energising and completion | Target achieved | Energising and completion certificate done | None | None | Progress report and Completion certificate | TECH | 65
Electricity Provision | Accessible basic and infrastructure services | To design electricity network at Madabani by 31 March 2017 | New Connection | Madabani designs completed | Madabani | Madabani | INEP | 129959.78 | 0 | 0 | 1/7/2016 | 30/06/2017 | Designs approval | Target achieved | Designs approval done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 66
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Sukani Phase 2 by 30 September 2016 | New Connection | Sukani (80) connection completed | Sukani | Sukani | INEP | 1814814.72 | 347359.46 | 1105231.48 | 1/7/2016 | 30/09/2016 | N/A | N/A | N/A | N/A | N/A | project progress reportcompletion certificate | TECH | 67
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Freedom Lusaka Phase 2 by 30 September 2016 | New Connection | Freedom Lusaka (51) Phase 2 connection completed | Freedom Lusaka Phase 2 | Freedom Lusaka Phase 2 | INEP | 125241.12 | 125241.12 | 1214587.21 | 1/7/2016 | 30/09/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 68
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Manavhela/ Madodonga phase 2 by 31 March 2017 | New Connection | Manavhela/ Madodonga phase 2 (207) completed | Manavhela/ Madodonga phase 2 | Manavhela/ Madodonga phase 2 | INEP | 285927.84 | 1649113.59 | 3710161.45 | 1/7/2016 | 31/06/2017 | Energise and completing | Target achieved | Energise and completing done | None | None | Progress report and Completion certificate | TECH | 69
Electricity Provision | Accessible basic and infrastructure services | To design electricity network at Mavhunga /Muromani by 31 December 2017 | Design | Mavhunga/ Muromani design completed | Mavhunga Muromani | Mavhunga Muromani | INEP | 141784.9 | 141784.9 | 369356.43 | 1/7/2016 | 31/12/2016 | N/A | N/A | N/A | N/A | N/A | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 70
Electricity Provision | Accessible basic and infrastructure services | To pay the engineer on the electrification of Vyeboom by 30 September 2017 (R867 541.56) | Payment | Payment Done | Payment | Vyeboom | INEP | 867542 | 867542 | 867541.56 | 1/7/2016 | 30/09/2016 | N/A | N/A | N/A | N/A | N/A | Payment certificate | TECH | 71
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To revitalize the OK/ Shoprite Traders market project by 30 June 2017 | N/A | Contract for revitalization of OK/ Shoprite Traders market awarded | OK/ Shoprite Traders market revitalization project | Makhado Municipality | MIG | 500000 | 500000 | 0 | 1/7/2016 | 31/003/2017 | Re-advertisement of tender | Target achieved | Re advertisement and evaluation done | None | None | Specification, Advert and Designs | TECH | 72
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To construct road Sereni Themba to Mashamba post office ( phase 3) by 30 June 2017 (4.2km) | Phase 1 and 2 Constructed | Surfacing completed for 4.2 km | Sereni Themba to Mashamba post office ( phase 3) | Makhado Municipality | MIG | 11800000 | 11800000 | 3359464.1 | 1/7/2016 | 30/06/2017 | Commence with construction and complete layer works | Target not achieved | Layer works not completed | Withdrawal from project by SP | Alternative SP has been appointed | Site establishment report, project progress report, | TECH | 73
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Robert khoza street ( Chavani and Bungeni road) by 31 December 2017 (3.5km) | N/A | Robert khoza street ( Chavani and Bungeni road) for 3.5km completed | To construct Robert khoza street ( Chavani and Bungeni road) | Makhado Municipality | MIG | 9246000 | 13254837.11 | 13421125.73 | 1/7/2016 | 31/12/2017 | N/A | N/A | N/A | N/A | N/A | Project progress report, handover report | TECH | 74
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshikwarani to Zamkomste Road - 1.5km by 30 June 2017 | N/A | Complete roadbed, subbase and base layers (1.5km) | Tshikwarani to Zamkomste Road - 1.5km | Makhado Municipality | MIG | 11800000 | 9291162.89 | 1309845.86 | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed | Suspension of site handover by community and rain | Project commenced | Site establishment report, project progress report, handover report | TECH | 75
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshirolwe,Matsa to Manyii road Phase 1- 1.2km by 30 June 2017 | N/A | Complete roadbed, subbase and base layers (1.2km) | Tshirolwe,Matsa to Manyii road P1- 1.2km | Makhado Municipality | MIG | 11800000 | 11300000 | 1696 | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed | Suspension of site handover by community and rain | Project commenced | Site establishment report, project progress report, handover report | TECH | 76
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Mudimeli bridge by 30 June 2017 | New | Mudimeli bridge completed | Mudimeli bridge | Makhado Municipality | MIG | 15000000 |  |  | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed |  |  | Specifications, advertisement, appointment letter, project progress report | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Khunda Roads stormwater 30 June 2017 | New | Khunda Roads stormwater completed | Khunda Roads stormwater | Makhado Municipality | MIG | 10000000 |  |  | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed |  |  | Advertisement copy, appointment letter, design report. | TECH | 80
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To contruct Waterval ablution facilities by 30 June 2017 | New | Waterval ablution facilities completed | Waterval ablution facilities | Makhado Municipality | MIG | 10000000 |  |  | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed |  |  | Advertisement copy, appointment letter, design report. | TECH | 81
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshedza to Vuvha road- 1km by 30 June 2017 | New | Tshedza to Vuvha road- 1km completed | Tshedza to Vuvha road- 1km | Makhado Municipality | MIG | 11800000 | 11800000 | 3 317 042. 17 | 1/7/2016 | 30/06/2017 | Site handover and establishment. Commence with box cutting. | Target not achieved | Layer works not completed | Rain delays | Programme reviewed | Site establishment report, project progress report, handover report | TECH | 77
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To contsruct Gombiti,Tshivhuyuni to Mamphagi road Phase 1- 1.4 km by 30 June 2017 | New | Gombiti,Tshivhuyuni to Mamphagi road Phase 1- 1. 4km completed | Gombiti,Tshivhuyuni to Mamphagi P1- 1.4km | Makhado Municipality | MIG | 11800000 | 9428286.31 | 2028459.37 | 1/7/2016 | 30/06/2017 | Site establishment | Target not achieved | Earthworks not completed | Suspension of site handover by community and rain | Project commenced | Site establishment report, project progress report, handover report | TECH | 78
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Xitacini to Jiweni Phase 1 - 2km by 30 June 2017 | New | Complete base layer and surfacing of 2km road | Xitacini to Jiweni P1 - 2km | Makhado Municipality | MIG | 11800000 | 11300000 | 1061654.29 | 1/7/2016 | 30/06/2017 | Site handover, site establishment, roadbed and subbase completed. | Target not achieved | Layer works not completed | Burning of construction equipment and rain | Programme reviewed | Site establishment report, project progress report, handover report | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To rehabilitate internal streets by 30 June 2017 | Gravel | Rehabilitation of Internal Streets completed | Rehabilitation of Internal Streets | Makhado Municipality | INCOME | 3000000 | 3000000 | 0 | 1/7/2016 | 30/06/2017 | Re-advertisement and Evaluation | Target achieved | Readvertisement and Evaluation done. | None | None | Spec, Advert and completion certificate | TECH | 80
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Fencing of graveyards by 31 March 2017 | Development | Fencing of graveyards completed | Fencing of graveyards | Hanani, Hlanganani township, Tsianda, Ndouvhada,Vleifontein. | MIG | 2500000 | 2000000 | 2554325.74 | 1/7/2016 | 31/03/2017 | N/A | N/A | N/A | N/A | N/A | Spec, Advert and completion certificate | TECH | 81
Building and Construction | Accessible basic and infrastructure services | To develop refuse transfer station for Waterval Region by 30 June 2017 | New | Evaluate, adjudicate and award contract. Commence with design in 2017/18 | Development of refuse transfer station for Waterval Region | Makhado Municipality | MIG | 500000 | 320000 | 0 | 1/7/2016 | 30/06/2017 | Re-advertisement of tender | Target achieved | Re advertisement and evaluation done | None | None | Specification, Advert and Designs | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To construct waste Disposal Cell (New landfill ) 30 June 2017 | New | Evaluate, adjudicate and award contract. Commence with design in 2017/18 | Construction of waste Disposal Cell (New landfill ) | Makhado Municipality | MIG | 500000 | 380000 | 0 | 1/7/2016 | 30/06/2017 | Re-advertisement of tender | Target achieved | Re advertisement and evaluation done | None | None | Specification, Advert and Designs | TECH | 83
Building and Construction | Accessible basic and infrastructure services | To upgrade Dzanani Transfer Station - Elec+ Guard room by 30 June 2017 | Upgrade | Evaluate, adjudicate and award contract. Commence with design in 2017/18 | Upgrade Dzanani Transfer Station - Elec+ Guard room | Makhado Municipality | MIG | 800000 | 800000 | 0 | 1/7/2016 | 30/06/2017 | Re-advertisement of tender | Target achieved | Re advertisement and evaluation done | None | None | Specification, Advert and Designs | TECH | 84
Building and Construction | Accessible basic and infrastructure services | Development of Kutama/Sinthumule Stadium by 30 June 2017 | Development | Evaluate, adjudicate and award contract. Commence with design in 2017/18 | Development of Kutama/Sinthumule Stadium | Makhado Municipality | MIG | 500000 | 500000 | 0 | 1/7/2016 | 30/06/2017 | Re-advertisement of tender | Target achieved | Re advertisement and evaluation done | None | None | Specification, Advert and Designs | TECH | 85
Building and Maintanance | Accessible basic and infrastructure services | Refurbishment of Caravan Park buildings 30 June 2017 | Refurbishment | Refurbishment of Caravan Park buildings completed | Refurbishment of Caravan Park buildings | Makhado | INCOME | 300000 | 455000 | 304790 | 1/7/2016 | 30/06/2017 | Repair of roof,ceiling, plumbing | Target achieved | Repair of roof,ceiling, plumbing done | None | None | Advertisement , Appointment letter and completion certificate | TECH | 86
Building and Maintanance | Accessible basic and infrastructure services | Ablution of Tree Park Facility by 30 June 2017 | New | Ablution of Tree Park Facility completed | Ablution of Tree Park Facility | Makhado | INCOME | 150000 | 250000 | 145500 | 1/7/2016 | 30/06/2017 | Appoint contractor and commence with the project | Target achieved | Appoint contractor and commence with the project and toilet complete | None | None | Spec, Advert and completion certificate | TECH | 87
Building and Maintanance | Accessible basic and infrastructure services | To construct Standby quarter perimeter wall by 31 March 2017 | Development | Standby quarter perimeter wall completed | Standby quarter perimeter wall | Makhado | INCOME | 225000 | 325000 | 393062.65 | 1/7/2016 | 31/03/2017 | Project removed during budget adjustment | Target achieved | Project removed during budget adjustment | None | None | Specification, advertisement, project progress report | TECH | 88
Building and Construction | Accessible basic and infrastructure services | To construct Carport for Employees at Dzanani Traffic by 31 March 2017 | New | Construction for Carport completed | Construction for Carport | Makhado Municipality | INCOME | 50000 | 47050 | 0 | 1/7/2016 | 31/03/2017 | Appoint contractor and commence with the project and project completed | Target achieved | Appoint contractor and commence with the project and project completed | None | None | Spec, Advert and completion certificate | TECH | 89
Building and Construction | Accessible basic and infrastructure services | To remove underground fuel tanks and rehabilitate the soil 30 June 2017 | New | Remove underground fuel tanks and rehabilitate the soil completed | Remove underground fuel tanks and rehabilitate the soil | Makhado Municipality | INCOME | 900000 | 895 000.00 | 760000 | 1/7/2016 | 30/06/2017 | Appoint contractors and complete with environmental assessment | Target achieved | Appoint contractors and complete with environmental assessment done | None | None | Spec, Advert and completion certificate | TECH | 90
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Rehabilittion of Waterval streets and stormwater by 30 June 2017 | N/A | Rehabilittion of Waterval streets and stormwater compeleted | Waterval streets and stormwater rehabilittion | Makhado Municipality | MIG | 600000 |  |  |  |  | Appoint consultant and complete designs |  |  |  |  | Terms of ref, Advert | TECH | 78
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Piesanghoek to Khunda road and stormwater Phase II by 30 June 2017 | N/A | Piesanghoek to Khunda road and stormwater Phase II | Piesanghoek to Khunda road and stormwater Phase II | Makhado Municipality | MIG | 4000000 |  |  |  |  | Completion of base, priming at 100% |  |  |  |  | Site establishment report, project progress report, handover report | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct a new bridge at Mudimeli by 2018 | N/A | Mudimeli bridge completed by 2018 | Mudimeli bridge | Makhado Municipality | MIG | 6054000 |  |  |  |  | Construction of concrete walls, decking of bridge and wing walls |  |  |  |  | Specifications, advertisement, appointment letter, project progress report | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To construct Industrial Paving of gate VTS - entrance by 30 June 2017 |  | Industrial Paving of gate VTS - entrance comp;le | Industrial Paving of gate VTS - entrance | Makhado Municipality | MIG | 1000000 |  |  |  |  | Setting out and construction of fence Finalisation of the fence |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 81
Building and Construction | Accessible basic and infrastructure services | Revitalisation of Tshakhuma Fruit Market (Phase 2) by 30 June 2017 |  | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Makhado Municipality | INCOME | 1100000 |  |  |  |  | Setting out and construction of fence Finalisation of the fence |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To plan Siloam Taxi Rank by 30 June 2017 | New | Siloam Taxi Rank (Planning) | Siloam Taxi Rank(Planning) | Siloam | MIG | 600000 |  |  |  |  | Appoint consultant and complete designs |  |  |  |  | Terms of reference, Advertisement, designs | TECH | 90
Building and Construction | Accessible basic and infrastructure services | Rehabilitation of Street (900m) -Dzanani township 30 June 2017 |  | Street Rehabilitation (900m) -Dzanani township | Street Rehabilitation (900m) -Dzanani township | Dzanani township | MIG | 5750000 |  |  |  |  | Setting out and construction of fence Finalisation of the fence |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 93
Building and Construction | Accessible basic and infrastructure services | Development of New Waterval Stadium by 30 June 2017 | New | New Waterval stadium developed | Development of New Waterval Stadium | Waterval | MIG | 11100000 |  |  |  |  | Paying of grass, electrification and water reticulation |  |  |  |  | Progress report and completion certificate | TECH | 94
Building and Construction | Accessible basic and infrastructure services | To construct Civic Centre external wall Painting 30 June 2017 |  | Civic Centre external wall Painting | Civic Centre external wall Painting | Makhado Municipality | INCOME | 300000 |  |  |  |  | Completion of project |  |  |  |  | Spec, Advert and completion certificate | TECH | 97

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Location | Funding Source | Budget 16/17 R'000 | Adjusted Budget | Expenditure | Start Date | End date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2017 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | INCOME | 163938800.12 | 199126314.45 |  | 1/7/2016 | 30/6/2017 | 70% | Target not Achieved | 36% | Re advertisemnet of the MIG projects delay the process | Appointment letter has been issued and construction on the process | Quarterly Financial Report | MM and All Directors | 91
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2017 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | INCOME | 112264000 | 136817564.45 | 55061637 | 1/7/2016 | 30/6/2017 | 70% | Target not Achieved | 33.42% | Re advertisemnet of the MIG projects delay the process | Appointment letter has been issued and construction on the process | Quarterly Financial Report | MM | 92
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2017 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | INCOME | 17000000 | 16000000 | 13789727 | 1/7/2016 | 30/6/2017 | 70% | Target Achieved | 84.02% | None | None | Quarterly Financial Report | MM | 93
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2017 | 100% | 100% | FMG | Makhado Municipality | INCOME | 1600000 | 1600000 | 1207591 | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Expenditure Report | B&T | 94
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2017 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | INCOME | 342227123 | 719929000 |  | 1/7/2016 | 30/6/2017 | 70% | Target Achieved | 76% | None | None | Section 71 report (c1 schedule) | B&T | 95
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2017 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Makhado Municipality | INCOME | Operational | Operational | Operational | 2017-01-01 | 30/6/2017 | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | Target Achieved | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) submitted to council with proposed inputs | None | None | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 96
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2017 | Final budget was submitted to Council | Final budget submitted to Council | Final budget | Makhado Municipality | INCOME | Operational | Operational | Operational | 2017-01-01 | 30/6/2017 | Send request to departments for proposed budget. Draft budget tabled to council by 31 March 2017 | Target Achieved | Send request to departments for proposed budget done . Draft budget tabled to council by 31 March 2017 | None | None | Final budget and Council Resolution | B&T | 97
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Makhado Municipality | INCOME | Operational | Operational | Operational | 2016-01-07 | 30/8/2016 | N/A | N/A | N/A | N/A | N/A | Copy of Financial statements | B&T | 98
Budget and Reporting | Sound financial management and viability | # of section 71 reports submitted to Treasury within 10 days after the end of the month by 30 June 2017 | 12 | 12 | Section 71 report submission | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 3 | Target Achieved | 3 | None | None | Copy of acknowledgement of receipt by Treasuries | B&T | 99
Supply Chain Management | Sound financial management and viability | To review the Supply Chain Management policy by 30 June 2017 | 2014/ 15 Supply Chain Management policy was reviewed and amended | Supply Chain Management policy reviewed | Supply Chain Management policy | Makhado Municipality | INCOME | Operational | Operational | Operational | 2016-01-07 | 30/6/2017 | Send the policy to departments for inputs | Target Achieved | Request for were made on the 12/01/2017 and inputs were received from departments | None | None | Council Resolution | B&T | 100
Asset Management | Sound financial management and viability | % of new acquisitions updated into the Asset Register by 30 June 2017 | 100% | 100% | Updating of Asset Register | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% | Target Achieved | 100% | None | None | Schedules of Asset Register movement | B&T | 101

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Adjusted Budget | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
5.4. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created 30 June 2017 | 600 | 800 | LED job opportunities | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 102
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2017 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Makhado Municipality | Income | 1200000 | 1 2 500 000.00 | 1200000 | 1/7/2016 | 30/9/2016 | N/A | N/A | N/A | N/A | N/A | Annual Show Report and Audited Financial Statements | DEVP | 103
Local Economic Development | Invest in local economy | # of LED projects supported 30 June 2017 | 9 | 6 | LED Strategy | Makhado Municipality | Income | Operational | Operational | Operational | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | N/A | N/A | LED strategy implementation report | MM and DEVP | 104

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17R'000 | Adjusted Budget | Expenditure | Start Date | End date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | Indicator No
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate Stategic and operational Risk Assessment and review and approval of risk and fraud management policies by 30 June 2017 | Strategic and Operational Risk Assessment Report developed / coordinated and 6 policies, plans and strategies reviewed and approved | 7 risk activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Attendance register, Minutes and Programme | MM | 105
Risk Management | Good governace and Administrative Excellence | Coordinate quarterly Strategic and Operational monitoring risk report 30 June 2017 | 4 quarterly Strategic and Operational monitoring risk report Coordinated | 4 activities coordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | Develop Quarterly Strategic Monitoring Risk Report, | Target achieved | Quarterly strategic Monitoring risk report developed | None | None | Strategic Monitoring Risk Report | MM | 106
Risk Management | Good governace and Administrative Excellence | Coordinate Risk Management Committee meetings 30 June 2017 | 4 Risk Management Committee meetings held | 4 activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | Cordinate1 Risk Management Committee meeting | Target not Achieved | Risk Committee Meeting not held | Unavailability of the Chairperson | None | Minutes and Attendance register | MM | 107
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2017 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of cases attended/# of cases reported) | Target achieved | No case received and attended to | None | None | Case Register | MM | 108
Policies and By Laws | Good governace and Administrative Excellence | # of policies reviewed by 30 June 2017 | 7 policies reviewed | 6 policies reviewed | Reviewing of Municipal policies | Makhado Municipality | INCOME | Operational |  |  | 1/7/2016 | 30/6/2017 | 6 draft policies |  |  |  |  | Council resolution for the approved policies | CORP | 108 | Adjusted during budget adjustment
Policies and By Laws | Good governace and Administrative Excellence | # of by laws reviewed by 30 June 2017 | 4 by laws reviewed | 1 by law reviewed | Review of the following by laws: Rules of Order | Makhado Municipality | Income | Operational |  |  | 1/7/2016 | 30/06/2017 | NA |  |  |  |  | Reviewed Rules of Order, Council Resolution, Provincial Gazette Promulgation | CORP | 109 | Adjusted during budget adjustment
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2017 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM | 109
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2017 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 110
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2017 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of projects executed/# of projects in the action plan) | Target achieved | 100% of project executed are finalised and reported to APAC | None | None | Internal Audit report to Audit and Performance Audit Committee | MM | 111
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2017 | 7 | 7 | Audit and Performance Audit Committee | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 | Target achieved | 2 | None | None | Minutes, Attendance register, invitations | MM | 112
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2017 | 4 | 4 | Audit and Performance Audit Committee Reports | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 | Target achieved | 1 | None | None | Council resolution, Attendance register | MM | 113
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 September 2016 | 1 | 1 | IAA and APAC Assessment report | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/09/2017 | N/A | N/A | N/A | N/A | N/A | Report, Council Resolution | MM | 114
Information Technology | Good governace and Administrative Excellence | Implement automisation of municipal call centre by 30 June 2017 | Manual system | Computerized call center system | Implement automisation of municipal call centre | Civic Center | INCOME | 500000 | 300000 | 0 | 1/7/2016 | 30/6/2017 | Evaluate tender and appoint service provider | Target not achieved | Evaluate of tender done and appoint service provider not done | Tender 9 of 2017 was evaluated on 28/03/2017 and no bidder complied with the bid document requirements | Re-advertise the tender | Specifications, Advert, Appointment letter, Project report | CORP | 115
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 30 June 2017 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Civic Center and regional offices | INCOME | 100000 | 125896.47 | 125896.47 | 1/7/2016 | 30/6/2017 | Compile spec and submit to bid committee | Target achieved | Compilation of specification done and submitted to bid committee | None | None | Purchase Orders, Test certificate | CORP | 116
Information Technology | Good governace and Administrative Excellence | To procure server harddrive 30 June 2017 | Phase 1 done | Server harddrive installed | Server harddrive | Civic Center | INCOME | 150000 | 124103.57 | 0 | 1/7/2016 | 30/6/2017 | Install and commission | Target achieved | Installation and commission done | None | None | Purchase Order | CORP | 117
Information Technology | Good governace and Administrative Excellence | To install telephone and computer network infrastructure new offices Civic Center by 31 December 2016 | New offices Civic Center | Network infrastructure new offices Civic Center | Network infrastructure new offices Civic Center | Civic Center | INCOME | 230000 | 136065 | 136064.4 | 1/7/2016 | 31/12/2016 | N/A | N/A | N/A | N/A | N/A | Installation report | CORP | 118
Information Technology | Good governace and Administrative Excellence | To procure and install the new VEEAM backup server by 30 June 2017 | Only two telephone points | New VEEAM backup server function | VEEAM backup server | Civic Center | INCOME | 150000 | 241135 | 152590.23 | 1/7/2016 | 30/06/2017 | Install and commission | Target achieved | Veeam Backup Server delivered on 16/11/2017 and installed by service provider on 23/11/2017 | NA | NA | Specifications, Apointment letter, Project report | CORP | 119
Information Technology | Good governace and Administrative Excellence | To add extra telephone points at Municipal Stores complex by 31 March 2017 | N/A | Add extra telephone points at Municipal Stores complex | Telephone points at Municipal Stores complex | Makhado Municipality (Stores complex) | INCOME | 200000 | 300000 | 0 | 1/7/2016 | 31/03/2017 | Testing and project signed off | Target not achieved | Testing not done and project signed off not done | Electricity stores did not have all brackets | Made brackets; will continue in Q4 | Specifications, Appointment letter, Project report | CORP | 120
Information Technology | Good governace and Administrative Excellence | To Implement MCGICTP in the policy 31 March 2017 | No ICT strategy | Implementation MCGICTP, 2015 | Implementation MCGICTP, 2015 | Makhado Municipality | INCOME | 500000 | 500000 | 0 | 1/7/2016 | 31/03/2017 | Evaluate tenders and appoint service provider | Target not achieved | Bid Evaluation was completed on the 13/03/2017, BAC did not yet submit their recommendation to Accounting Officer | Bottle neck at SCM unit impacts on timelines; validity period of tender expired; may have to be readvertised | Project have to be re-advertised because its validity period expired in the meantime | Specifications, Appointment letter, Approved ICT Strategy | CORP | 121
Information Technology | Good governace and Administrative Excellence | To purchase laptops, computers and printers by 31 March 2017 | New equipment | ICT equipment purchased | Purchase of ICT equipment | Makhado Municipality | INCOME | 400000 | 500000 | 270268.09 | 1/7/2016 | 31/03/2017 | Delivery of all equipements | Target achieved | All equipements delivered | None | None | Proof of purchase | CORP | 122
Information Technology | Good governace and Administrative Excellence | Upgrade VIP HR ESS Software (for employee leave application apart from existing VIP Leave module) BY 30 June 2017 | Upgrade | ESS Software (for employee leave application apart from existing VIP Leave module) | ESS Software (for employee leave application apart from existing VIP Leave module) | Civic Center | INCOME | 200000 | #VALUE! | Operational | 1/7/2015 | 31/12/2015 | Project removed during budget adjustment | Project removed during budget adjustment | Project removed during budget adjustment | Project removed during budget adjustment | N/A | Approval by MM, Project report | CORP | 123
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2017 | 15 | 6 | Council meeting | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2015 | 30/6/2017 | 2 | Target achieved | 3 | None | None | Minutes, Attendance register, notice of invitations. | CORP | 124
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2017 | 25 | 24 | Executive Committee Meetings | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2015 | 30/6/2017 | 6 | Target achieved | 9 | None | None | Minutes, Attendance register, notice of invitations. | CORP | 125
Communication | Good governace and Administrative Excellence | To review BathoPele Service Standards by 31 December 2016 | 1 | BathoPele Service Standards reviewed | Bathopele service standards | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2015 | 31/12/2017 | N/A | N/A | N/A | N/A | N/A | Approved 2015 Batho Pele Service Standards | CORP | 126
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | New | Council approved website policy | Comprehensive website policy | Civic Center | INCOME | Operational | Operational | Operational | 1/7/2015 | 31/12/2017 | N/A | N/A | N/A | N/A | N/A | Council resolution | CORP | 127
Communication | Good governace and Administrative Excellence | To revamp municipal website by 30 June 2017 | Upgrade | Municipal website revamped | Revamp municipal website | Civic Center | INCOME | 60000 | 80000 | 0 | 1/7/2015 | 30/6/2017 | Write memorandum for approval by MM | Target achieved | Memorandum for approval by MM done | None | None | Attendance register, Memo and Order request | CORP | 128
Public Participation | Good governace and Administrative Excellence | To review the public participation by 31 March 2017 | Public Participation policy | Public Participation policy reviewed | Public Participation Policy | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 31/03/2017 | Submit the final version of the Public Participation Policy to Council for approval | Target achieved | Final version of the Public Participation Policy was submitted and approved by Council Resolution A.104.14.07.16 | None | None | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 129
Public Participation | Good governace and Administrative Excellence | # of ward committee meetings held by 30 June 2017 | 456 | 456 | Support services for monthly ward committee meetings | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 114 | Target achieved | 114 | NA | NA | Minutes, Attendance register, Ward committee quarterly report | CORP | 130
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2017 | 4 | 4 | Public Participation | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 | Target achieved | 1 | None | None | Attendance register and Programme | CORP | 131
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 September 2016 | 1 | 1 | Imbizo Feedback Session | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/09/2017 | N/A | N/A | N/A | N/A | N/A | Attendance register and program | CORP | 132
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework by 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/09/2017 | N/A | N/A | N/A | N/A | N/A | Approved Stakeholders management Framework and council resolution | CORP | 133
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 June 2017 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | INCOME | Operational | Operational | Operational | 1/7/2016 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Approved Communication strategy and council resolution | CORP | 134