## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
SECOND QUARTER/MID-YEAR PERFORMANCE REPORT
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER/ORGANISATIONAL LEVEL)
FOR
2016/2017 FINANCIAL YEAR

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vision and Mission
3. Departments
4. Higher Level SDBIP
5. Lower SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
MFMA Section 72. (1) The accounting officer of a municipality must by 25 January of each year- a) assess the performance of the municipality during the first half of the financial year, taking into account- i. the monthly statements referred to in section 71 for the first half of the ii. the municipality's service delivery performance during the first half of financial year: the financial year, and the service delivered targets and performance indicators set in the service delivery and budget implementation plan: identified in the annual report: and control of the municipality, taking into account reports in terms of section 88 from any such entities; and iii. the past year's annual report, and progress on resolving problems iv. the performance of every municipal entity under the sole or shared b) submit a report on such assessment to- i. the mayor of the municipality; ii. the National Treasury; and relevant the (2) The statement referred to in section 71(1) for the sixth month of a financial year may be incorporated into the report referred to in subsection (I)(b) of this section. (3) The accounting officer must, as part of the review. a) make recommendations as to whether an adjustments budget is necessary: and b) (b) recommend revised projections for revenue and expenditure to the extent that this may be necessary.

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## ANALYSIS (hidden)
SECOND QUARTER ANALYSIS REPORT 2016/17 FY
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
SECOND QUARTER ANALYSIS REPORT 2016/17
Integrated Development Planning | 1 | 1 | 0 | 0
Performance Management | 4 | 3 | 0 | 1
Human Resources and Organizational Development | 8 | 5 | 1 | 2
Special Programs | 2 | 2 | 0 | 0
Spatial and Town Planning | 20 | 15 | 5 | 0
| 35 | 26 | 6 | 3
TOTAL
0%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | 1 | 0 | 1 | 0
Library Services | 1 | 0 | 1 | 0
Waste Management | 2 | 0 | 1 | 1
Parks and Recreational | 4 | 0 | 4 | 0
Protection Services | 1 | 0 | 1 | 0
Electrical Provision | 30 | 14 | 12 | 4
Roads, Bridges and Storm water | 10 | 3 | 6 | 1
Building & Construction | 9 | 5 | 4 | 0
| 58 | 22 | 30 | 6
TOTAL
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
MUNICIPAL FINANCE AND MANAGEMENT AND VIABILITY
Expenditure management | 4 | 1 | 2 | 1
Revenue Management | 2 | 1 | 0 | 1
Budget and Reporting | 3 | 1 | 0 | 2
Supply Chain Management | 1 | 0 | 1 | 0
Asset Management | 1 | 1 | 0 | 0
| 11 | 4 | 3 | 4
TOTAL
0%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | 3 | 0 | 0 | 3
TOTAL | 0 | 0 | 0 | 3
0%
PROGRAMME | NO OF INDEX | TARGET ACHIEVED | TARGET NOT ACHIEVED | TARGET NOT APPLICABLE
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | 3 | 2 | 0 | 1
Fraud and Anti - Corruption | 1 | 1 | 0 | 0
Policies and By Laws | 2 | 1 | 0 | 1
Public Participation | 6 | 2 | 1 | 3
Internal Auditing | 6 | 3 | 0 | 3
Information Technology | 10 | 4 | 6 | 0
Council Services | 2 | 2 | 0 | 0
Communication | 3 | 2 | 1 | 0
| 33 | 17 | 8 | 8
TOTAL
0%
OVERALL PERFORMANCE

## HIGH LEVEL SDBIP
4. HIGHER LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Project Name | Location | Ward/Dept | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End Date | 1st Q Target | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | IDP Review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Complete the IDP analysis phase and conduct the IDP representative forum. | Conduct Strategic Planning session and compile the IDP strategic chapter | Target achieved | Strategic Planning was conducted session and IDP strategic chapter compiled | None | None | Operational | Council resolutions, Draft IDP, Attendance register, Invitations for strategic plan, IDP Consultation attendance register. | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2017/2018 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2016/2017 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2017/2018 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Signed SDBIP | MM | 2
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2017 | 165 | 135 | Training | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | 70 | 50 | Target not achieved | Only 12 employees has undergone the process of training | Delay in the appointment of service provider | Service provider has been appointed the training will commence during third quarter | Operational | Proof of attendance | CORP | 3
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2017 | 16 | 16 | Training | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Proof of attendance | CORP | 4
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2017 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Organogram review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | Invite inputs from departments regarding the new organogram | Target achieved | Invite inputs from departments regarding the new organogram done | None | None | Operational | Minutes and attendance register, Council resolutions, | CORP | 5
Human Resources and Organizational Development | Invest in human capital | To review the HR Strategy by 30 June 2017 | HR Strategy in place | HR Strategy reviewed | HR Strategy review | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | Appointment of facilitator, Development of terms of reference | Information sharing with stakeholders. Consultation with management | Target achieved | Information sharing with stakeholders done. Consultation with management done | None | None | Operational | Appointment letter, Draft HR Strategy, Approved HR Strategy, Council resolution | CORP | 6
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | 4 | 4 | Recruitment in terms of EE Plan | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Appointment letters | CORP | 7
Spatial and Town Planning | Advance Spatial Planning | % achievements of spatial programs indicators/targets per quarter | 100% (16/16) | 100% (16/16) | Permission to Occupy | Makhado Municipality | N/A | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 100% (15/15) | 100% (15/15) | Target achieved | 100% (15/15) | None | None | Operational | Activity reports | DEVP | 8
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Makhado Town, Tshikota Township, Vleifontein, Waterval Township, Dzanani township, Vuwani Township, Kutama-Sinthumule Area, Brambos | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | 2016-01-07 | 30/6/2017 | 19149 (non cumulaitve) | 19149 (non cumulaitve) | Target achieved | 19149 (non cumulaitve) | None | None | Operational | Proof of collection from the affected stakeholders. | MM and COMM | 9
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2017 | 3 | 3 | Development of Parks | 5047 park,Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 0 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | - | Approval memo. RFP, appointment letter, Completion certificate | COMM | 10
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2017 | 1180 | 1100 | Electrification of households | Magau, Tshiozwi, Ramantsha, Madodonga,Mamburu, Makushu, Wisagalaza, Sukani, Mamburu, Gogobole, Tshivulana, Ratombo, Fredom, Lusaka, Tshivhuyuni. | Ward 23,25,03 | INCOME | 21824299 | 5995984.33 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 25000000 | Proof of connections to targeted households | MM and TECH | 11
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads tarred by 30 June 2017 | 18.9km | 49.9km | Upgrading of roads | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 24383575.87 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | 149751285 | Project progress report, Certificate of completion | TECH | 12
Sports Facilities | Accessible basic and infrastructure services | To construct Tshivhuyuni sports and recreational facilities by 30 June 2017 | N/A | Construction of Tshivhuyuni sports and recreational facilities completed | Construction of Tshivhuyuni sports and recreational facilities | Makhado Municipality | Ward 12 | MIG | 600000 |  | 2016-01-07 | 30/6/2017 | Develop terms of ref and submit to SCM | Advertisent to appoint consulting engineer. | Target achieved | Advertisent to appoint consulting engineer done | None | None | N/A | Terms of ref, Advert, Designs, Appointment letter for consultants | TECH | 13
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Financial Statements | Sound Financial Management and viability | To obtain unqualified audit opinion by 31 December 2015 | Unqualified audit opinion | Unqualified audit opinion obtained | Auiting of financial statements | Makhado Municipality | Aministration | Income | Opeartional | Opeartional | 2016-01-07 | 31/12/2016 | Develop financial statement and submit to AG | Unqualified audit opinion obtained | Target not achieved | Qualified Opinion | Supply Chain Compliance issues | To develop and implement the AGSA action plan | Opeartional | AG report | B&T | 14
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | Aministration | Income | 198206314.45 | 13274391.75 | 2016-01-07 | 30/6/2017 | 10% | 40% | Target Not Achieved | 36% (50963056.79/198206314.45) | Delays in procurement processes | To improve in the third quarter | OPEX | Quarterly Financial Report | MM and All Directors | 15
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | Aministration | Income | 136817564 | 24383575.87 | 2016-01-07 | 30/6/2017 | 10% | 40% | Target Not Achieved | 18% (R24201576/ R136817564) | Delays in procurement processes | To improve in the third quarter | OPEX | Quarterly Financial Report | MM | 16
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | Aministration | Income | 17000000 | 13305 | 2016-01-07 | 30/6/2017 | 10% | 40% | Target Achieved | 83% (R13 305 089.47/ R16 000 000.00 | None | None | OPEX | Quarterly Financial Report | MM | 17
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Makhado Municipality | Aministration | Income | 1600000 | 829996 | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | Expenditure Report | B&T | 18
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | Aministration | Income | 342227123 | 89333110.28 | 2016-01-07 | 30/6/2017 | 20% | 45% | Target Achieved | 94% (R89333110.28/R94745938.80) | None | None | OPEX | Section 71 report (c1 schedule) | B&T | 19
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created | 800 | 800 | LED job opportunities | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | EPWP, CWP, and Community Projects reports | MM and DEVP | 20
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governace and Administrative Excellence | # of risk activities cordinated by 30 June 2016 | 13 | 13 | Risk Management activities | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 2 | 3 | Target achieved | 3 | None | None | OPEX | Risk Management Register and Reports | MM | 21
Policies and By Laws | Good governace and Administrative Excellence | # of by laws to be reviewed by 30 June 2016 | 4 | 6 | Reviewing of Municipal By-laws | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | Council resolutions, Copies of approved by laws. | CORP | 22
Internal Auditing | Good governace and Administrative Excellence | No of internal audit indicators/ activities/ projects implemented by 30 June 2016 | 6 | 8 | Internal Audit projects | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-04 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | Copy of the plan | MM | 23
Information Technology | Good governace and Administrative Excellence | No of IT projects implimented by 30 June 2016 | 8 | 8 | IT Projects | Civic Center | Aministration | Income | R3000,000 |  | 2016-01-07 | 30/6/2017 | 2 | 3 | Target achieved | 3 | None | None | OPEX | Advertisement for RFP | CORP | 24
Council Services | Good governace and Administrative Excellence | # of Council meetings convened by 30 June 2016 | 15 | 6 | Council meetings | Makhado Municipality | Aministration | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 1 | 1 | Target achieved | 1 | None | None | OPEX | Minutes, Attendance register, notice of invitations. | CORP | 25
Communication | Good governace and Administrative Excellence | No of communication indicators/activities/projects implemented by 30 June 2016 | 5 | 5 | Communication projects | Civic Center | Ward 20 | Income | R20,000.00 | 0 | 2016-01-07 | 30/6/2017 | 2 | 3 | Target achieved | 3 | None | None | OPEX | TVs and payment certificates | CORP | 26
Public Participation | Good governace and Administrative Excellence | No of public participation indicators/activities/projects implemented by 30 June 2016 | 7 | 6 | Public Participation | Makhado Municipality | All wards | Income | Operational | Operational | 2016-01-07 | 30/6/2017 | 3 | N/A | N/A | N/A | N/A | N/A | OPEX | Attendance register and Programme | CORP | 27

## LMTOD
5. LOWWER SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End Date | 1st Q Target | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | 17/18 R'000 | 18/19 R'000 | Portfolio Of Evidence | Dept | Indicator No
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2016/2017 financial year by 31 May 2017 | IDP review for 2015/2016 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2017 | IDP Review | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | Complete the IDP analysis phase and conduct the IDP representative forum. | Conduct Strategic Planning session and compile the IDP strategic chapter | Target achieved | Strategic Planning sesion was conducted and IDP strategic chapter compiled | None | None | Operational | Operational | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget 30MJune 2017 | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Makhado Municipality | Income | Operational | Operational | 1/4/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Signed SDBIP | MM | 2
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2017 | 8 | 8 | Quarterly performance reports | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 (Draft Annual Report 2015/2016 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 | 1 (First Quarter SDBIP performance Report 2016/2017) | Target achieved | 1 (First Quarter SDBIP performance Report 2016/2017) submitted to Council | None | None | Operational | Operational | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 3
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 September 2016 (# of managers with signed performance agreements/# of managers appointed) | 100% (6/6) | 100% | Performance agreements | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/09/2016 | 100% | 100% | Target achieved | 100% (6/6) | None | None | Operational | Operational | Signed Performance Agreements | MM | 4
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conducted by 30 June 2017 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 (Annual Assessment 2013/2014) | 1 (Informal Assessment 2014/2015) | Target achieved | 1 (Informal Assessment 2014/2015) conducted | None | None | Operational | Operational | Scorecards, Attendance Register | MM | 5
Human Resources and Organizational Development | Invest in human capital | To fill all (100%) posts in terms of the approved priority list by 30 June 2017 | 25 employees were appointed, 8 interns appointed. | 100% prioritised post filled | Personnel Recruitment | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | Submit an item to council for decision regarding the advertised posts. | Implement the Council resolution. | Target achieved | Council resolution I plemented (Post were advertised) | None | None | Operational | Operational | Advertisement, Shortlisting reports, Interview reports and Appointment letters, Council resolution | CORP | 6
Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2017 | 6 events | 6 events | Employee Assistance Campaigns | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 events | 1 event | Target achieved | 1 event conducted | None | None | Operational | Operational | Invitations, attendance registers and close-out report | CORP | 7
Human Resources and Organizational Development | Invest in human capital | To develop 5 outstanding HR policies by 30 June 2017 | No transfer policy, Outdated Placement, Standby and Overtime policy | Transfer policy, Placement policy, Standby Allowance policy and Overtime policy. | Review and Development of HR policies | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/6/2017 | Development of 3 draft policies | Submit the policies (Transfer policy, Placement policy, Standby Allowance policy) to LLF | Target achieved | Policies (Transfer policy, Placement policy, Standby Allowance policy) sbmitted to LLF | None | None | Operational | Operational | Council resolutions, Draft and Final policy documents | CORP | 8
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualified learners by 31 March 2017 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | Makhado Municipality | Income | 450000 | 295.26 | 1/7/2016 | 31/03/2017 | Bursary Committee meeting to review External Bursary Policy and procedures | Advertisement for applicants to respond | Target achieved | Advertisement for applicants to respond done | None | None | Operational | Operational | Advert, List of qualifying leaners and Letters of bursary awards | CORP | 9
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2017 | 48 events done in 2015/2016 | 49 for 2016/2017 | Special Programs | Makhado Municipality | Income | 600000 | 253688.75 | 1/7/2016 | 30/6/2017 | 17 | 8 | Target achieved | 8 Events held | None | None | Operational | Operational | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 10
Spatial and Town Planning | Advance Spatial Planning | To purchase Plan Print Machine for Building Section by 31 March 2017 | Old Machine | Plan Print Machine for Building Section purchased | Plan Print Machine | Makhado Municipality | INCOME | 250000 | 0 | 1/7/2016 | 31/12/2016 | Develop Specification and submit to supply chain management unit. | Tender advertisement | Target not achieved | Tender advertisement not done | The tender has been cancelled due to centralization of functionality to ICT | The project will be done by ICT. | Operational | Operational | Specifications, Advertisement, Proof purchase | DEVP | 11
Spatial and Town Planning | Advance Spatial Planning | To finalise the extension of Civic Centre by 31 December 2016 | New building | Extension of Civic Centre finalized | Extension of Civic Centre | Makhado Municipality | INCOME | 100000 | 223762.5 | 1/7/2016 | 31/12/2016 | Paving of the surrounding building | Finalise paving of the surrounding building | Target not Achieved | Finalise paving of the surrounding building not done | Financial contraints | To be adjusted | Operational | Operational | Project Report | DEVP | 12
Spatial and Town Planning | Advance Spatial Planning | To finalize the New Disaster centre -Erf 235 30 June 2017 | New building | New Disaster centre -Erf 235 finalized | New Disaster centre -Erf 235 | Makhado Municipality | INCOME | 500000 | 267790 | 1/7/2016 | 30/06/2017 | Finalise Roofing | Plastering,electrical connection and Plumbing | Target achieved | Plastering,electrical connection and Plumbing done | None | None | Operational | Operational | Project Report | DEVP | 13
Spatial and Town Planning | Advance Spatial Planning | To purchase 18 x Aircons for new offices by 31 March 2017 | New building | 18 x Aircons for new offices purchased | 18 x Aircons for new offices | Makhado Municipality | INCOME | 200000 | 267790 | 1/7/2016 | 31/03/2016 | Purchase aircons needed for 1st quarter | Purchase aircons needed for 2nd quarter | Target Achieved | Purchase aircons needed for 2nd quarter (17aircons purcharsed) | None | None | Operational | Operational | Proof of purchase and installation | DEVP | 14
Spatial and Town Planning | Advance Spatial Planning | To purchase 2 x Theodolities for Survey Technician by 31 March 2017 | New | 2 x Theodolities for Survey Technician purchased | 2 x Theodolities for Survey Technician | Makhado Municipality | INCOME | 100.000.00 | 0 | 1/7/2016 | 31/03/2016 | Develop Specification | Tender advertisement | Target not Achieved | Tender advertisement not done | Financial contraints | To be adjusted | Operational | Operational | Specifications, Advertisement, Delivery note. | DEVP | 15
Spatial and Town Planning | Advance Spatial Planning | Upgrading of Dzanani Traders Market 30 June 2017 | N/A | Upgrading of Dzanani Traders Market | Upgrading of Dzanani Traders Market | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 30/6/2017 | Develop Specification for designs and erection of market stalls | Tender advertisement | Target not Achieved | Tender advertisement not done | Delay in finalising specification | To adevrtise befire end of third quarter | Operational | Operational | Designs, Specifications, Advertisement, Appointment letter | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | Development of informal business area Ext 12 by 30 June 2017 |  | Informal business area Ext 12 developed by 30 June 2017 | Development of informal business area | Makhado Municipality | INCOME | 3000000 |  | 1/7/2016 | 30/06/2017 | Design the plans internally. Develop specifications for tender advertisement | Tender advertisement for construction of informal business area for motor mechanics |  |  |  |  | Operational | Operational | Designs, Specifications, Advertisement, Appointment letter | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival by 30 June 2017 | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Target achieved | 30 (30/30) 30 application received/(# of application attended to within 90 days). | None | None | Operational | Operational | Site inspection report, Register of applications | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival by 30 June 2017 | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Target achieved | 11 correponces written and 1462 benefiiries capturered | None | None | Operational | Operational | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2017 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of building plans assessed/# of building plans received) | 100% (# of building plans assessed/# of building plans received) | Target achieved | 100% (33/33) 33 received and 18 aprroved | None | None | Operational | Operational | Building plans register | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2017 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | Target achieved | 100% 1(19/19) 19 applications processed/# applications received) | None | None | Operational | Operational | Zoning certificates issued | DEVP | 20
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2017 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# applications received) | 100% (# of applications processed/# applications received) | Target achieved | 100% (40/40) 40applications processed/# applications received) | None | None | Operational | Operational | EXCO resolutions | DEVP | 21
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days by 30 June 2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Target achieved | 100% (9/9) 9 application for land use rights inspection conducted within 14 days/# of application received) | None | None | Operational | Operational | Site inspection report, Register of applications | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2017 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target achieved | 100% (10/10) 10 applications processed/# of applications received) | None | None | Operational | Operational | Copy of occupancy certificates issued | DEVP | 23
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target achieved | 100% (12/12) 12 applications processed/# of applications received) | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 24
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Makhado Municipality | INCOME | 1000 000 .00 | 0 | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target achieved | 100% (16/16) applications processed/# of applications received) | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 25
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival by 30 June 2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target achieved | 100% (8/8) applications processed/# of applications received) | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 26
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Target Achieved | 100% (1/1) 1 queries processed/# of queries received) | None | None | Operational | Operational | Correspondence letters and emails. | DEVP | 27
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification by 30 June 2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Makhado Municipality | INCOME | Operational | Operational | 1/1/2016 | 30/6/2017 | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target achieved | 100% (16/16) contravention notices issued within 5 days/# of contravention identified) | None | None | Operational | Operational | Duplicate notices | DEVP | 28
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2017 | 240 | 240 | Routine Inspection | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 60 | 60 | Target Achieved | Routine inspection done | None | None | Operational | Operational | Inspection form, Register | DEVP | 29
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours by 30 June 2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 5 | Target achieved | 100% (145/145) site inspections conducted within 24 hours/# of site inspections application received) | None | None | Operational | Operational | Inspection form, Register | DEVP | 30
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2017 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 30/6/2017 | Proposed names | Consultations on proposed names. | Target not Achieved | Consultations on proposed names was done | None | None | Operational | Operational | Expenditure Report | DEVP | 31

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location/Ward | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End Date | 1st quarter | 2nd quarter | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | Portfolio of Evidence | DEPT | Indicator No
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2017 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Makhado Municipality | INCOME | N/A | 3652.84 | 1/7/2016 | 30/6/2017 | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers | Receiving information from stakeholders. | Target achieved | Receiving information from stakeholders done | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 32
Library Services | Promote community and environmental welfare | To refurbish the library roof by 30 June 2017 | Roof damaged | Refurbishment of the library building completed | Refurbish library building | Makhado Municipality | INCOME | 1200000 | 0 | 1/7/2016 | 30/6/2017 | Development of specifications, Advertisement for Contractor | Evaluation, Adjudication and Appointment of Contractor | Target not achieved | Evaluation , Adjudication and Appointment of Contractor not yet done | Re-prioritization of major projects (re-advertisement). Evaluated for 4 weeks due to volume of documents | To be awarded in the 3rd quarter | Project Progress report | TECH/COMM | 33
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal by 30 June 2017 | 46637 | 19149 | Waste Management | Ward 22, 23, 24, 25, 26. | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Monthly collection reports | COMM | 34
Waste Management | Promote community and environmental welfare | To rehabilitate the existing landfill site by 31 March 2017 | New | Existing Landfill site rehabilitated completed | Rehabilitation of the existing Landfill site | Makhado Municipality | INCOME | 3000000 | 1958825.79 | 1/7/2016 | 31/03/2017 | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. | Evaluation and Adjudication of tenders. Appointment of a service provider.Design of collection pipes and evaporation ponds. Laying of collection pipes and construction of evaporation ponds. Caping of waste with soill | Target not achieved | Evaluation and Adjudication of tenders not done. Appointment of a service provider not done.Design of collection pipes and evaporation ponds not done. Laying of collection pipes and construction of evaporation ponds not done . Caping of waste with soill not done | Delay in committee sitting | Expedite the process of appointment of service provider | Completion certificate | COMM | 35
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Development of Landfillsite | Makhado Municipality | MIG | 5 000 000.00 - |  |  |  | Approval to commence with the project from the MM, Development of specification and submit to SCM. | Advertisent for tendering. Evaluation, Adjudication and appointment of a service provider. |  |  |  |  | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM | 33 | Rollover project
Parks and Recreation | Promote community and environmental welfare | To develop E59 and E60 Park (Makhado Town) by 30 June 2017 | Development | Development of E59 and E60 Park (Makhado Town) completed | Development of E59 and E60 Park (Makhado Town) | Makhado Municipality | INCOME | 400000 | 0 | 1/7/2016 | 30/6/2017 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Appointment of service providers | Target not achieved | Appointment of service providers not done | Delay in committee sitting | Expedite the process of appointment of service provider | Approval memo, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | To develop Dzanani Park next to Shopping Mall by 30 June 2017 | N/A | Development of Dzanani Park next to Shopping Mall completed | Development of Dzanani Park next to Shopping Mall | Makhado Municipality | INCOME | 200000 | 0 |  |  | Approval to commence with the project from the MM. Request for proposal from service providers. | Appointment of service providers | Target not achieved | Appointment of service providers | Delay in committee sitting | Expedite the process of appointment of service provider | Approval memo. RFP, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | Refurnishment and fencing Eltivillas Swimming Pool by 30 June 2017 | N/A | Refurnish and fencing Eltivillas Swimming Pool completed | Refurnish and fencing Eltivillas Swimming Pool | Makhado Municipality | INCOME | 150000 | 0 |  |  | Approval to commence with the project from the MM. Request for proposal from service providers. | Appointment of service providers | Target not achieved | Appointment of service providers | Delay in committee sitting | Expedite the process of appointment of service provider | Approval memo. RFP, appointment letter, Completion certificate | COMM
Parks and Recreation | Promote community and environmental welfare | To refurbish Potgieter Park by 30 June 2017 | Refurbishment | Refurbishment of Potgieter Park completed | Refurbishment of Potgieter Park | Makhado Municipality | INCOME | 300000 | 0 | 1/7/2016 | 30/6/2017 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Appointment of service providers | Target not achieved | Appointment of service providers not done | Delay in committee sitting | Expedite the process of appointment of service provider | Approval memo, appointment letter, Completion certificate | COMM | 37
Parks and Recreation | Promote community and environmental welfare | To construct Tshikota cemetery ablution facilities by 30 June 2017 | No ablution facilities | Construction of Tshikota cemetery ablution facilities completed | Construction of Tshikota cemetery ablution facilities | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 30/6/2017 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Appointment of service providers, start with the design of the ablution plans and submit to building section for approval | Target not achieved | Appointment of service providers, start with the design of the ablution plans and submit to building section for approval | None responsive from the service provider | Re- advertisement of the tender was done | Approval memo, appointment letter, Completion certificate | COMM | 38
Protection Services | Promote community and environmental welfare | To purchase special Garage Roller Door for VTS and 2x 30m long chains |  | Special Garage Roller Door for VTS and 2x 30m long chains | Special Garage Roller Door for VTS and 2x 30m long chains | Makhado Municipality | INCOME | 800000 |  | 1/7/2016 | 30/6/2017 | N/A | N/A |  | N/A |  |  | Specifications, Advertisement, Appointment letter, delivery note | TECH
Parks and Recreation | Promote community and environmental welfare | To pave open Erf 1 -N1 by 30 June 2017 | New | Paving of open Erf 1 -N1 completed | Paving open Erf 1 -N1 | Makhado Municipality | INCOME | 1000000 | 0 | 1/7/2016 | 30/6/2017 | Approval to commence with the project from the MM. Development of specifications and submit to the SCM. Advertisement of the tender. | Appointment of service providers | Target not achieved | Appointment of service providers not done | To be adjusted during budget adjustment | To be adjusted during budget adjustment | Approval memo, appointment letter, Completion certificate | COMM | 39
Protection Services | Promote community and environmental welfare | Establishment of Watervaal Registering Authority by 31 December 2017 | New | Establishment of Watervaal Registering Authority completed | Establishment of Watervaal Registering Authority | Waterval Traffic Station | INCOME | 200000 | 0 | 1/7/2016 | 31/12/2017 | Approval from the MM. Development of specification and submit to supply chain management | Purchase E- Natis equipments | Target not achieved | Purchase of E- Natis equipments not done | The Deparment of Transport did not provide the municipality with the quote | Follow has been done and the E Natis will be purchase during third quarter | Purchase order | COMM | 40
Electricity Provision | Accessible basic and infrastructure services | To replace air conditioner by 30 September 2016 | New | Air Conditioners replaced | Air Conditioners | Makhado | INCOME | 150000 | 0 | 1/7/2016 | 30/09/2017 | Advertisement | Adjudication | Target achieved | Adjudication done | None | None | Advertisement , Adjudication minutes, appointment letter and Job Cards | TECH | 41
Electricity Provision | Accessible basic and infrastructure services | To purchase CT VT Units 11kv and 22kv by 30 June 2017 | New | CT VT Units 11kv and 22kv | CT VT Units 11kv and 22kv | Makhado | INCOME | 400000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Adjudication | Target not achieved | Adjudication not done | BSC postponed | Adjudication to be completed during third quarter. | Advertisement , Adjudication minutes, appointment letter and Job Cards | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To procure Mini Subs by 31 March 2017 | New | Mini Subs replaced | Mini Subs | Makhado | INCOME | 700000 | 257000 | 1/7/2016 | 31/03/2017 | Develop specification, | Requisitions and orders | Target achieved | Requisitions and orders done | None | None | Specification, orders, GRV | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | To procure MV Cable 70 mm 11kv by 31 March 2017 | New | MV Cable 70mm 11kV procured | MV Cable 70mm 11kV | Makhado | INCOME | 500000 | 0 | 1/7/2016 | 31/03/2017 | Develop specification, | Requisitions and orders | Target not achieved | Requisitions and orders not done | Financial constraints | The budget to be adjusted to ring main units. MV Cable projects to be implemented during 2017/18 financial year. | Specification, orders, GRV | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | To purchase strategic spares by 31 March 2017 | New | Strategic spares | Strategic spares | Makhado | INCOME | 200000 | 0 | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Specification, orders, GRV | TECH | 45
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2017 | New | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Makhado | INCOME | 5000000 | 0 | 1/7/2016 | 31/03/2017 | Develop specification, | Requisitions and orders | Target not achieved | Requisitions and orders not done | Delays in Committee sittings | Requisitions and orders to be completed during third quarter. | Specification, orders, GRV | TECH | 46
Electricity Provision | Accessible basic and infrastructure services | To upgrade Shefeera Line by 30 June 2017 | Upgrade | Upgrade Shefeera Line | Upgrade Shefeera Line | Makhado Municipality | INCOME | 300000 | 0 | 1/7/2016 | 30/06/2017 | Design, Appointment of labour, procurement of PPE, bush clearing and pegging. | Excavating pole holes, dress and plant poles | Target not achieved | Excavating pole holes, dress and plant poles not done | Delays in Committee sittings | Excavating pole holes, dress and plant poles to be completed during third quarter. | List of Labourer, Completion certificate | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute Beaufort West line by 30 June 2017 | Upgrade | Reroute of Beaufort West line upgraded | Upgrade and reroute Beaufort West line | Beaufort West line | INCOME | 1000000 | 0 | 1/7/2016 | 30/06/2017 | Desings and Advertisement | Adjudication | Target not achieved | Adjudication not done | Delays in Committee sittings | Adjudication to be completed during third quarter. | Desings , Advertisement, Adjudication minutes and completion certificate | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs 6km by 30 June 2017 | Upgrade | Reroute transmission line 66kV bulk supply to Levubu and Beaufort subs upgraded | Upgrading reroute transmission line 66kV bulk supply to Levubu and Beaufort subs | Makhado Municipality | INCOME | 8000000 |  |  |  | Advertisement for Engineer | Appointment of the engineer |  |  |  |  | Advertisement, adjudication minutes and appointment letters and completion certificate | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To upgrade urban substation by 30 June 2017 | Upgrade | Urban substation upgraded | Upgrade urban substation | Makhado Municipality | INCOME | 5000000 | 332759.36 | 1/7/2016 | 30/06/2017 | Renovations, palisades & contractor to place orders | Lead time for delivery | Target achieved | Lead time for delivery done | none | None | Progress report handover and Completion certificate | TECH | 49
Electricity Provision | Accessible basic and infrastructure services | Upgrading bulk supply Tshituni 2.5MVA by 30 June 2017 | Upgrade | Upgrading bulk supply Tshituni 2.5MVA | Upgrading bulk supply Tshituni 2.5MVA | Makhado Municipality | INCOME | 3000000 | 89043.86 | 1/7/2016 | 30/06/2017 | Application lettre to Eskom and feasibility quate | Budget quaote | Target achieved | Budget quaote done | None | None | Application letter, and feasibility quate | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To upgrade Mountain line by 30 June 2017 | Upgrade | Mountain line upgraded | Upgrading Mountain line | Makhado Municipality | INCOME | 300000 | 0 | 1/7/2016 | 30/06/2017 | Recruitment and procument of PPE | Dress and plant poles phase 2, stringing of conductors phase 2, closing spans phase 2 | Target not achieved | Dress and plant poles phase 2, stringing of conductors phase 2, closing spans phase 2 not done | Pole truck broken (frequent breakdowns) | Outsource truck | List of Labourer, Completion certificate | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To transform oil purification by |  | transform oil purification | transforming oil purification | Makhado Municipality | INCOME | 350000 | 0 | 1/7/2016 | 30/06/2017
Electricity Provision | Accessible basic and infrastructure services | To replace outdoor Curcuit breaker by 30 June 2017 | New | Outdoor curcuit breaker replaced | Circuit breaker | Makhado Municipality | INCOME | 1000000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Adjudication | Target not achieved | Adjudication not done | Delays in Committee sittings | Adjudication to be completed in the 3rd quarter | Advertisement,Adjudication minutes appointment letter, Completion certificate | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2017 | New | Replacement of channel cover completed | Substation channel cover replacements | Makhado Municipality | INCOME | 250000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Evaluation | Target achieved | Evaluation done | None | None | Advert, evaluation minutes, Purchase order | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | Purification of transformer oil by 30 June 2017 | N/A | Transformer oil purified | Transformer oil | Makhado Municipality | INCOME | 350000 | 0 | 1/7/2016 | 30/06/2017 | Specs, advertise, | Evaluation & appointments | Target not achieved | Evaluation & appointments not done | Delays in Committee sittings | Evaluation & appointments to be completed in the third quarter\ | Specs, Ads, evaluatiion & adjudication minutes. Appointment letter. Order. | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | To renovate Substation control room by 30 June 2017 | N/A | Substation control room renovated | Substation control room renovations | Makhado Municipality | INCOME | 100000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Evaluation | Target achieved | Evaluation done | None | None | Advert, evaluation minutes, Purchase order | TECH | 55
Electricity Provision | Accessible basic and infrastructure services | To Service OCB's substation by 30 June 2017 | N/A | Service OCB's | Service OCB's | Makhado Municipality | INCOME | 200000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Adjudication | Target not achieved | Adjudication not done | Delays in Committee sittings | Adjudication to be completed in the 3rd quarter | Advert, evaluation minutes, Purchase order | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To refurbish Transformer in (Levubu) by 30 June 2017 | N/A | Transformer refurbished (Levubu) | Transformer refurbishment (Levubu) | Makhado Municipality | INCOME | 600000 | 0 | 1/7/2016 | 30/06/2017 | Advertisement | Adjudication | Target not achieved | Adjudication not done | Delays in Committee sittings | Adjudication to be completed in the 3rd quarter | Advert, adjudication minutes, Completion certificate | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | Post connection Own licensed areas by 30 June 2017 | N/A | Post connection Own licensed areas | Post connection Own licensed areas | Makhado Municipality | INCOME | 2000000 |  | 1/7/2016 | 30/06/2017 | Appoint contractor | Site hand over and labour recruitment, pegging and planting poles | Target achieved | Site hand over and labour recruitment, pegging and planting poles done | None | None | Appointment letter, project progress report, completion certificate | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village connection completed | Wisagalaza 2 & Chitasi village | Wisagalaza village | INEP/ | 7771500 |  | 1/7/2016 | 30/06/2017 | Appointment of contractor's labour, surveying of poleholes, excarvating poleholes | Dress and planting of poles, stringing of conductors |  |  |  |  | Appointment letter, project progress report, completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Tshikhwani/ Rathidili by 30 June 2017 | New Connetion | Tshikhwani/ Rathidili connection completed | Tshikhwani/ Rathidili | Tshikhwani/ Rathidili | INEP | 1663485.12 | 827318.16 | 1/7/2016 | 30/06/2017 | Appoint engineer, capacity verification and designs | Design approval and appoint contractor | Target achieved | Design approval and appoint contractor done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Maname Paradise by 30 June 2017 | New Connetion | Maname Paradise connection completed | Maname Paradise | Maname Paradise | INEP | 831742.56 | 0 | 1/7/2016 | 30/06/2017 | Appoint engineer, capacity verification and designs | Design approval and appoint contractor | Target not achieved | Design approval and appoint contractor not done | Delays by the SP | Put the service provider on terms for termination | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ratombo/ by 30 June 2016 | N/A | Ratombo connection completed | Ratombo | Ratombo | INEP /income | 1708852.9 | 1553244.3 | 1/7/2016 | 30/06/2017 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. | Target achieved | Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes done. | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Tshiozwi/ Gogobole phase 2 by 30 June 2017 | New Connetion | Tshiozwi/ Gogobole phase 2 completed | Tshiozwi/ Gogobole phase 2 | Tshiozwi/ Gogobole phase 2 | INEP | 1512259.2 | 1252126.83 | 1/7/2016 | 30/06/2017 | Appoint contractor. Commence with project up to pole pegging | Pole planting and stringing | Target achieved | Pole planting and stringing done | None | None | Progress report and Completion certificate | TECH | 62
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 by 30 June 2017 | New Connetion | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 completed | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | Magau/ Makhitha/Tshikodobo/ Zamekomste phase 2 | INEP | 146500.11 | 1037444.43 | 1/7/2016 | 30/06/2017 | Appoint contractor. Commence with project up to pole pegging | Pole planting and stringing | Target achieved | Pole planting and stringing done | None | None | Progress report and Completion certificate | TECH | 63
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mammburu phase 2 by 30 June 2017 | New Connetion | Mammburu connection completed | Mammburu | Mammburu | INEP | 354435.75 | 1506269.84 | 1/7/2016 | 30/06/2017 | Appoint contractor. Commence with project up to pole pegging | Pole planting and stringing | Target achieved | Pole planting and stringing done | None | None | Progress report and Completion certificate | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Madabani by 30 June 2017 | New Connetion | Madabani completed | Madabani | Madabani | INEP | 129959.78 | 0 | 1/7/2016 | 30/06/2017 | Appoint engineer, capacity verification and designs | Designs approval & appoint contractor | Target not achieved | Designs approval & appoint contractor not done | Delays by the SP | Put the service provider on terms for termination | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 65
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Sukani Phase 2 by 31 December 2017 | New Connetion | Sukani connection completed | Sukani | Sukani | INEP | 1814814.72 | 1105231.48 | 1/7/2016 | 31/12/2017 | Energising and completion | N/A | N/A | N/A | N/A | N/A | project progress reportcompletion certificate | TECH | 66
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Freedom Lusaka Phase 2 by 30 June 2017 | New Connetion | Freedom Lusaka Phase 2 connection completed | Freedom Lusaka Phase 2 | Freedom Lusaka Phase 2 | INEP | 125241.12 | 1214587.21 | 1/7/2016 | 30/06/2017 | Energising and completion | N/A | N/A | N/A | N/A | N/A | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 67
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Manavhela/ Madodonga phase 2 by 30 June 2017 | New Connetion | Manavhela/ Madodonga phase 2 completed | Manavhela/ Madodonga phase 2 | Manavhela/ Madodonga phase 2 | INEP | 285927.84 | 3571969.2276 | 1/7/2016 | 30/06/2017 | Appointment of contractor and pole pegging | Pole planting and stringing | Target achieved | Pole planting and stringing done | None | None | Progress report and Completion certificate | TECH | 68
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mavhunga /Muromani by 30 June 2017 | New Connetion | Mavhunga/ Muromani connection completed | Mavhunga Muromani | Mavhunga Muromani | INEP | 141784.9 | 369356.13 | 1/7/2016 | 30/06/2017 | Appointment of engineer, capacity verification and designs | Design approval and appointment of contractor | Target achieved | Design approval and appointment of contractor done | None | None | Desings approval, Site handover certificate, progress report and Completion certificate | TECH | 69
Electricity Provision | Accessible basic and infrastructure services | To pay the engineer on the electrification of Vyeboom by 30 September 2017 | Payment | Payment Done | Payment | Vyeboom | INEP | 867542 | 867541.56 | 1/7/2016 | 30/09/2016 | Pay engineer | N/A | N/A | N/A | N/A | N/A | Payment certificate | TECH | 70
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Revitalization of OK/ Shoprite Traders market project by 31 March 2017 | N/A | Revitalization of OK/ Shoprite Traders market project completed | OK/ Shoprite Traders market revitalization project | Makhado Municipality | MIG | 500000 | 0 | 1/7/2016 | 31/003/2017 | Develop specification | Tender advertisement | Target achieved | Tender advertisement done | None | None | Specification, Advert and Designs | TECH | 71
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | Construction of Sereni Themba to Mashamba post office ( phase 3) by 30 June 2017 | Phase 1 and 2 Constructed | Sereni Themba to Mashamba post office ( phase 3) 4.2 km | Sereni Themba to Mashamba post office ( phase 3) | Makhado Municipality | MIG | 11800000 | 1357492.11 | 1/7/2016 | 30/06/2017 | Advertisement for Construction and appointment of contractor | Complete earthworks and layerworks for 2km | Target not achieved | Site establishment, Setting out, construction fo sub base (20%) not done | Tender re-advertised | Complete earthworks and layerworks for 2km to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 72
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Robert khoza street ( Chavani and Bungeni road) by 30 June 2017 | N/A | To construct Robert khoza street ( Chavani and Bungeni road) | To construct Robert khoza street ( Chavani and Bungeni road) | Makhado Municipality | MIG | 9246000 | 13254837.1138 | 1/7/2016 | 30/06/2017 | 4.5km access road completed and site handover | N/A | N/A | N/A | N/A | N/A | Site establishment report, project progress report, handover report | TECH | 73
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshikwarani to Zamkomste Road - 4.5km by 30 June 2017 | N/A | Tshikwarani to Zamkomste Road - 4.5km completed | Tshikwarani to Zamkomste Road - 4.5km | Makhado Municipality | MIG | 11800000 | 610941.34 | 1/7/2016 | 30/06/2017 | Appoint contractors, preliminary requirements and site establishment | Complete earthworks and layerworks for 1.2km | Target not achieved | Complete earthworks and layerworks for 1.2km not done | Tender re-advertised | Complete earthworks and layerworks for 1.2km to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 74
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshirolwe,Matsa to Manyii road P1- 20km by 30 June 2017 | N/A | Tshirolwe,Matsa to Manyii road P1- 20km completed | Tshirolwe,Matsa to Manyii road P1- 20km | Makhado Municipality | MIG | 11800000 | 729295.26 | 1/7/2016 | 30/06/2017 | Appoint contractors, preliminary requirements and site establishment | Complete earthworks and layerworks for 1.0km | Target not achieved | Complete earthworks and layerworks for 1.0km not done | Tender re-advertised | Complete earthworks and layerworks for 1.0km to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 75
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Mudimeli bridge by 30 June 2017 | New | Mudimeli bridge completed | Mudimeli bridge | Makhado Municipality | MIG | 15000000 | 817448.84 | 1/7/2016 | 30/06/2017 | Development of specifications, Advertisement for Contractor. | Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | No progress. | Tender re-advertised | Accelerate construction programme | Specifications, advertisement, appointment letter, project progress report | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Khunda Roads stormwater 30 June 2017 | New | Khunda Roads stormwater completed | Khunda Roads stormwater | Makhado Municipality | MIG | 10000000 | 1163926.74 | 1/7/2016 | 30/06/2017 | Advertisement for appointment of Consulting Engineers. | Evaluation, Adjudication and Appointment of Consulting Engineers. | Target not achieved | No progress. | Tender re-advertised | Accelerate construction programme | Advertisement copy, appointment letter, design report. | TECH | 80
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To contruct Waterval ablution facilities by 30 June 2017 | New | Waterval ablution facilities completed | Waterval ablution facilities | Makhado Municipality | MIG | 10000000 | 748903.37 | 1/7/2016 | 30/06/2017 | Advertisement for appointment of Consulting Engineers. | Evaluation, Adjudication and Appointment of Consulting Engineers. | Target not achieved | No progress. | Tender re-advertised | Accelerate construction programme | Advertisement copy, appointment letter, design report. | TECH | 81
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Tshedza to Vuvha road- 4.3 km by 30 June 2017 | New | Tshedza to Vuvha road- 4.3 km completed | Tshedza to Vuvha road- 4.3 km | Makhado Municipality | MIG | 11800000 | 817448.84 | 1/7/2016 | 30/06/2017 | Appoint contractors, preliminary requirements and site establishment | Complete earthworks and layerworks for 1.0km | Target not achieved | Complete earthworks and layerworks for 1.0km not done | Tender re-advertised | Complete earthworks and layerworks for 1.0km to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 76
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Gombiti,Tshivhuyuni to Mamphagi P1- 15km by 30 June 2017 | New | Gombiti,Tshivhuyuni to Mamphagi P1- 15km completed | Gombiti,Tshivhuyuni to Mamphagi P1- 15km | Makhado Municipality | MIG | 11800000 | 1163926.74 | 1/7/2016 | 30/06/2017 | Appoint contractors, preliminary requirements and site establishment | Complete earthworks and layerworks for 900m | Target not achieved | Complete earthworks and layerworks for 900m not done | Tender re-advertised | Complete earthworks and layerworks for 900m to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 77
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Xitacini to Jiweni P1 - 6.1km by 30 June 2017 | New | Xitacini to Jiweni P1 - 6.1km completed | Xitacini to Jiweni P1 - 6.1km | Makhado Municipality | MIG | 11800000 | 748903.37 | 1/7/2016 | 30/06/2017 | Appoint contractors, preliminary requirements and site establishment | Complete earthworks and layerworks for 2.0km | Target not achieved | Complete earthworks and layerworks for 2.0km not done | Tender re-advertised | Complete earthworks and layerworks for 2.0km to be completed in the 3rd quarter | Site establishment report, project progress report, handover report | TECH | 78
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To rehabilitate of Internal Streets by 30 June 2017 | Gravel | Rehabilitation of Internal Streets completed | Rehabilitation of Internal Streets | Makhado Municipality | INCOME | 3000000 | 0 | 1/7/2016 | 30/06/2017 | Develop specifications for the rehabilitation of internal streets in Makhado | Advertise to appoint a contractor | Target achieved | Advertise to appoint contractor done | None | None | Spec, Advert and completion certificate | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Fencing of graveyards by 30 June 2017 | Development | Fencing of 8 graveyards | Fencing of graveyards | Hanani, Hlanganani township, Tsianda, Ndouvhada,Vleifontein. | MIG | 2500000 | 1851280.18 | 1/7/2016 | 30/06/2017 | Appoint contractors and erect all vertical poles | Complete project and project handover | Target achieved | Complete project and project handover done | None | None | Spec, Advert and completion certificate | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To develop refuse transfer station for Waterval Region by 30 June 2017 | New | Development of refuse transfer station for Waterval Region | Development of refuse transfer station for Waterval Region | Makhado Municipality | MIG | 500000 | 0 | 1/7/2016 | 30/06/2017 | Develop terms of reference for the refuse transfer station | Advertise to appoint Consulting Engineers | Target not achieved | Advertise to appoint Consulting Engineers not done | Re-prioritization of major projects (re-advertisement). Evaluated for 4 weeks due to volume of documents | Advertise to appoint Consulting Engineers to be completed in the 3rd quarter | Spec, advert and completion certificate | TECH | 81
Building and Construction | Accessible basic and infrastructure services | To construct waste Disposal Cell (New landfill ) 30 June 2017 | New | Construction of waste Disposal Cell (New landfill ) | Construction of waste Disposal Cell (New landfill ) | Makhado Municipality | MIG | 500000 | 678000 | 1/7/2016 | 30/06/2017 | Advertise for appointment of contractors | Appoint contractors, preliminary requirements and site establishment | Target not achieved | Appoint contractors, preliminary requirements and site establishment not done | Re-prioritization of major projects (re-advertisement). Evaluated for 4 weeks due to volume of documents | Appoint contractors, preliminary requirements and site establishment to be completed in the 3rd quarter | Spec, advert and completion certificate | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To upgrade Dzanani Transfer Station - Elec+ Guard room by 30 June 2017 | Upgrade | Upgrade Dzanani Transfer Station - Elec+ Guard room | Upgrade Dzanani Transfer Station - Elec+ Guard room | Makhado Municipality | MIG | 800000 | 0 | 1/7/2016 | 30/06/2017 | Develop specifications for the upgrading of Dzanani Transfer Station | Advertise to appoint Contractors | Target not achieved | Advertise to appoint Contractors not done | Review of the advert | Advertise to appoint Contractors to be completed in the 3rd quarter | Memo,, Spec and completion certificate | TECH | 83
Building and Construction | Accessible basic and infrastructure services | Development of Kutama/Sinthumule Stadium by 30 June 2017 | Development | Kutama/Sinthumule Stadium developed | Development of Kutama/Sinthumule Stadium | Makhado Municipality | MIG | 500000 | 0 | 1/7/2016 | 30/06/2017 | Develop terms of reference for Kutama/Sinthumule Stadium | Advertise to appoint Consulting Engineers | Target not achieved | Advertise to appoint Consulting Engineers not done | Re-prioritization of major projects (re-advertisement). Evaluated for 4 weeks due to volume of documents | Advertise to appoint Consulting Engineers to be completed in the 3rd quarter | Advertisement copy, appointment letter,project progress report, handover report | TECH | 84
Building and Maintanance | Accessible basic and infrastructure services | Refurbishment of Caravan Park buildings 30 June 2017 | Refurbishment | Refurbishment of Caravan Park buildings | Refurbishment of Caravan Park buildings | Makhado | INCOME | 300000 | 158540 | 1/7/2016 | 30/06/2017 | Specification, advertisement | Appointment of contractor | Target achieved | Appointment of contractor done. | None | None | None | TECH | 85
Building and Maintanance | Accessible basic and infrastructure services | Ablution of Tree Park Facility by 31 March 2017 | New | Ablution of Tree Park Facility | Ablution of Tree Park Facility | Makhado | INCOME | 150000 | 0 | 1/7/2016 | 31/03/2017 | Develop and submit spec to SCM | Advertise to appoint contractor | Target achieved | Advertise to appoint contractor done | None | None | Spec, Advert and completion certificate | TECH | 86
Building and Maintanance | Accessible basic and infrastructure services | To construct Standby quarter perimeter wall by 31 March 2017 | Development | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Makhado | INCOME | 225000 | 210562.65 | 1/7/2016 | 31/03/2017 | Develop specification and advertisement and procurement of materials | Construction of brickwork (internal staff) | Target achieved | Construction of brickwork (internal staff) done | None | None | Specification, advertisement, project progress report | TECH | 87
Building and Construction | Accessible basic and infrastructure services | To construct Carport for Employees at Dzanani Traffic by 31 March 2017 | New | Construction for Carport | Construction for Carport | Makhado Municipality | INCOME | 50000 | 44561.4 | 1/7/2016 | 31/03/2017 | Develop and submit spec to SCM | Acquisition of quotations | Target achieved | Acquisition of quotations done | None | None | Spec, Advert and completion certificate | TECH | 88
Building and Construction | Accessible basic and infrastructure services | To remove underground fuel tanks and rehabilitate the soil 30 June 2017 | New | Remove underground fuel tanks and rehabilitate the soil | Remove underground fuel tanks and rehabilitate the soil | Makhado Municipality | INCOME | 900000 | 0 | 1/7/2016 | 30/06/2017 | Develop specifications for appointment of a service provider | Advertise to appoint a contractor | Target achieved | Advertisement to appoint a contractor done | None | None | Spec, Advert and completion certificate | TECH | 89
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Rehabilittion of Waterval streets and stormwater by 30 June 2017 | N/A | Rehabilittion of Waterval streets and stormwater compeleted | Waterval streets and stormwater rehabilittion | Makhado Municipality | MIG | 600000 |  |  |  | Develop terms of ref and submit to SCM | Advertisement to appoint consulting engineer. |  |  |  |  | Terms of ref, Advert | TECH | 78
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Piesanghoek to Khunda road and stormwater Phase II by 30 June 2017 | N/A | Piesanghoek to Khunda road and stormwater Phase II | Piesanghoek to Khunda road and stormwater Phase II | Makhado Municipality | MIG | 4000000 |  |  |  | Advertisement for Construction and appointment of contractor | Site establishment, Setting out, construction fo sub base (20%) |  |  |  |  | Site establishment report, project progress report, handover report | TECH | 79
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct a new bridge at Mudimeli by 2018 | N/A | Mudimeli bridge completed by 2018 | Mudimeli bridge | Makhado Municipality | MIG | 6054000 |  |  |  | Procurementprocess for contractor and appointment of contractor | Foundation 100% done and the columns |  |  |  |  | Specifications, advertisement, appointment letter, project progress report | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To construct Industrial Paving of gate VTS - entrance by 30 June 2017 |  | Industrial Paving of gate VTS - entrance comp;le | Industrial Paving of gate VTS - entrance | Makhado Municipality | MIG | 1000000 |  |  |  | Advertisement for appointment of Contractors | Evaluation, Adjudication and Appointment of Contractor. |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 81
Building and Construction | Accessible basic and infrastructure services | Revitalisation of Tshakhuma Fruit Market (Phase 2) by 30 June 2017 |  | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Revitalisation of Tshakhuma Fruit Market (Phase 2) | Makhado Municipality | INCOME | 1100000 |  |  |  | Advertisement for appointment of Contractors | Evaluation, Adjudication and Appointment of Contractor. |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To plan Siloam Taxi Rank by 30 June 2017 | New | Siloam Taxi Rank (Planning) | Siloam Taxi Rank(Planning) | Siloam | MIG | 600000 |  |  |  | Develop terms of ref and submit to SCM | Advertisent to appoint consulting engineer. |  |  |  |  | Terms of reference, Advertisement, designs | TECH | 90
Building and Construction | Accessible basic and infrastructure services | Rehabilitation of Street (900m) -Dzanani township 30 June 2017 |  | Street Rehabilitation (900m) -Dzanani township | Street Rehabilitation (900m) -Dzanani township | Dzanani township | MIG | 5750000 |  |  |  | Advertisement for appointment of Contractors | Evaluation, Adjudication and Appointment of Contractor. |  |  |  |  | Advertisement copy, appointment letter,project progress report, handover report | TECH | 93
Building and Construction | Accessible basic and infrastructure services | Development of New Waterval Stadium by 30 June 2017 | New | New Waterval stadium developed | Development of New Waterval Stadium | Waterval | MIG | 11100000 |  |  |  | Complete earthworks and layer works | Complete pavilions, ablution faciities, irrigation system and parking area |  |  |  |  | Progress report and completion certificate | TECH | 94
Building and Construction | Accessible basic and infrastructure services | To construct Civic Centre external wall Painting 30 June 2017 |  | Civic Centre external wall Painting | Civic Centre external wall Painting | Makhado Municipality | INCOME | 300000 |  |  |  | Develop spec and submit to SCM | Advertise to appoint service provider |  |  |  |  | Spec, Advert and completion certificate | TECH | 97

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Location | Funding Source | Budget 16/17 R'000 | Expenditure | Start Date | End date | 1st Q Target | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2017 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Makhado Municipality | INCOME | 198206314.45 | 13274391.75 | 1/7/2016 | 30/6/2017 | 10% | 40% | Target Not Achieved | 36% (50963056.79/198206314.45) | Delays in procurement processes | To improve in the third quarter | Operational | Operational | Quarterly Financial Report | MM and All Directors | 90
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2017 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Makhado Municipality | INCOME | 13681756 | 24383575.87 | 1/7/2016 | 30/6/2017 | 10% | 40% | Target Not Achieved | 18% (R24201576/ R136817564) | Delays in procurement processes | To improve in the third quarter | Operational | Operational | Quarterly Financial Report | MM | 91
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2017 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Makhado Municipality | INCOME | 16000000 | 13305 | 1/7/2016 | 30/6/2017 | 10% | 40% | Target Achieved | 83% (R13 305 089.47/ R16 000 000.00 | None | None | Operational | Operational | Quarterly Financial Report | MM | 92
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2017 | 100% | 100% | FMG | Makhado Municipality | INCOME | 1625000 | 829996 | 1/7/2016 | 30/6/2017 | N/A | N/A |  | N/A | N/A | N/A | Operational | Operational | Expenditure Report | B&T | 93
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2017 | 90% | 90% (308004300) | Revenue Collection | Makhado Municipality | INCOME | 405037000 | 89333110.28 | 1/7/2016 | 30/6/2017 | 20% | 45% | Target Achieved | 94% (R89333110.28/R94745938.80) | None | None | Operational | Operational | Section 71 report (c1 schedule) | B&T | 94
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2017 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Makhado Municipality | INCOME | Operational | Operational | 2017-01-01 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 95
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2017 | Final budget was submitted to Council | Final budget submitted to Council | Final budget | Makhado Municipality | INCOME | Operational | Operational | 2017-01-01 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Final budget and Council Resolution | B&T | 96
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Makhado Municipality | INCOME | Operational | Operational | 2016-01-07 | 30/8/2016 | Financial statements compiled and submitted to AG | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Copy of Financial statements | B&T | 97
Budget and Reporting | Sound financial management and viability | # of section 71 reports submitted to Treasury within 10 days after the end of the month by 30 June 2017 | 12 | 12 | Section 71 report submission | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 3 | 3 | Target Achieved | 3 | None | None | Operational | Operational | Copy of acknowledgement of receipt by Treasuries | B&T | 98
Supply Chain Management | Sound financial management and viability | To review the Supply Chain Management policy by 30 June 2017 | 2014/ 15 Supply Chain Management policy was reviewed and amended | Supply Chain Management policy reviewed | Supply Chain Management policy | Makhado Municipality | INCOME | Operational | Operational | 2016-01-07 | 30/6/2017 | N/A | Send the policy to departments for inputs | Target not Achieved | Send the policy to departments for inputs not done | To be done before the end of the third quarter | None | Operational | Operational | Council Resolution | B&T | 99
Asset Management | Sound financial management and viability | % of new acquisitions updated into the Asset Register by 30 June 2017 | 100% | 100% | Updting of Asset Register | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% | 100% | Target Achieved | 100% | None | None | OPEX | OPEX | Schedules of Asset Register movement | B&T | 100

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 1st Q Target | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
5.4. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created 30 June 2014 | 600 | 800 | LED job opportunities | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | EPWP, CWP, and Community Projects reports | MM and DEVP | 101
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2016 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Makhado Municipality | Income | 1200000 | 5758 | 1/7/2016 | 30/9/2016 | Host official opening and the Three Days Makhado Annual Show. | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | Annual Show Report and Audited Financial Statements | DEVP | 102
Local Economic Development | Invest in local economy | # of LED projects supported 30 June 2017 | 9 | 6 | LED Strategy | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/9/2017 | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | OPEX | LED strategy implementation report | MM and DEVP | 103

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Location | Funding Source | Budget 16/17R'000 | Expenditure | Start Date | End date | 1st Q Target | 2nd Q Targets | Performance Remarks | Actual Performance Notes | Challenges | Measures for improvements | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | Indicator No
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate Stategic and operational Risk Assessment and review and approval of risk and fraud management policies by 30 June 2017 | Strategic and Operational Risk Assessment Report developed / coordinated and 6 policies, plans and strategies reviewed and approved | 7 risk activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Attendance register, Minutes and Programme | MM | 104
Risk Management | Good governace and Administrative Excellence | Coordinate quarterly Strategic and Operational monitoring risk report 30 June 2017 | 4 quarterly Strategic and Operational monitoring risk report Coordinated | 4 activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Develop Quarterly Strategic Monitoring Risk Report, | Develop Quarterly Strategic Monitoring Risk Report, | Target Achieved | Quarterly Strategic Monitoring Risk Report done | None | None | Operational | Operational | Strategic Monitoring Risk Report | MM | 105
Risk Management | Good governace and Administrative Excellence | Coordinate Risk Management Committee meetings 30 June 2017 | 4 Risk Management Committee meetings held | 4 activities cordinated | Risk Management project | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Cordinate1 Risk Management Committee meeting | Cordinate1 Risk Management Committee meeting | Target Achieved | 1 Risk Committee meeting held | None | None | Operational | Operational | Minutes and Attendance register | MM | 106
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2017 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Target Achieved | 0% of case received | None | None | Operational | Operational | Case Register | MM | 107
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2017 | 7 by laws reviewed | 6 by laws reviewed | Reviewing of Municipal By-laws | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Development of the 6 draft policies | Submit the 6 draft policies to Council for provisional approval | Target Achieved | 6 draft policies were submitted to Council for provisional approval | None | None | Operational | Operational | 6 draft policies Council resolution Invitations, attendance registers, Final council resolutions and Promulgation notice for by laws | CORP | 108
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 September 2016 | 4 by laws reviewed | 1 by law reviewed | Review of the following by laws: Rules of Order | Makhado Municipality | Income | Operational | Operational | 1/7/2016 | 30/06/2017 | Submit reviewed Rules of Order to Council and promulgate in Limpopo Provincial Gazette after approval by Council | NA | NA | NA | NA | NA | operational | operational | Reviewed Rules of Order, Council Resolution, Provincial Gazette Promulgation | CORP | 109
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2017 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Council Resolution, Copy of the plan | MM | 110
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2017 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | N/A | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Copy of the plan | MM | 111
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2017 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | Target Achieved | 100% (6/6) planned project executed | None | None | Operational | Operational | Internal Audit report to Audit and Performance Audit Committee | MM | 112
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2017 | 7 | 7 | Audit and Performance Audit Committee | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 2 | 1 | Target Achieved | 1 | None | None | Operational | Operational | Minutes, Attendance register, invitations | MM | 113
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2017 | 4 | 4 | Audit and Performance Audit Committee Reports | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 | 1 | Target Achieved | 1 | None | None | Operational | Operational | Council resolution, Attendance register | MM | 114
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 September 2016 | 1 | 1 | IAA and APAC Assessment report | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | 1 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Report, Council Resolution | MM | 115
Information Technology | Good governace and Administrative Excellence | Implement automisation of municipal call centre by 30 June 2017 | Manual system | Computerized call center system | Implement automisation of municipal call centre | Civic Center | INCOME | 500000 | 0 | 1/7/2016 | 30/6/2017 | Compile specification, call for tender advertisement | Evaluate tender and appoint service provider | Target not Achieved | Evaluate tender and appoint service provider not done | Busy benmarking with othe r municipoality | To be done in the thrird quarter | Operational | Operational | Specifications, Advert, Apointment letter, Project report | CORP | 116
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 30 June 2017 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Regional offices | INCOME | 100000 | 125896.47 | 1/7/2016 | 30/6/2017 | Conduct internal analysis and submit to IMPC | Complile spec and submit to bid committee | Target not Achieved | Compile spec and submit to bid committee not done | Delay in the network project at Waterval offices | Memo was generated for implementation. | Operational | Operational | Orders, Payment certificate and intallation report | CORP | 117
Information Technology | Good governace and Administrative Excellence | To install server harddrive 30 June 2017 | Phase 1 done | Server harddrive installed | Server harddrive | Civic Center | INCOME | 150000 | 0 | 1/7/2016 | 30/6/2017 | Compile specification, call for quatationt | Evaluate quoate and appoint service provider | Target achieved | Evaluate quoate and appoint service provider done | None | None | Operational | Operational | Appointment letter, Project agreement, installation report and payment certicate | CORP | 118
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2016 | Unacceptable standard of server room | Acceptable server room conditions | Upgrade server room | Civic Center | INCOME | 50000 | 0 | 1/7/2016 | 31/12/2016 | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business | Evaluate PINACLE AFRAC'S proposal and decide on the wayforward | Target not Achieved | Evaluate PINACLE AFRAC'S proposal and decide on the wayforward not done | Delay was due to time frame for dismatling of envirorac and UPS without distrupting business | The memo was generated | Operational | Operational | Approved memorandum, Written propoal, wayforward outcomes | CORP | 119
Information Technology | Good governace and Administrative Excellence | To install telephone and computer network infrastructure new offices Civic Center by 31 December 2016 | New offices Civic Center | Network infrastructure new offices Civic Center | Network infrastructure new offices Civic Center | Civic Center | INCOME | 230000 | 136164.4 | 1/7/2016 | 31/12/2016 | Link of telephone and computer services between Civi centre and new building | Installation of new points and telephone and cables | Target achieved | Installation of new points and telephone and cables done | None | None | Operational | Operational | Installation report | CORP | 120
Information Technology | Good governace and Administrative Excellence | To procure and install the new VEEAM backup server by 30 June 2017 | Only two telephone points | New VEEAM backup server function | VEEAM backup server | Civic Center | INCOME | 150000 | 12400 | 1/7/2016 | 30/06/2017 | Compile specification, call for quatation | Evaluate quoate and appoint service provider | Target achieved | Evaluate quoate and appoint service provider done | None | None | Operational | Operational | Specifications, Apointment letter, Project report | CORP | 121
Information Technology | Good governace and Administrative Excellence | To add extra telephone points at Municipal Stores complex by 31 March 2017 | N/A | Add extra telephone points at Municipal Stores complex | Telephone points at Municipal Stores complex | Makhado Municipality (Stores complex) | INCOME | 200000 | 0 | 1/7/2016 | 31/03/2017 | Compile specification, call for quatation from the existing service provider | Deliver install and commission telephone services | Target not Achieved | Deliver install and commission telephone services not done | Delay in the identification of telephone points with telecom | The project to be implementation in the third quarter | Operational | Operational | Specifications, Apointment letter, Project report | CORP | 122
Information Technology | Good governace and Administrative Excellence | To Implement MCGICTP in the policy 31 March 2017 | No ICT strategy | Implementation MCGICTP, 2015 | Implementation MCGICTP, 2015 | Makhado Municipality | INCOME | 500000 | 0 | 1/7/2016 | 31/03/2017 | Complile specification and call for tender for specicizide services | Evaluate tenders and appoint service provider | Target not Achieved | Evaluate tenders done and appoint service provider not done | Delay in SCM process | The project to be implementation in the third quarter | Operational | Operational | Specifications, Apointment letter, Approved ICT Strategy | CORP | 123
Information Technology | Good governace and Administrative Excellence | To purchase laptops, computers and printers by 31 March 2017 | New equipment | ICT equipment purchased | Purchase of ICT equipment | Makhado Municipality | INCOME | 400000 | 171728.77 | 1/7/2016 | 31/03/2017 | Submit quatation to IMPC and call for qoatations | Evaluate quatations and appoint service provider | Target achieved | Evaluate quatations and appoint service provider done | None | None | Operational | Operational | Proof of purchase | CORP | 124
Information Technology | Good governace and Administrative Excellence | Upgrade VIP HR ESS Software (for employee leave application apart from existing VIP Leave module) | Upgrade | ESS Software (for employee leave application apart from existing VIP Leave module) | ESS Software (for employee leave application apart from existing VIP Leave module) | Civic Center | INCOME | 200000 | 0 | 1/7/2015 | 31/12/2015 | Call for quatation from existing service provider and get approval to MMM | Implement the module and allow for testing period | Target not Achieved | Implement the module and allow for testing period not done | The project cancelled and to be impemented in the next financial year adjusted | The project cancelled and to be impemented in the next financial year adjusted | Operational | Operational | Approval by MM, Project report | CORP | 125
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 | 1 | Target achieved | 4 | None | None | Operational | Operational | Minutes, Attendance register, notice of invitations. | CORP | 126
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 6 | 6 | Target achieved | 9 | None | None | Operational | Operational | Minutes, Attendance register, notice of invitations. | CORP | 127
Communication | Good governace and Administrative Excellence | To review BathoPele Service Standards by 31 December 2016 | 1 | BathoPele Service Standards reviewed | Bathopele service standards | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 31/12/2017 | Distribute for comments of all departments | Submit reviewed Service Standards to Council for approval | Target Achieved | Service Standards was reviewed and submitted to Council for approval done | None | None | Operational | Operational | Approved 2015 Batho Pele Service Standards | CORP | 128
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 |  | Council approved website policy | Comprehensive website policy | Civic Center | INCOME | Operational | Operational | 1/7/2015 | 31/12/2017 | Submit to Council for approval | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Council approval of policy | CORP | 129
Communication | Good governace and Administrative Excellence | Revamp municipal website | Upgrade | Municipal website revamped | Revamp municipal website | Civic Center | INCOME | 60000 | 0 | 1/7/2015 | 30/6/2017 | N/A | Invitation to SETA for presentation | Target Achieved | Invitation to SETA for presentation done | None | None | Operational | Operational | Attendance register, Memo and Order request | CORP | 130
Public Participation | Good governace and Administrative Excellence | To review the public participation by 31 March 2017 | Public Participation policy | Public Participation policy reviewed | Public Participation Policy | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Compile public participation policy and submit to Council for approval of Draft Policy | Conduct public consultation of the draft public participation policy | Target Achieved | Public consultation of the draft public participation policy conducted | None | None | Operational | Operational | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 131
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 30 June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Makhado Municipality | INCOME | Operational | Operational | 1/7/2016 | 30/6/2017 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Target not Achieved | 76 ward committee meetings not held and quarterly ward committees' report not submitted to Council. | Delay in the formation of ward commitees | Meetings and reports to be done after formation of ward committee is completed | Operational | Operational | Minutes, Attendance register, Ward committee quarterly report | CORP | 132
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/6/2017 | 1 | 1 | Target Achieved | 1 | None | None | Operational | Operational | Attendance register and Programme | CORP | 133
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 September 2016 | 1 | 1 | Imbizo Feedback Session | Makhado Municipality | INCOME | Operational | Operational | 1/7/2015 | 30/08/2017 | 1 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Attendance register and program | CORP | 134
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework by 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Income | INCOME | Operational | Operational | 1/7/2015 | 30/08/2017 | 1 | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Approved Stakeholders management Framework and council resolution | CORP | 135
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Income | INCOME | Operational | Operational | 1/7/2015 | 30/06/2016 | Communication Strategy approved | N/A | N/A | N/A | N/A | N/A | Operational | Operational | Approved Communication strategy and council resolution policy and council resolution | CORP | 136