## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
1ST QUARTER PERFORMANCE REPORT 2015/2016
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER/ORGANISATIONAL LEVEL)
FOR
2015/2016 FINANCIAL YEAR

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1) of MFMA states that On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must—
(a) consider the statement or report;
(b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan;
(c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget;
(d) issue any appropriate instructions to the accounting officer to ensure—
(i) that the budget is implemented in accordance with the service delivery
and budget implementation plan; and
(ii) that spending of funds and revenue collection proceed in accordance
with the budget;

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## Analysis
4. MAKHADO MUNICIPALITY'S KPA AND PROGRAMME ANALYSIS |  |  |  |  | Indicator No
Municipal Transformation and Organisational Development (17%)
Programmes | Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
1. Integrated Development Planning | 1 | 1 | 0 | 0
2. Performance Management System | 4 | 2 | 1 | 1 | 5
3. Human Resource Management | 6 | 2 | 1 | 3 | 8
4. Special Programmes | 2 | 2 | 0 | 0
5. Spatial and Town Planning | 16 | 14 | 2 | 0 | 25 and 29
Total | 29 | 21 | 4 | 4
86%
Basic Service Delivery (56%)
Programmes | Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
1. Disaster Management | 1 | 0 | 0 | 0
2. Library Services | 1 | 1 | 0 | 0
3. Waste Management | 3 | 2 | 0 | 1
4. Parks and Recreation | 3 | 3 | 0 | 0
5. Electrical Engineering | 31 | 28 | 2 | 1 | 50 and 52
6. Roads and Stormwater | 8 | 6 | 2 | 0 | 75-82
7. Sports Facilities | 3 | 0 | 3 | 0
8. Building and Construction | 4 | 1 | 3 | 0
Total | 54 | 41 | 10 | 2
79%
Local Economic Development (4%)
Programmes | Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
1. Local Economic Development | 4 | 1 | 0 | 3
Total | 4 | 1 | 0 | 3
75%
Municipal Finance Management and Viability (9%)
Programmes | Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
1. Expenditure Management | 4 | 3 | 0 | 1
2. Revenue Management | 2 | 1 | 0 | 1
3. Budget and Control | 4 | 2 | 0 | 2
4. Supply Chain Management | 2 | 2 | 0 | 0
5. Asset Management | 1 | 1 | 0 | 0
Total | 13 | 9 | 0 | 4
100%
Good Governance and Public Partcipation (14%)
Programmes | Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
1. Risk Management | 1 | 0 | 1 | 0 | 101
2. Fraud and anti Corruption | 1 | 1 | 0 | 0
3. Public Participation | 7 | 4 | 3 | 0 | 131
4. Policies and By-laws | 1 | 1 | 0 | 0
5. Internal Auditing | 9 | 5 | 0 | 4
6. Information Technology | 8 | 7 | 1 | 0 | 120
7. Communication and event management | 5 | 4 | 1 | 0 | 130
8. Council Services | 2 | 2 | 0 | 0
Total | 34 | 24 | 6 | 4
82%
SUMMARY OF ORGANISATIONAL SCORECARD
| Total no of Indicators | Achieved | Not Achieved | Not Applicable for the Quarter
MTOD | 29 | 21 | 4 | 4
BSD | 54 | 41 | 10 | 2
LED | 4 | 1 | 0 | 3
MFMV | 13 | 9 | 0 | 4
GGPP | 34 | 24 | 6 | 4
| 133 | 96 | 20 | 17
AVERAGE PERFORMANCE
MTOD |  | 86
BSD | BSD | 79
LED | LED | 75
MFMV | MFMV | 100
GGPP | GGPP | 82
TOTAL |  | 84%
ORGANISATIONAL PERFORMANCE

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## MTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 1st Q Target | 15/16 R'000 | 16/17 R'000 | Performance Remarks (Target achieved/Target not achived) | Actual Performance Notes | Challenges | Intervention | Portfolio Of Evidence | Dept | Indicator No
4. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2015 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2016, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2016 | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Complete the IDP analysis phase and conduct the IDP representative forum. | Operational | Operational | Target achieved | The IDP analysis phase has been completed and the IDP representative forum has been conducted | N/A | N/A | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Collect information from departments, Develop a draft SDBIP, Submit to departments for inputs, Incorporate inputs and submit to council for approval by 31 March 2015. Submit to the Mayor for signature, Submit to council for noting. | Makhado Municipality | Income | Operational | Operational | 1/4/2015 | 30/6/2016 | N/A | Operational | Operational | N/A | N/A | N/A | N/A | Signed SDBIP | MM | 2
Performance Management | Good governance and administrative excellence | Number of organisational performance reports developed and submitted to Council by 30 June 2015 | 8 | 8 | Quarterly performance reports | Develop a reporting template and send to departments, Receive completed template and consolidate into one report. Organise SDBIP Management meeting to consider the report. Submit the report to Council for approval. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 2 (Draft Annual Report 2014/2015 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 | Operational | Operational | Target achieved | Draft Annual Report 2014/2015 in term of Section 46 MSA and Fourth Quarter SDBIP performance Report 2014/2015 developed and submitted to Council | N/A | N/A | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 3
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2015 (# of managers with signed performance agreements/# of managers appointed) | 100% (5/5) | 100% | Performance agreements | Develop draft performance agreements. Engage the relevant Section 57 Managers. Submit the final performance agreement to Municipal Manager for signing. Submit the signed agreement to MEC for Cooperative Governance Human Settlement and Traditional Affairs. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% | Operational | Operational | Target achieved | 100% (5/5) All Section 57 Managers signed performance agreements | N/A | N/A | Signed Performance Agreements | MM | 4
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2015 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Write a memorandum for approval of panel members and dates. Invite the participate Conduct assessment and compile assessment report. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 (Annual Assessment 2014/2015) | Operational | Operational | Target not achieved | Annual Assessment for 2014/2015) has been conducted | The assessement were postponement due to unavailability of panel members | To do the assessment in November 2015 | Scorecards, Attendance Register | MM | 5
Human Resources and Organizational Development | Invest in human capital | % of municipalities budget actual spent on implementing the WSP 2015/2016 | New Indicator | 0.31% (2596927.18/835130000) | Training inline with the WSP | Spending of budgt on training of employees and councillors | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A |  |  | N/A | N/A | N/A | N/A | Section 71 reports | CORP | 6
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Draft Organogram 2015/2016 | Approved Organogram by may 2016 | Organogram review | Reviewing of organizational structure | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A | Operational | Operational | N/A | N/A | N/A | N/A | Invitations to the depts, Minutes and attendance register, Council resolutions, | CORP | 7
Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2015 | 67 employees appointed | 30 | Personnel Recruitment | Personnel Recruitment as per priority list | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Advertisement of 10 posts (1st bench) | Advertisement and appointment letter |  | Target not achieved | No posts were ad ertised for first quarter | Delays in terms of identifying critical positions by management | To advertise in October 2015 | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP | 8
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | New Indicator | 8 | Recruitment in terms of EE Plan | Appoint personel at the three highest level following the EE Plan | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | N/A |  |  | N/A | N/A | N/A | N/A | Appointment letters | CORP | 9
Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2016 | 6 events | 6 events | Employee Assistance Campaigns | Orgnanize and present Employee Assistance campaigns for all staff in all regions | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 2 events |  |  | Target achieved | 2 events were ognanized and present Employee Assistance campaigns for all staff in all regions were conducted | None | None | Invitations, attendance registers and close-out report | CORP | 10
Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Development of 3 outstanding HR policies | Compile Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy and submit to Council for approval- then implement | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Development of 3 draft policies |  |  | Target achieved | 3 draft policies has been developed namely, Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy | None | None | Approved 3 policies and the council resolutions (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP | 11
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | 15 awards of bursary | Makhado Municipality | Income | 450000 | Operational | 1/7/2015 | 30/6/2016 | Bursary Committee meeting to review External Bursary Policy and procedures | Operational | Operational | Target achieved | Bursary Committee meeting for review of External Bursary Policy and procedures has been conducted | None | None | Advert, List of qualifying leaners and Letters of bursary awards | CORP | 12
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | 43 events done in 2014/15 | 49 for 2015/16 | Special Programs | Organize and conduct the special programs undertaken in the different desks of the Special Programs Unit | Makhado Municipality | Income | 1250000 |  | 1/7/2015 | 30/6/2016 | 11 | Operational | Operational | Target achieved | None | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 13
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Application received, Site visits, Stand demarcated and compile a report | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of application received/(# of application attended to within 90 days). |  |  | Target Achieved | 100% (16/16) | None | None | Site inspection report, Register of applications | DEVP | 14
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Receive housing queries and attend to them in a form of meetings or written correspondence | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of housing queries attended within 30 days/# of received) |  |  | Target Achieved | 100% (16/16) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 15
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2015 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Response to applicant in writing | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of building plans assessed/# of building plans received) | Operational | Operational | Target Achieved | 100% (149/149) | None | None | Building plans register | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Target Achieved | 100% (30/30) | None | None | Zoning certificates issued | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Target Achieved | 100% (30/30) | None | None | EXCO resolutions | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) |  |  | Target Achieved | 100% (43/43) | None | None | Site inspection report, Register of applications | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2015 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Operational | Operational | Target Achieved | 100% (10/10) | None | None | Copy of occupancy certificates issued | DEVP | 20
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target Achieved | 100% (66/66) | None | None | Application Assessment Report, Register of applications | DEVP | 21
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target Achieved | 100% (8/8) | None | None | Application Assessment Report, Register of applications | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target Achieved | 100% (4/4) | None | None | Application Assessment Report, Register of applications | DEVP | 23
Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Receive application, Send to MM for approval, Notify the applicants to go and pay, After receiving the proof of payment a venue is booked. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target Achieved | 100% (43/43) | None | None | Bookings register | DEVP | 24
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Receive complaints, Liaise with the commissioner and complainant, Arrange a meeting if need | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of queries processed/# of queries received) |  |  | Target not achieved | None | None | None | Correspondence letters and emails. | DEVP | 25
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Conduct inspection, Upon identifying a contravention a notice is issued | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of contravention notices issued within 5 days/# of contravention identified) |  |  | Target Achieved | 100% (16/16) | None | None | Duplicate notices | DEVP | 26
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2015 | 240 | 240 | Routine Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 60 |  |  | Target Achieved | 100% (171/171) | None | None | Inspection form, Register | DEVP | 27
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) |  |  | Target Achieved | 100% (186/186) | None | None | Inspection form, Register | DEVP | 28
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2015 | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming | Conduct public consultation on street names. Compile a list of street names for approval by Council. | Makhado Municipality | Income | 50000 | -- | 1/7/2015 | 30/6/2016 | Proposed names | 200000 | 200000 | Target not Achieved | Draft specification for street naming completed and street names | None | None | Expenditure Report | DEVP | 29

## BSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location/Ward | Funding Source | Budget 15/16 R'000 | Expenditure | 1st quarter | Performance Remarks (Target achieved/Target not achived) | Actual Performance Notes | Challenges | Intervention | Portfolio of Evidence | Dept | Indicator No
5. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers. Receiving information form stakeholders. Update received informkation into the Disaster Management Plan. Draft Disaster Management Plan completed. Submission of the Disaster Management Plan to the IDP Manager for submission to Council | Makhado Municipality | Income |  |  | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers | Target achieved | A request letter to sector departments and municipal regional offices was written. The letter is delivered and a delivery register is kept. Information about new buildings and new employees in key positions was reuqested. | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 30
Library Services | Promote community and environmental welfare | To Refurbish the library roof by 30 June 2016 | Roof dameged | Refurbishment of the library building completed | Refurbish library building | Development of specifications, Advertisement for Contractor. Evaluation, Adjudication and Appointment of Contractor. Construction of roof. Finalisation of the roof and handing over | Makhado Municipality | Income | 1000000 | 0 | Development of specifications, Advertisement for Contractor | Target achieved | Development of specifications done, Advertisement for Contractor done. | None | None | Project Progress report | TECH | 31
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Collection of waste in all the villages in ward 22, 23, 24, 25 and 26 | Wrad 22, 23, 24, 25, 26. | Income | Operational | Operational | N/A | N/A | N/A | N/A | N/A | Monthly collection reports | MM and COMM | 32
Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Development of | Approval to commence with the project from the MM, Development of specification and submit to SCM. Advertisent for tendering. Evaluation, Adjudication and appointment of a service provider. Development of designs and drawings, Construction of 1 x evaporation ponds (excavation, levelling, linning) | Makhado Municipality | MIG | 5 000 000.00 - |  | Approval to commence with the project from the MM, Development of specification and submit to SCM. | Target achieved | Approval to commence with the project from the MM was done, Specification was developed and submitted to SCM on the 2nd of September 2015. | None | None | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM | 33
Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | N/A | Landfill site rehabilitated ompleted | Rehabilitation of the existing Landfill site (Vondelling) | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. Seek quotation for levelling and caping waste with soil and complete the process. Inustallation of leachete collection pipes. Construction of leachete collection dam. | Makhado Municipality | INCOME | 4000000 | 712000 | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Seek quotation for levelling and caping waste with soil and complete the process. | Target achieved | Memorandum of approval to MM was done. Development of specifications was done and submitted to the BSC on the 2nd of Spetmber 2015. Quotation for levelling was done. Caping waste with soil was done. | None | None | Geotechnical report | TECH | 34
Parks and Recreation | Promote community and environmental welfare | To development of 5047 Park by 30 June 2016 | N/A | Development of 5047 Park completed | Development of 5047 Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Makhado Municipality | INCOME | 700000 | 0 | Approval to commence with the project from the MM. Request for proposal from service providers. | Target achieved | Approval to commence with the project from the MM was obtained. Request for proposal from service providers was submitted to SCM on the 2nd September 2015 | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 35
Parks and Recreation | Promote community and environmental welfare | To develop the N1 recreational park by 30 June 2016 | N/A | Development of N1 recreational park completed | Development of N1 recreational park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park |  |  | 300000 | 436842.11 | Approval to commence with the project from the MM. Request for proposal from service providers. | Target achieved | Approval to commence with the project from the MM was obtained. Request for proposal from service providers was submitted to SCM on the 2nd September 2015 | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 36
Parks and Recreation | Promote community and environmental welfare | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat by | N/A | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat completed | Refurbishment and Upgrading of Civic Centre Park+ Tshirululuni/Meerkat Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Makhado Municipality | INCOME | 500000 | 0 | Approval to commence with the project from the MM. Request for proposal from service providers. | Target achieved | Approval to commence with the project from the MM was obtained. Request for proposal from service providers was submitted to SCM on the 2nd September 2015 | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 37
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Magau/Makhitha/Tshikodobo/Zamekomste by 30 June 2016 | N/A | MAGAU/Makhitha/Tshikodobo/Zamekomste connection completed | MAGAU | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dressing and planting of poles, stringing of conductors. Service connections, switching on and completion of the project | Makhado Municipality | INCOME | 935201.32 | 99000 | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment | Target achieved | Development of specifications done, approval of specs done, Advertisement for appointment contractor done, Evaluation done, Adjudication and appointment done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 39
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at MAGULULE by 30 June 2016 | N/A | TSHIOZWI /GOGOBOLE connection completed | TSHIOZWI & GOGOBOLE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dressing and planting of poles, stringing of conductors. Service connections, Switching on. Completion of the project | Makhado Municipality | INCOME | 2101576 | 176000 | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment | Target achieved | Development of specifications done, approval of specs done, Advertisement for appointment contractor done, Evaluation done, Adjudication done and appointment done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 40
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ramantsha by 30 June 2016 | N/A | Ramahantsha /Riverside connection completed | RAMANTSHA/RIVERSIDE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dressing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | Makhado Municipality | INCOME | 1281962 | 110000 | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment | Target achieved | Development of specifications done, approval of specs done, Advertisement done. Appointment contractor not done, Evaluation done , Adjudication done and Appointment not done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 41
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Madodonga/Manavhela by 30 June 2016 | N/A | Madodonga/Manavhela connection completed | MADODONGA | Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | Makhado Municipality | INCOME | 1681261 | 110000 | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment | Target achieved | Development of specifications done , approval of specs done , Advertisement for appointment of contractor done, Evaluation, Adjudication done and appointment done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Mamburu by 30 June 2016 | N/A | Mamburu connection completed | Mamburu | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication. Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. Excavating the pole holes dressing and planting of poles, stringing of conductors. Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate | Makhado Municipality | INEP | 2250000 | 0 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Target achieved | Development of specifications done , Advertisement for engineer and contractor done, Evaluation and Adjudication done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Makhushu by 30 June 2016 | N/A | Makhushu connection completed | MAKUSHU | Development specification for contractor, materials and works, Approval of specification, advertisement, evaluation, adjudication and appointment. Site handover to the contractor, site establishment, appointmnet of labour, survying pole holes, excavating poleholes, dress and plant pole holes and string of conductors. Service connections. Switching on and completion of the project | Makhado Municipality | INEP | 490000 | 0 | Development specification for contractor, materials and works, Approval of specification, advertisement, evaluation, adjudication and appointment | Target achieved | Development specification for contractor not done, materials and works not done, Approval of specification not done, advertisement not done, evaluation not done, adjudication done and appointment done | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | Designs for 2016/2017 electrification projects ) by 30 June 2016 | N/A | Designs for 2016/2017 electrification projects completed | Designs for 2016/2017 electrification projects | Development of specification for engineer, approval of specs, Advertisement. Evaluation, Adjudicationa nd appointment of the engineer.Completion of designs, designs approval by ESKOM, technical electrification forum meeting. | Makhado Municipality | INEP | 952500 | 0 | N/A | N/A | N/A | N/A | N/A | Specifications, Advertisement, appointment letter, Designs, Minutes of of technical forum meeting | TECH | 45
Electricity Provision | Accessible basic and infrastructure services | To upgrade Industrial line by 30 June 2016 | N/A | Upgrading Industrial line | Upgrading Industrial line | Planning and designs, appointment of labour, procurement of PPE, prepare alternative supply, bush clearing phase 1, pegging phase 1, excavating of pole holes for phse 1. Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. bush clearing phase 2, pegging phase 2, excavating pole holes phase 2.Dress and plant poles phase 2, strining of conductors phase 2, closing spans phase 2 | Makhado Municipality | INCOME | 250000 | 38857 | Planning and designs, appointment of labour, procurement of PPE, prepare alternative supply, bush clearing phase 1, pegging phase 1, excavating of pole holes for phse 1 | Target achieved | Planning and designs done , appointment of labour done, procurement of PPE done, prepare alternative supply done, bush clearing phase 1 done, pegging phase 1 done, excavating of pole holes for phse 1done | None | None | Designs, Appointment letter for labourers, Project progress report, | TECH | 46
Electricity Provision | Accessible basic and infrastructure services | To upgrade Shefeera Line by 30 June 2016 | N/A | Upgrade Shefeera Line | Upgrade Shefeera Line | Upgrade Shefeera Line. Appointment of labour, procurement of PPE, bush clearing and mpegging. Excavating pole holes, dress and plant poles. Stringing of conductors, closing spans | Makhado Municipality | INCOME | 600000 | 70323.4 | Appointment of labour, procurement of PPE, bush clearing and mpegging | Target achieved | Appointment of labour done, procurement of PPE done, bush clearing and pegging done | None | None |  | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To upgrade Urban Substations by 30 June 2015 | N/A | Upgrade Urban Substations | Upgrade Urban Substations | Upgrade Urban Substations. Completion of upgarde designs, contractor specification compilation. Advertisent for tendering. Evaluation. Adjudication and appointment of contractor.Procurement of upgrade equipment fo Stubb street substation | Makhado Municipality | INCOME | 2500000 | 211621.21 | Completion of upgrade designs, contractor specification compilation | Target achieved | Completion of upgrade designs done, contractor specification compilation done | None | None |  | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | To upgrade Mountain line by 30 June 2016 | N/A | Upgrading Mountain line | Upgrading Mountain line | Planning and designs, appointment of labour, procurement of PPE, bush clearing and, pegging, excavating of pole holes. Dress and plant poles, stringing of conductors. closing spans, pegging, exate pole holes. Dress and plant poles, strining of conductors, closing spans | Makhado Municipality | INCOME | 250000 | 65587.29 | Planning and designs, appointment of labour, procurement of PPE, bush clearing and, pegging, excavating of pole holes | Target achieved | Planning and designs done, appointment of labour done, procurement of PPE done, bush clearing doen and, pegging and excavating of pole holes done | None | None |  | TECH | 49
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute Beaufort West line by 30 June 2016 | N/A | Upgrade and reroute of Beaufort West line completed | Upgrade and reroute Beaufort West line | Surveying of the pole holes and excavating pole holes | Beaufort West line | INCOME | 1500000 | 0 | Development of specifications for a contractor and works, approval of specs, advertisement, evaluation | Target not achieved | Development of specifications done for a contractor and works, approval of specs done, advertisement not done, evaluation not done | Delays in submitting the specification to supply chain | The process of evaluation to be completed in the second quarter | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To replace oil curcuit breaker by 30 June 2016 | N/A | Replacement of oil curcuit breaker completed | Oil | Replace oil circuit breaker |  | INCOME | 400000 | 0 | Development of specificatons, approval of specs, advertisement, and site inspection | Target achieved | Development of specificatons done, approval of specs done, advertisement done, and site inspection done | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | N/A | Replacement of channel cover completed | Substation channel cover replacements | Replacement of channel cover |  | INCOME | 200000 | 0 | Develop specification and quate. Specification approval. Advertisement and Evaluation . | Target not achieved | Development of specification done and quate. Specification approval done. Advertisement done and Evaluation not done . | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | N/A | Standby generator installed | Standby (Backup) Electricity Power Generator-Dzanani | Installation of standby generator | Dzanani | INCOME |  | 0 | Development of specifications, approval of specification and advertisement | Target achieved | Development of specifications done , approval of specification done and advertisement done | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | To replace air conditioner by 30 Septemeber 2015 | N/A | Air Conditioners replaced | Air Conditioners | Replacement of air conditioner | Makhado | INCOME | 150000 | 128768 | Procurement, Quatations , Installations and invoice | Target avhieved | Procurement done, Quatations done , Installations and invoice done | None | None | Orders and project progress report | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | N/A | CT VT Units 11kv & 22kv replaced | CT VT Units 11kv & 22kv | Replacement of CT VT Units 11kv & 22kv | Makhado | INCOME | 300000 | 0 | Develop specification, specification approval, advertisementand evaluation | Target achieved | Development of specification done, specification approval done, advertisement done and evaluation done | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 55 | Visit Mr Mavhivha
Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming Bravo 9 and A21 by 31 March 2016 | N/A | Low voltage to medium voltage in Rural Farming Bravo 9 and A21 upgraded | Low voltage to medium voltage in Rural Farming Bravo 9 and A21 | Ugrading Low voltage to medium voltage , Bravo 9 and A21 | Makhado | INCOME | 250000 | 127578.8 | Planning, bush clearing pagging , escavating pole holes, dressing of plant hole, stringing the conductor | Target achieved | Planning done, bush clearing pagging done , escavating pole holes done, dressing of plant hole done, stringing the conductor done | None | None | Project progress report | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | N/A | Mini Subs replaced | Mini Subs | Replacement of Mini Subs | Makhado | INCOME | 900000 | 665000 | Develop specification, requisitions and orders | Target achieved | Development of specification done, requisitions and orders done | None | None | Specification, orders, delivery notes | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | N/A | MV Cable 95mm 22kV replaced | MV Cable 95mm 22kV | Replacement of MV Cable 95mm 22kV | Makhado | INCOME | 150000 | 136500 | Develop specification, requisitions and orders | Target achieved | Development of specification done, requisitions and orders done | None | None | Specification, orders, delivery notes | TECH
Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | N/A | Recloser and controllers whole network procured | Recloser and controllers whole network | Procure, supply and delivery of recloser and controllers whole network | Makhado | INCOME | 700000 | 0 | Develop specification, specification approval, advertisement, evaluation and adjudication | Target achieved | Development of specification done, specification approval done, advertisement done, evaluation and adjudication done | None | None | Specification, orders, delivery notes, progress report, completion certificate | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | N/A | Remote control of switch gear Tshipise & Levubu procured | Remote control of switch gear Tshipise & Levubu | Procure, supply and delivery of remote control of switch gear Tshipise & Levubu | Makhado | INCOME | 120000 | 0 | Develop specification, specification approval, advertisement and Site establishment | Target achieved | Develop specification done, specification approval done, advertisement and Site establishment done | None | None | Specification, advertisement, appointment letter, payment certificate | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Replacement of Ring Main Units 11 kV (RMU) | Makhado | INCOME | 300000 | 8000 | Develop specification, requisitions and orders | Target achieved | Develop specification done, requisitions and orders done | None | None | Specification, order, delivery note, project progress report, payment certificate | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To constuct Standby quarter perimeter wall by 31 March 2016 | N/A | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Construction of standby quarter perimeter wall | Makhado | INCOME | 60000 | 0 | Develop specification and advertisement and procurement of materials | Target achieved | Development of specification done and advertisement done and procurement of materials was done | None | None | Specification, advertisement, project progress report | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | N/A | Standby quarter guard room completed | Standby quarter guard room | Construction of standby quarter guard room | Makhado | INCOME | 25000 | 0 | Develop specification and advertisement and procurement of materials | Target achieved | Development of specification was done and advertisement done and procurement of materials was done | None | None | Specification, advertisement, project progress report | TECH | 62
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village connection completed | Wisagalaza 2 & Chitasi village | Electricity connections | Wisagalaza village | INEP/ | 7771500 | 4620047.1838 | Appointment of contractor's labour, surveying of poleholes, excarvating poleholes | Target achieved | Appointment of contractor's labour done, surveying of poleholes done, excarvating poleholes done | None | None | Appointment letter, project progress report, completion certificate | TECH | 63
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at SUKANI by 30 June 2016 | N/A | SUKANI connection completed | SUKANI | Electricity connections | SUKANI | INEP | 1392000 | 0 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Target achieved | Development of specifications done, Advertisement for engineer and contractor done, Evaluation and Adjudication done | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 64
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at TSHIVHULANA by 30 June 2016 | N/A | TSHIVHULANA connection completed | TSHIVHULANA zone 5 | Electricity connections | TSHIVHULANA zone 5 | /INCOME INEP | 1632000 | 0 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Target achieved | Development of specifications done, Advertisement for engineer and contractor done, Evaluation and Adjudication done | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 65
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at Ratombo/ by 30 June 2016 | N/A | RATOMBO connection completed | RATOMBO | Electricity connections | RATOMBO | INEP /income |  | 0 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Target achieved | Development of specifications done, Advertisement for engineer and contractor done, Evaluation and Adjudication done | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 66
Electricity Provision | Accessible basic and infrastructure services | To connect electricity at MUKONDENI by 30 June 2016 | N/A | MUKONDENI connection completed | MUKONDENI & Freedom Lusaka | Electricity connections | MUKONDENI & Freedom Lusaka | INEP | 1040000 | 0 | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication | Target achieved | Development of specifications done, Advertisement for engineer and contractor done, Evaluation and Adjudication done | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 67
Electricity Provision | Accessible basic and infrastructure services | Electrification Rabali Stadium by 30 June 2016 | N/A | Electrification Rabali Stadium facility completed | Electrification Rabali Stadium | Electrification Rabali Stadium | Makhado Municipality | Income | 150000 |  | Development of specifications, approval of specs, advertisement | Target achieved | Development of specifications, approval of specs, advertisement done | None | None | Specifications, Advertisement, Apointment letter, delivery notes, | TECH | 68
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshikota access road by 30 June 2016 | Gravell road | Tshikota upgrading of streets and Pretorius completed | Completion of Tshikota upgrading of streets and Pretorius | Tshikota upgrading of streets and Pretorius | Makhado Municipality | MIG | 1936405 | 1642080.0882 | Fencing along Pretorius street Surfacing of cemetery street Handover of the project. | Target achieved | Fencing along Pretorius streetd done Surfacing of cemetery street done Handover of the project. | None | None | Project progress report, handover report | TECH | 69
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To upgrade Magau road phase 2 by 30 June 2016 | Gravell road | Magau road phase 2 completed | Magau road phase 1 | Magau road phase 1 | Makhado Municipality | MIG | 22000000 | 4547719.3422 | Construction of roadbed and bridge wingwalls | Target achieved | Construction of roadbed and bridge wingwalls done | None | None | Project progress report, Completion certificate, handover report | TECH | 70
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhulana to Tshilaphala access road by 30 June 2016 | Gravell road | Tshivhulana to Tshilaphala access road constructed to a base level. | Tshivhulana to Tshilaphala access road | Tshivhulana to Tshilaphala access road | Makhado Municipality | MIG | 13976988.13 | 0 | Development of specifications, Advertisement for Contractor. | Target achieved | Development of specifications done, Advertisement for Contractor done. | None | None | Specifications, advertisement, appointment letter, project progress report | TECH | 71
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road by 30 June 2016 | Gravell road | Ledig road completed | Ledig road | Ledig road construction | Makhado Municipality | MIG | 9387156 | 5505314.8786 | Construction of base and stormwater drainages | Target achieved | Construction of base done and stormwater drainages done | None | None | Project progress report, handover report | TECH | 72
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road by 30 June 2016 | N/A | Robert Khoza /Chabani Bungeni road completed | Robert Khoza /Chabani Bungeni road construction | Robert Khoza /Chabani Bungeni road | Makhado Municipality | MIG | 23000000 | 3903251.66 | Site establishment Setting out the road Roadbed preparation | Target achieved | Site establishment done Setting out the road done Roadbed preparation done | None | None | Site establishment report, project progress report, handover report | TECH | 73
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road phase 1 by 30 June 2016 | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | Tshivhazwaulu to Rasivhetshela road phase 1 | Tshivhazwaulu to Rasivhetshela road phase 1 | Makhado Municipality | MIG | 23811987.67 | 3096296.1838 | Construction of roadbed and bridge wingwalls | Target achieved | Construction of roadbed done and bridge wingwalls done | None | None | Site establishment report, project progress report, handover report | TECH | 74
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct a new bridge at Mudimeli by 2018 | N/A | Mudimeli bridge completed by 2018 | Mudimeli bridge | Construction of Mudimeli bridge | Makhado Municipality | MIG | 5 758 786. - |  | Development of specifications, Advertisement for Contractor. | Target not achieved | Development of specifications done, Advertisement for Contractor not done | Delays on the review of specification by AG | Advertisement to be done during secon quarter | Specifications, advertisement, appointment letter, project progress report | TECH | 75
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads abd bridge projects by 30 June 2016 | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access roaGombiti,Tshivhuyuni,Muwaweni to Mphage road completed | Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access roaGombiti,Tshivhuyuni,Muwaweni to Mphage road | Planning of new road/bridges | Makhado Municipality | MIG | 1 600 000 |  | Advertisement for appointment of Consulting Engineers. | Target not achieved | Advertisement for appointment of Consulting engineer not done | Delays on the review of specification by AG | Advertisement to be done during second quarter | Advertisement copy, appointment letter, design report. | TECH | 76
Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Upgrading of Vuwani sports facilities | Upgrading of Vuwani sports facilities | Makhado Municipality | MIG | 2492678 | 957943.1132 | Planting of grass Construction of offices and change rooms | Target not achieved | Planting of grass not done Construction of offices and change rooms is in progress | Delays in terms of community protest | The project to be completed during second quarter | Project progress report, handover report | TECH | 77
Sports Facilities | Accessible basic and infrastructure services | To construct concrete palisade by 30 June 2016 | N/A | Provision of concrete palisade Waterval completed | Construction of concrete palisade at Waterval stadium | Construction of concrete palisade at Waterval stadium | Makhado Municipality | MIG | 800000 | 0 | Advertisement for appointment of Consulting Engineers. | Target not achieved | Advertisement for appointment of Consulting Engineers not done | Review the scope of work | Advertisement for appointment of Consulting Engineers to be done during second quarter | Advertisement copy, appointment letter, design report. | TECH | 78
Sports Facilities | Accessible basic and infrastructure services | To construct ablution facility by 30 June 2016 (Waterval Stadium) | N/A | Provision of Waterval stadium ablution facility completed | Construction of ablution facility at Waterval stadium | Construction of ablution facility at Waterval stadium | Makhado Municipality | MIG | 300000 | 0 | Advertisement for appointment of Consulting Engineers. | Target not achieved | Advertisement for appointment of Consulting Engineers not done | Review the scope of work | Advertisement for appointment of Consulting Engineers to be done during second quarter | Advertisement copy, appointment letter, design report. | TECH | 79
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing | Makhado Municipality 2 per region | MIG | 2000 000.00 | 0 | Advertisement for appointment of Contractors | Target not achieved | Advertisement for appointment of Contractors not done. | Corfirmiation of site | Advertisement for appointment of Contractors to be done during second quarter | Advertisement copy, appointment letter,project progress report, handover report | TECH | 80
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Fencing Vuwani Cemetery | Fencing Vuwani Cemetery | Makhado Municipality | Income | 300000 | 0 | Advertisement for appointment of Contractors | Target not achieved | Advertisement for appointment of Contractors not done. | Delay by officials to start with the project | To be done in the second quarter | Advertisement copy, appointment letter,project progress report, handover report | TECH | 81
Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | N/A | Vuwani cemetry Ablution Facility completed | Vuwani Cemetery (Toilet) | Vuwani Cemetry (Toilet) | Makhado Municipality | Income | 70000 | 0 | Advertisement for appointment of Contractors | Target not achieved | Advertisement for appointment of Contractors not done. | Delay by officials to start with the project | To be done in the second quarter | Advertisement copy, appointment letter,project progress report, handover report | TECH | 82
Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | N/A | Graveyard fencing completed | Fencing grave yard +sliding gate(Dzanani cemetery) | Fencing grave yard +sliding gate(Dzanani cemetery) | Dzanani township | Income | 300000 | 0 | Advertisement for appointment of Contractors | Target achieved | Advertisement for appointment of Contractors is done | None | None | Advertisement copy, appointment letter,project progress report, handover report | TECH | 83

## MFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Project Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End date | 1st Q Target | Performance Remarks (Target achieved/Target not achived) | Actual Performance Notes | Challenges | Intervention | Portfolio Of Evidence | Dept | Indicator No
6. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Capture spending on capital project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 163938800.12 | 31224893 | 1/7/2015 | 30/6/2016 | 10% | Target achieved | 19% 31224893 capital budget spent | None | None | Quarterly Financial Report | MM and All Directors | 84 | 7539142
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Capture spending on MIG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 112264000 | 22632052.07 | 1/7/2015 | 30/6/2016 | 10% | Target achieved | 20% 22632052 MIG spent | None | None | Quarterly Financial Report | MM | 85 | 5690000
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Capture spending on INEP project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 17000000 | 4620047.18 | 1/7/2015 | 30/6/2016 | 10% | Target achieved | 27% 4620047 INEP spent | None | None | Quarterly Financial Report | MM | 86 | 0.75473
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Capture spending on FMG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Income | 1600000 | 390280.83 | 1/1/2016 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Expenditure Report | B&T | 87
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Collection of payment for services such as electricity, property rates, refuse removal | Makhado Municipality | Income | 342227123 | 304582139.47 | 1/7/2015 | 30/6/2016 | 20% | Target achieved | 89% 304582139.47 revenue collected | None | None | Section 71 report (c1 schedule) | B&T | 88
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Send the policies for inputs by other department. Present the draft review to management. Submit to council for approval. | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 89
Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to council | Draft budget | Collect budget from departments, Consolidate the budget, Present the draft to management, Submit to council for approval | Makhado Municipality | Income | Operational | Operational | 1/1/2016 | 31/3/2016 | N/A | N/A | N/A | N/A | N/A | Draft budget and Council Resolution | B&T | 90
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget was submitted to council | Final budget submitted to council | Final budget | Take the draft budget for public participation with the IDP. Incorporate inputs and submit the budget for final approval | Makhado Municipality | Income | Operational | Operational | 1/4/2016 | 31/5/2016 | N/A | N/A | N/A | N/A | N/A | Final budget and Council Resolution | B&T | 91
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2015 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Compile the financial statement. Review the compiled financial statement. Present to management meeting. Submit to AG for auditing. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 31/8/2015 | Financial statements compiled and submitted to AG | Target achieved | Financial statements were compiled and submitted to AG by 31 of August 2015 | None | None | Copy of Financial statements | B&T | 92
Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Section 71 report submission | Compile the section 71 report. Submit to treasury within 10 days after month end. Submit to council for approval. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 3 | Target achieved | 3 section 71 reports were compiled and submitted to treasury within 10 days after month end and it was submitted to council for approval. | None | None | Copy of acknowledgement of receipt by Treasuries | B&T | 93
Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Tender adjudication | Set date for adjudication committee. Adjudicate tenders within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Target achieved | 88.9% (8/9) tenders warded within 90 days | Delays in committee sitting | Stick on the schedule fo committee sitting | Monthly Tender Reports | B&T | 94
Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | Quotations | Set date for quotation committee. Assess the quotation within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of quotations processed/# of quotations received) | Target achieved | 86% (72/84 )quatations processed within 18 days | Delays in committee sitting | Stick on the schedule fo committee sitting | Quotations Report | B&T | 95
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Asset Register | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Target achieved | 3months updated reports -acquisitions, Bar code and capture into the asset register. | None | None | Schedules of Asset Register movement | B&T | 96

## LED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End Date | 1st Q Target | Performance Remarks (Target achieved/Target not achived) | Actual Performance Notes | Challenges | Intervention | Portfolio Of Evidence | Dept | Indicator No
7. LOCAL ECONOMIC DEVELOPMENT
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Community works programme, Expanded public works programme, Community projects | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP | 97
Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2015 | N/A | Development of Makhado information and recreational centre completed | Makhado N1 Information and Caravan Recreational/Entertainment centre | Advertisement of the project. Evaluation and Adjudication, Appointment of a contractor. | Makhado Municipality | Income | 500000 |  | 01/01/2016 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, Appointment letter (contrcator) | DEVP | 98
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2015 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Identify the officials to serve Host Makhado annual show | Makhado Municipality | Income | 159300 |  | 1/7/2015 | 30/9/2016 | Host official opening and the Three Days Makhado Annual Show. | Target achieved | The opening of the show has been done.The three day Makhado Annual Show has been hosted | N/A | N/A | Annual Show Report and Audited Financial Statements | DEVP | 99
Local Economic Development | Invest in local economy | # of LED projects supported 30th June 2014 | 9 | 6 | LED Strategy | Community works programme, Transnet/Furniture, Rural Farmers (tractor landing), Salaunavhe Poultry farm, Local Builder Training (NHBRC), Dzanani Informal traders facility | Makhado Municipality | Income | Operational | Operational | 1/7/2015 | 30/9/2016 | N/A | N/A | N/A | N/A | N/A | LED strategy implementation report | MM and DEVP | 100

## GGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location | Funding Source | Budget 15/16 R'000 | Expenditure | Start Date | End date | 1st Q Target | Performance Remarks (Target achieved/Target not achived) | Actual Performance Notes | Challenges | Intervention | Portfolio Of Evidence | Dept | Indicator No
8. GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Risk Management | Good governace and Administrative Excellence | To cordinate 13 risk management activities by 30 June 2016 | 13 activities were cordinated | 13 risk activities cordinated | Risk Management project | Facilitate and coordinate risk management meetings | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 2 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Risk Management Committee Meeting held) | Target Not Achieved | Quarterly Strategic Monitoring Risk Report developed and Risk Committee meeting not held. | Unavailability of the Chairperson | N/A | Attendance register, Minutes and Programme | MM | 101
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of cases attended/# of cases reported) | Target Achieved | No case of Fraud or Corruption received | None | None | Case Register | MM | 102
Public Participation | Good governace and Administrative Excellence | To develop the public participation by 31 March 2016 | No policy | Public Participatuion policy approved by Council | Public Participation Policy | Compile Public Participation Policy and submit to Council for approval | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 31/3/2016 | Compile public participation policy and submit to Council for approval of Draft Policy | Target not Achieved | The Draft public participation policy has been done. | There was an advancement of Council meeting | The draft public participation policy to be submitted to Council by December 2015 | Approved draft policy Notice for the meeting Programmes and attendance register Final approve policy | CORP | 103
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 3o June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 38 wards | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Target Achieved | 114 ward committee meetings were held and submission of quarterly ward committees' report to Council was done. | None | None | Minutes, Attendance register, Ward committee quarterly report | CORP | 104
Public Participation | Good governace and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | 2 | 2 | Training of ward committees | Arrange and coordinate training event of all ward committees for at least 2 events | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Approval of the memorandum by MM (1st training) | Target Achieved | Approval of the memorandum by MM (1st training) was done | None | None | Training attendance register; training curriculum | CORP | 105
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 6 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool Quarry Pound Street and diverse Financial Hawkers and Market | Makhado Municipality | Income | 1/7/2015 |  | 01/07/2015 | 30/06/2016 | Development of the 6 draft policies | Target Achieved | 6 draft by laws has been developed i.e Swimming pool Quarry Pound Street and diverse Financial Hawkers and Market | None | None | 6 draft policies Council resolution Invitations, attendance registers, Final council resolutions and Promulgation notice for by laws | CORP | 106
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality | Income | OPEX | OPEX | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM | 107
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality | Income | OPEX | OPEX | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM | 108
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Implementation of the Approved Internal Audit Plan | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of projects executed/# of projects in the action plan) | Target achieved | 100% achievement. Two (2/2) projects planned for 1st quarter completed. - PMS quarter 4 review - Security Management Review | None | None | Internal Audit report to Audit and Performance Audit Committee | MM | 109
Internal Auditing | Good governace and Administrative Excellence | % implementation of the AG(SA) action plan by 30 June 2016 | 80% | 100% | AG(SA) action plan | Implementation of the AG(SA) action plan | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Progress report | All departments | 110
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | 7 | 7 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 2 | Target achieved | Two (2) Audit and Performance Audit Committee meeting held on 22 July and 21 August 2015. | None | None | Minutes, Attendance register, invitations | MM | 111
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | 4 | 4 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 x Audit and Performance Audit Committee Report for 4th quarter was developed and submitted to Council. | None | None | Council resolution, Attendance register | MM | 112
Internal Auditing | Good governace and Administrative Excellence | # of Audit Steering Committee meetings held by 30 June 2016 | 8 | 8 | Audit Steering Committee | Organize Audit Steering Committee meetings | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 2 | Target achieved | Two (2) Audit Steering Committee meetings held on 10 and 22 September 2015 | None | None | Minutes, Attendance register, invitations | MM | 113
Internal Auditing | Good governace and Administrative Excellence | # of OPCA meetings held by 30 June 2016 | 6 | 6 | Operation Clean Audit (OPCA) | Organize OPCA meetings | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Minutes, Attendance register, invitations | MM | 114
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 2 | 2 | IAA and APAC Assessment report | Organize IAA and APAC Assessment report and submit to council | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | IAA and APAC Assessment reports was done and submitted to council | N/A | N/A | Report, Council Resolution | MM | 115
Information Technology | Good governace and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Manual system | Computerized call center system | Upgrade municipal call center | Upgrade municipal call center from manual system to computerized logging, recording and referencing system and audio recording system according to needs of business units Phase 1 2015/2016 - the logging and referencing system Phase 2 - Audio recording system for 2016/2017 | Civic Center | Income | R3000,000 | 0 | 1/7/2015 | 31/3/2016 | Request for proposals for call and recording | Target achieved | Request for proposals for call and recording was done | None | None | Advertisement for RFP | CORP | 116
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 december 2015 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Increase speed of server output to networks for data transfer between workstations and servers | Civic Center and regional offices | Income | R200,000 | 0 | 1/7/2015 | 31/3/2016 | Call for quotations and award the project | Target achieved | Call for quotations and awarding of the project was done | None | None | Orders, Payment certificate and intallation report | CORP | 117
Information Technology | Good governace and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Phase 1 done | Complete server upgrade project | Upgrade of servers | Complete upgrade of servers - expansion of data centre server | Civic Center | income | R200,000 | 0 | 1/7/2015 | 31/3/2016 | Call for quotations and award the project | Target achieved | Call for quotations and awarding of the project was done | None | None | Appointment letter, Project agreement, installation report and payment certicate | CORP | 118
Information Technology | Good governace and Administrative Excellence | To upgrade the internet dataline by 31 March 2016 | Existing dataline too slow | Internet dataline upgraded | Internet dataline upgrade | Upgarde the internet dataline to optimise speed for offsite backups and internet use. (Changed from Upgrade of TMS) | Civic center | Income | R150,000 | 0 | 1/7/2015 | 31/3/2016 | Memorandum approval by the MM in terms TELKOM quotations | Target achieved | Memorandum approval by the MM in terms TELKOM quotations was generated | None | None | Approved memorandum, TELKOM agrement, Close out report, Proof of payment | CORP | 119
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Upgrade server room | Upgrade of server room by removing carpets and workstation equipment | Civic Center | Income | R70,000 | 0 | 1/7/2015 | 31/3/2016 | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business | Target not achived | Memorandum approval by the MM to hire PINACLE AFRICA for dismatling of envirorac and UPS without distrupting business not generated | The amount budget for the project was used for the REPLACEMENT of the UPS | None | Approved memorandum, Written propoal, wayforward outcomes | CORP | 120
Information Technology | Good governace and Administrative Excellence | To procure video editing software by 31 December 2015 | N/A | Procure video editing software | Procure video editing software | Procure Video Editing software suitable for use by business process owner | Civic Center | Income | R10,000 | 0 | 1/7/2015 | 2015-01-12 | Call for quotations | Target achieved | Call for quotations was done | None | None | Appointment letter, Installation, report; payment certificates, | CORP | 121
Information Technology | Good governace and Administrative Excellence | To procure ICT office equipment 31 March 2016 | 2014/15 critical needs only | According to needs analysis | Procure ICT office equipment | Procure laptops, computers, printers and desktops according to accurate needs analysis | Civic Center | Income | R200,000 | 0 | 1/7/2015 | 31/12/2015 | Memorandum to MM for approval to standardise equipment and suace a single service provider registered in the field. | Target achieved | Memorandum to MM was generated for approval to standardise equipment and suace a single service provider registered in the field. | None | None | Appointment letter, Orders, payment certificates and Asset Register | CORP | 122
Information Technology | Good governace and Administrative Excellence | To procure hand held communication radios 30 September 2015 | N/A | 2 | Hand held communication radios | Procure two (2) hand held communication radios for registry staff to communicate | Civic Center | Income | R10,000 | 0 | 1/7/2015 | 30/9/2015 | Call for quotations and procure | Target achieved | Call for quotations and procurement were done | None | None | Appointment letter, payment certificates, | CORP | 123
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 3 Council meeting were held | None | None | Minutes, Attendance register, notice of invitations. | CORP | 124
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 6 | Target achieved | 6 Executive Committee Meetings were held | None | None | Minutes, Attendance register, notice of invitations. | CORP | 125
Communication | Good governace and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | N/A | 2 | Television sets | Procure and install television sets in the Office of the Speaker and the Office of the Chief Whip | Civic Center | Income | R20,000.00 | 0 | 1/7/2015 | 30/9/2015 | Call quotations and procure | Target achieved | Call quotations and procurement ere done | None | None | TVs and payment certificates | CORP | 126
Communication | Good governace and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | N/A | 2 | Decoders | Procure and install decoders for DSTV in the Office of the Speaker and the Office of the Chief Whip | Civic Center | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | Call quotations and procure | Target achieved | Call quotations and procurement were done | None | None | Decoders and payment certificates | CORP | 127
Communication | Good governace and Administrative Excellence | To procure 2 X radios of regional broadcasting stations by 30 June 2016 | N/A | 2 | Radios | Procure radios for regional broadcasting services that also have a recording function | Civic Center | Income | R800.00 | 0 | 1/7/2015 | 30/9/2015 | Call quotations and procure | Target achieved | Memo to procure radio's has been submitted to SCM for further processing and the quatations has been received | None | None | Radios and payment certificates | CORP | 128
Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Reviewed Bathopele service standards | Review the 2014/15 ed Makhado Bathopele Service Standards and submit to Council for approval | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Distribute for comments of all departments | Target achieved | Distribution for comments by all departments was done | None | None | Approved 2015 Batho Pele Service Standards | CORP | 129
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Comprehensive website policy | Develop website policy for approval by Council | Civic Center | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | Submit to Council for approval | Target not achieved | The draft policy is developed but not submitted to Council. | There was an advancement of Council meeting | To submit the draft policy to Council | Council approval of policy | CORP | 130
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target not achieved | The approval to conduct the public participation by MM was approved | Unvailability of the Mayor | To be held during October 2015 | Attendance register and Programme | CORP | 131
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Imbizo Feedback Session | Giving Feedback to community on service delivery issues raised during 2014/2015 financial year | Makhado Municipality | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | Target not achieved | Consultation with the members of the public not done | Unvailabi;ity of the Mayor | To be held during October 2015 | Attendance register and program | CORP | 132
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework by 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | Income | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Stakeholders Management Framework reviewed | Target achieved | Stakeholders Management Framework was developed | None | None | Approved Stakeholders management Framework and council resolution | CORP | 133
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | Income | Income | OPEX | OPEX | 1/7/2015 | 30/06/2016 | Communications Strategy reviewed | Target achieved | Communoication strategy was reviewed and submitted to Council for Adoption | None | None | Approved Communication strategy and council resolution policy and council resolution | CORP | 134