## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
ANNUAL PERFORMANCE
REPORT
2015/2016
SECTION 46 OF MSA

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vison and Mission
3. Departments
4. HIGHER LEVEL SDBIP
4.1. Municipal Transformation and Organisational Development
4.2. Baisc service Delivery
4.3. Local Economic Development
4.4. Municipal Finance Management and Viability
4.5. Good Governance and Public Participation
5. LOWER LEVEL SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. SERVICE PROVIDER PERFORMANCE
6. CONCLUSION

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The financial year 2015/2016 has recorded crucial administrative and service delivery highlights which will be reflected in this Annual Performance Report. The report present the achievements and challenges for the year under review in terms of the SDBIP targets. While accepting the challenge regarding the regress in terms of audit opinion from Unqualified to Qualified in the 2014/2015, the municipality is pleased to indicate that on audit of predetermined objectives or performance information, an unqualified outcome has been achieved in all audited priority areas. This confirms the municipality’s effectiveness in monitoring and evaluation of the service delivery performance. It further confirms Makhado Municipality’s seriousness in achieving its vision, mission and strategic objectives.
Section 46 (1) of MSA state that a municipality must prepare for each financial year an annual report consisting of (a) a performance report reflecting— (i) the municipality’s, and any service provider’s, performance during that financial year, also in comparison with targets of and with performance in the previous financial year; (ii) the development and service delivery priorities and the performance targets set by the municipality for the following financial year; and (iii) measures that were or are to be taken to improve performance; (b) the financial statements for that financial year prepared in accordance with the standards of generally recognised accounting practise referred to in section 89 of the Public Finance Management Act, 1999 (Act No. 1 of 1999); (c) an audit report on the financial statements and the report on the audit performed in terms of sec[ion 45(b); and (d) any other reporting requirements in terms of other applicable legislation. A municipality must table its annual report within one month of receiving the audit report referred to in subsection (1)(c). (3) (a) The municipal manager must— (i) by prior notice in the media, inform the local community of the meeting or meetings of the council at which the municipality’s annual report is tabled or discussed, which meetings must be open to the public; (ii) give written notice of such meetings to the Auditor-General and the MEC for local government in the province; (iii) submit copies of the minutes of those meetings to the Auditor-General and the MEC for local government in the province; (b) Representatives of the Auditor-General and the MEC for local government in the province are entitled to attend and to speak at such meetings, and the municipal manager must be available to respond to questions related to the annual report. (4) The municipality must adopt its annual report, and within 14 days (a) make copies of the report accessible to the public, interested organisations and the media, free of charge or at a reasonable price; and (b) submit a copy of the report t (i) the MEC for local government in the province; .- (ii) the Auditor-General; and (iii) such other institutions as may be prescribed by regulation,

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## HIGH LEVEL SDBIP
4. HIGHER LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets | Start Date | End Date | Location | Ward/Dept. | Funding Source | Budget 15/16 R'000 | Adjustment budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio Of Evidence | Dept.
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP Review | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | 1/7/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target achieved | IDP review for 2016/2017 completed and approved by Council | None | None | Council resolutions, Draft IDP, Attendance register, Invitations for strategic plan, IDP Consultation attendance register. | MM
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | 1/4/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target achieved | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | None | None | Signed SDBIP | MM
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2016 | Training | 114 | 135 | 1/4/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target achieved | 147 | None | none | Proof of attendance | CORP
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2016 | Training | 61 | 16 | 1/4/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target achieved | 16 councilors were trained | None | none | Proof of attendance | CORP
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Organogram review | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | 1/7/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target achieved | Adopted by Council | none | none | Minutes and attendance register, Council resolutions, | CORP
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | Recruitment in terms of EE Plan | 3 | 4 | 1/7/2015 | 30/6/2016 | Makhado Municipality | N/A | Income | Operational | Operational | Target not achieved | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Appointment letters | CORP
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | Special Programs | 49 events done in 2014/15 | 43 for 2015/16 | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target achieved | 48 events was done | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2016 (Dzanani) | Street Naming (Dzanani) | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | 1/7/2015 | 30/6/2016 | Makhado Municipality | 33 | Income | Operational | Operational | Target not achieved | Service provider appointed delayed in terms of completing the project | Delay by the appointed service provider | Follow up with the service provider to complete printing of street name plates and poles to enable the municipality to install | Expenditure Report | DEVP
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | Waste Management | 46637 | 19149 | 1/7/2015 | 30/6/2016 | Makhado Town, Tshikota Township, Vleifontein, Waterval Township, Dzanani township, Vuwani Township, Kutama-Sinthumule Area, Brambos | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | Target achieved | 19149 | None | None | Proof of collection from the affected stakeholders. | MM and COMM
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2016 | Development of Parks | 2 | 3 | 1/7/2015 | 30/6/2016 | 5047 park, Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 12000000 | Target achieved | 3 | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2016 | Electrification of households | 1047 | 1180 | 1/7/2015 | 30/6/2016 | Magau, Tshiozwi, Ramantsha, Madodonga, Mamburu, Makushu, Wisagalaza, Sukani, Mamburu, Gogobole, Tshivhulana, Ratombo, Freedom, Lusaka, Tshivhuyuni. | Ward 23,25,03 | INCOME | 21824299 | 22199786 | Target achieved | 746 | 332 connections were not done (30 at Makushu, 286 not done at Wisagalaza) | None | Proof of connections to targeted households | MM and TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads upgraded from gravel to tar/paving by 30 June 2016 | Upgrading of roads | 26km | 18.9km | 1/7/2015 | 30/6/2016 | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 79361617 | Target achieved | 18.9km | 21.9km roads upgraded from gravel tar/paving | None | Project progress report, Certificate of completion | TECH
Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | Upgrading of Vuwani sports facilities | N/A | Upgrading of Vuwani sports facilities completed | 1/7/2015 | 30/6/2016 | Makhado Municipality | Ward 3 | MIG | 2492678 | 4492677.57 | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/17 | Project progress report, handover report | TECH
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | Planning for Waterval sports facility. | N/A | Planning for Waterval sports facility completed. | 1/7/2015 | 30/6/2016 | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 | Target achieved | Design completed and advertised for appointment of contractors | None | None | Advertisement copy, appointment letter, design report. | TECH
Building and Construction | Accessible basic and infrastructure services | # of graveyards to be developed by 30 June 2016 | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | 1 | 10 | 1/7/2015 | 30/6/2016 | Graveyard fencing (Tshituni Mawoni, Madodonga, Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein, Vuwani, Dzanani) | Ward 35, 25, 1,12,8,27,32,20 | MIG | 26700000 | 26700000 | Target not achieved | 4 graveyards were developed (Madodonga, Tshivhuyuni, Tshituni, Dzanani) | 5 graveyards were not fenced due to financial constraints and Contractor appointed. No progress on site | Tender advertised for graveyards in 2016/17 FY | Advertisement copy, appointment letter, project progress report, handover report | TECH
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Financial Statements | Sound Financial Management and viability | To obtain unqualified audit opinion by 31 December 2015 | Auditing of financial statements | Unqualified audit opinion | Unqualified audit opinion obtained | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | N/A | 169,734,677.34 | Target not achieved | Qualified audit opinion | SCM ,Valuation roll community challenges Asset and revenue roads impairment | Compliance , improve methodology in impairment and completing the capturing of Coghsta outcome on valuation roll appeal hearing | AG Audit Report 2014/2016 | MM and All Directors
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | Capital Budget | 85% (Total budget spent/Total budget) | 90% (Total budget spent/Total budget) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | 163938800.12 | 169,734,677.34 | Target achieved | 94% of Capital budget spent. (159156491.4/169315416) | NONE | NONE | Quarterly Financial Report | MM and All Directors
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | MIG | 98% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | 112264000 | 112264000 | Target achieved | 100% of MIG spent (112264000) | NONE | NONE | Quarterly Financial Report | MM
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | INEP | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | 17000000 | 17000000 | Target achieved | 100% of INEP Spent (17000000) | NONE | NONE | Quarterly Financial Report | MM
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | FMG | 100% | 100% | 1/1/2016 | 31/3/2016 | Makhado Municipality | Administration | Income | 1600000 | 1600000 | Target achieved | 100% of FMG Spent (1600000) | NONE | NONE | Expenditure Report | B&T
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | Revenue Collection | 90% | 90% (308004300) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | 342227123 | 342227123 | Target achieved | 96% of Revenue collected (27850683.76/29114673.61%) | NONE | Move into restructured tariffs once energy audit is completed in municipality | Section 71 report (c1 schedule) | B&T
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created | LED job opportunities | 600 | 800 | 1/7/2015 | 30/06/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target achieved | 1600 LED job opportunities created | None | None | EPWP, CWP, and Community Projects reports | MM and DEVP
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governance and Administrative Excellence | # of risk activities coordinated by 30 June 2016 | Risk Management activities | 13 | 13 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | 13 risk activities were coordinated | None | None | Risk Management Register and Reports | MM
Policies and By Laws | Good governance and Administrative Excellence | # of by laws to be reviewed by 30 June 2016 | Reviewing of Municipal By-laws | 7 | 4 | 01/07/2015 | 30/06/2016 | Makhado Municipality | Administration | Income | 1/7/2015 | OPEX | Target achieved | 4 by laws were reviewed | None | None | Council resolutions, Copies of approved by laws. | CORP
Internal Auditing | Good governance and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Audit Charters | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | 1/4/2015 | 30/6/2015 | Makhado Municipality |  | Income | OPEX | OPEX | Target achieved | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | None | None | Council Resolution, Copy of the plan | MM
Information Technology | Good governance and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Upgrade of servers | Phase 1 done | Complete server upgrade project | 1/7/2015 | 31/3/2016 | Civic Center |  | income | R200,000 | 148958 | Target achieved | Server upgrade were completed | None | None | Appointment letter, Project agreement, installation report and payment certificate | CORP
Council Services | Good governance and Administrative Excellence | # of Council meetings convened by 30 June 2016 | Council meetings | 15 | 6 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | Thirteen (13) Council meetings were convened | None | None | Minutes, Attendance register, notice of invitations. | CORP
Communication | Good governance and Administrative Excellence | # of communication indicators/activities/projects implemented by 30 June 2016 | Communication projects | 5 | 5 | 1/7/2015 | 30/9/2015 | Civic Center | Ward 20 | Income | R20,000.00 | N/A | Target achieved | 5 communication indicators / activity /projects were implemented | None | None | TVs and payment certificates | CORP
Public Participation | Good governance and Administrative Excellence | # of imbizos convened by 30 June 2016 | Public Participation | 4 | 4 | 1/7/2015 | 30/6/2016 | Makhado Municipality |  | Income | OPEX | OPEX | Target achieved | 4 imbizos convened | None | None | Attendance register and Programme | CORP

## LMTOD
5. LOWER SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets | Start Date | End Date | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio Of Evidence | Dept.
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (LOWER SDBIP)
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2016 | Quarterly performance reports | 8 | 8 | 1/7/2015 | 30/6/2016 | Makhado Municipality | 21 | Income | Operational | Operational | Target achieved | 8 organisational performance reports developed and submitted to Council | None | None | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2016 (# of managers with signed performance agreements/# of managers appointed) | Performance agreements | 100% (3/3) | 100% (6/6) | 1/7/2015 | 30/6/2016 | Makhado Municipality | 21 | Income | Operational | Operational | Target achieved | 100% (6/6) Section 57 Managers signed performance agreements | None | None | Signed Performance Agreements | MM
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conducted by 30 June 2016 | Individual Performance Assessment | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | 1/7/2015 | 30/6/2016 | Makhado Municipality | 21 | Income | Operational | Operational | Target achieved | 4 section 57 managers individual assessment conducted | None | None | Scorecards, Attendance Register | MM
Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2016 | Personnel Recruitment | 67 employees appointed | 30 | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Target not achieved | The recruitment process was done up to receiving application. 25 Employees appointed as roll over from 2014/2015 FY. 8 Interns were advertised and appointed | Adjusted during budget adjustment due to MEC ruling due to redemarcation of municipal boundaries in Vhembe District | Adjusted during budget adjustment due to MEC . The exemption was requested to fill the critical post which was not approved | Adjusted during budget adjustment due to MEC declaration | CORP
Human Resources and Organizational Development | Invest in human capital | # of employee assistance programmes events conducted by 30 June 2016 | Employee Assistance Campaigns | 6 events | 6 events | 1/7/2015 | 30/6/2016 | Makhado Municipality | 21 | Income | Operational | Operational | Target achieved | 6 employee assistance programmes events were conducted | None | None | Invitations, attendance registers and close-out report | CORP
Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | Development of 3 outstanding HR policies | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | 1/7/2015 | 30/6/2016 | Makhado Municipality | 21 | Income | Operational | Operational | Target achieved | Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy scheduled to be adopted by Council on the 14th July 2016 | None | None | Exco Agenda of 404th meeting for 23 June 2016 with draft Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | External Bursary Award | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target achieved | 15 bursaries were awarded | None | None | Advert, List of qualifying leaners and Letters of bursary awards | CORP
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | Permission to Occupy | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (35/35 of application received/(35/35 of application attended to within 90 days). | None | None | Site inspection report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | Housing Coordination | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (383/383 of housing queries attended within 30 days/# of received) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2016 (# of building plans assessed/# of building plans received) | Building Plans | 100% processed | 100% | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% processed | None | None | Building plans register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2016 (# of applications processed/# applications received) | Zoning of land | 100% processed | 100% (# of applications processed/# applications received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (53/53 of applications processed/53/53 applications received) | None | None | Zoning certificates issued | DEVP
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2016 (# of applications processed/# applications received) | Rezoning of land | 100% processed | 100% (# of applications processed/# applications received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (102 of applications processed/102/102 applications received) | None | None | EXCO resolutions | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | Land Use Management | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (79/79 of application for land use rights inspection conducted within 14 days/79/79 of application received) | None | None | Site inspection report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2016 (# of applications processed/# of applications received) | Occupancy of land | 100% processed | 100% (# of applications processed/# of applications received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (32/32of applications processed/32/32 of applications received) | None | None | Copy of occupancy certificates issued | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | Pegging Applications | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (203/203 of applications processed/203/203 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | Demarcation of sites | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (58/58 of applications processed/58/58 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | Property application | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (17/17 of applications processed/17/17 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | Property application | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (174/174 of applications processed/174/174 of applications received) | None | None | Bookings register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | Land Claims | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (1/1of queries processed/1/1 of queries received) | None | None | Correspondence letters and emails. | DEVP
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | By Law Enforcement | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 1/1/2016 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (38/38 of contravention notices issued within 5 days/38/38 of contravention identified) | Continuation of illegal activities by clients | Continuous involvement with legal division to institute legal proceedings | Duplicate notices | DEVP
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2016 | Routine Inspection | 240 | 240 | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 299 routine inspection conducted | None | None | Inspection form, Register | DEVP
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | Site Inspection | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target Achieved | 100% (446/446 of site inspections conducted within 24 hours/446/446 of site inspections application received) | None | None | Inspection form, Register | DEVP

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets | Start Date | End date | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjusted budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio of Evidence | Dept.
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (LOWER SDBIP)
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Annual Revision of the Disaster Management Plan | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | 2015-01-07 | 30/06/2016 | Community Services - disaster Management Unit | N/A | Income | Operational | Operational | Target Achieved | Disaster Management Plan is reviewed and included to the IDP for 2016/2017 | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM
Library Services | Promote community and environmental welfare | To do designs for refurbishment of the library roof by 30 June 2016 | Designs for Refurbishment of library building | Roof damaged | Designs for Refurbishment of the library building completed | 2015-01-07 | 30/06/2016 | Community Services - Library Services Unit | Ward 20 | Income | 1000000 | 200000 | Target Achieved | Designs for Refurbishment of the library building is completed. | None | None | Project Progress report | TECH
Waste Management | Promote community and environmental welfare | To develop Landfill site and recycling centre by 30 June 2016 | Development of Landfill site Makhado + recycling centre | N/A | Landfill site Makhado + recycling centre completed | 2015-01-07 | 30/06/2016 | Tshikota | Ward 21 | MIG | 5 000 000.00 - | 5599366.72 | Target not achieved | Landfill site Makhado + recycling centre not completed. | Delays in terms of appointment of service provider. The tender was readvertised. The service provider started the project around June 2016 | Construction has started and the project to be completed during first quarter 2016/17 financial year | Approval memo, Specifications, Advertisement copy, Appointment letter, Project progress report | COMM
Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | Rehabilitation of the existing Landfill site (Vondelling) | N/A | Landfill site rehabilitation completed. | 2015-01-07 | 30/06/2016 | Makhado Municipality | 21 | INCOME | 4000000 | 3083000 | Target not achieved - Completion of the evaporation ponds and V-drains not done. Planting of vegetation and grass not done. The service provider has been appointed for the supplier tipper truck and excavator , for the supplier of the soil to cover the compacted waste body | Landfill site rehabilitation not completed. | Specification of the advertised tender has been revised and tenders were not responsive | The tender is readvertised and the contractor will start immediately after appointment. Take note that the old landfill can only be closed once the new one is completed | Project Progress Report. | TECH
Parks and Recreation | Promote community and environmental welfare | To develop 5047 Park by 30 June 2016 | Development of 5047 Park | N/A | Development of 5047 Park completed | 2015-01-07 | 30/06/2016 | 5047 Park | Ward 20 | INCOME | 700000 | 700000 | Target Achieved | Development of 5047 Park is completed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
Parks and Recreation | Promote community and environmental welfare | To pay the service provider for development of the N1 recreational park by 30 June 2016 (R436842.11) | Payment for Development of N1 recreational park | N/A | Payment of service provider for Development of N1 recreational park done (R436842.11) | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 21 | INCOME | 1000000 | 500000 | Target Achieved | The payment of service provider has been done for N1 recreational park (R436842.11). | None | None | Proof of payment | COMM
Parks and Recreation | Promote community and environmental welfare | To refurbish and upgrade Civic Centre Park+ Meerkat park by 30 June 2016 | Refurbishment and Upgrading of Civic Centre Park and Meerkat Park | N/A | Refurbishment and Upgrading of Civic Centre Park+Meerkat park completed | 2015-01-07 | 30/06/2016 | Civic Centre Park | Ward 20&21 | INCOME | 500000 | 500000 | Target achieved | Refurbishment and Upgrading of Civic Centre Park+Meerkat park is completed. | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
Electricity Provision | Accessible basic and infrastructure services | To connect 50 households at Magau by 30 June 2016 | Magau electrification | N/A | 50 households at Magau connected | 2015-01-07 | 30/06/2016 | Magau | Ward 23 | INCOME | 935201.32 (INCOME) 712 000 (INEP) | 935201.32 (INCOME) 712 000 (INEP) | Target achieved - 100 households were completed by the time the project start hence 100 was done. | 100 households at Magau connected | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 40 households at TSHIOZWI /GOGOBOLE by 30 June 2016 | TSHIOZWI & GOGOBOLE electrification | N/A | 40 households connected at TSHIOZWI /GOGOBOLE | 2015-01-07 | 30/06/2016 | Tshiozwi Gogobole | Ward 23 | INCOME | 2101576 | 2101576 | Target achieved | 93 households connected at TSHIOZWI /GOGOBOLE | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 96 households at Ramantsha/Riverside by 30 June 2016 | RAMANTSHA/RIVERSIDE electrification | N/A | 96 households at Ramahantsha /Riverside connected | 2015-01-07 | 31/03/2016 | RAMANTSHA/RIVERSIDE | Ward 23 | INCOME | 1281962 | 1281962 | Target Achieved | 96 households at Ramahantsha /Riverside connected | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 83 households at Madodonga/Manavhela by 30 June 2016 | MADODONGA electrification | N/A | 83 households at Madodonga/Manavhela connected | 2015-01-07 | 31/03/2016 | MADODONGA | Ward 25 | INCOME | 1681261 | 1681261 | Target Achieved | 91 households at Madodonga/Manavhela connected | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 120 households at Mamburu by 30 June 2016 | Mamburu electrification | N/A | 120 households at Mamburu connected | 2015-01-07 | 30/06/2016 | Mamburu | Ward 25 | INEP | 2250000 | 2250000 | Target achieved | 180 households at Mamburu connected | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 30 households at Makhushu by 30 June 2016 | MAKUSHU electrification | N/A | 30 households at Makhushu connected | 2015-01-07 | 30/06/2016 | MAKUSHU | Ward 25 | INEP | 490000 | 490000 | Target not achieved | 30 households at Makhushu not connected. Project commenced, contractor on site, materials on site. No construction. | Delay in submission of designs and establishment of new households during planning and design period. The actual required number of connections is 123 and costing approximately R3million rands. | Construction of the project has started. The project will be done by end of the first quarter 2016/2017 | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
Electricity Provision | Accessible basic and infrastructure services | To do designs for Vyeboom 2016/2017 electrification projects ) by 30 June 2016 | Designs for Vyeboom 2016/2017 electrification projects | N/A | Designs for Vyeboom 2016/2017 electrification projects completed | 2015-01-07 | 30/06/2016 | Vyeboom village | Ward 3 | INEP | 952500 | 952500 | Target achieved | Designs for Vyeboom 2016/2017 electrification projects completed and project was handed over to Eskom | None | None | Specifications, Advertisement, appointment letter, Designs, Minutes of technical forum meeting | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 3km Industrial line by 30 June 2016 | Upgrading 3km Industrial line | N/A | Upgrading 3km Industrial line completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 21 | INCOME | 250000 | 250000 | Target not achieved - Phase 1 is completed. About 30% of poles planted in ph2. No conductor strining no closing spans. | Upgrading 3km Industrial line not completed. | Labour unrest in Mar/Apr 2016. Due to time and financial constraints, Service provider could not be appointed to speed up the project. Funds were transferred to finance the EPWP workers who are on 12 months contract with the municipality | The project is budgeted again in the 2016/2017 financial year. | Designs, Appointment letter for labourers, Project progress report, | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 4.5km Shefeera Line by 30 June 2016 | Upgrade 4.5km Shefeera Line | N/A | Upgrade 4.5km Shefeera Line completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 21 | INCOME | 600000 | 512999 | Target achieved | Upgrade 4.5km Shefeera Line is completed | None | None |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To appoint the contractor for upgrade of Urban Substations by 30 June 2016 | Upgrade Urban Substations | N/A | Appointment of contractor and site handover. | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 20 | INCOME | 2500000 | 2500000 | Target achieved | Appointment of contractor and site handover was done. | None | None |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade 5km Mountain line by 30 June 2016 | Upgrading 5km Mountain line | N/A | Upgrading 5km Mountain line completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 30 | INCOME | 250000 | 250000 | Target not achieved | Upgrading 5km Mountain line not completed. | Labour unrest Mar/Apr. Due to time and financial constraints, SP could not be appointed to speed up the project. Funds were transferred to finance the EPWP workers who are on 12 months contract with the municipality | The project is budgeted again in the 2016/2017 financial year. |  | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute 2.2km Beaufort West line by 30 June 2016 | Upgrade and reroute 2.2km Beaufort West line | N/A | Upgrade and reroute 2.2km Beaufort West line completed | 2015-01-07 | 30/06/2016 | Beaufort West line | Ward 30 | INCOME | 1500000 | 1500000 | Target achieved | Upgrade and reroute 2.2km Beaufort West line is completed | None | None | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace oil circuit breaker by 30 June 2016 | Oil circuit breaker replacement | N/A | Replacement of oil circuit breaker completed | 2015-01-07 | 30/06/2016 | Main substation | Ward 21 | INCOME | 400000 | 400000 | Target achieved | Replacement of oil circuit breaker is completed | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | Substation channel cover replacements | N/A | Replacement of channel cover completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | All wards | INCOME | 0 | 0 | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | Standby (Backup) Electricity Power Generator-Dzanani | N/A | Standby generator installed | 2015-01-07 | 31/03/2016 | Dzanani | 33 | INCOME | 250000 | 250000 | Target Achieved | Standby generator s installed | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | % requested air conditioners replaced/installed by 30 June 2016 (# replaced/# requested) | Air Conditioners | N/A | 100% requested Air Conditioners replaced/installed | 2015-01-07 | 30/06/2016 | Municipal area | All municipal office | INCOME | 150000 | 450000 | Target achieved | 100% (27 replacement request done, 9 new installation done, 258 maintenance request done) | None | None | Orders, job cards, photos, invoices, payment certificates | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | CT VT Units 11kv & 22kv | N/A | CT VT Units 11kv & 22kv replaced | 2015-01-07 | 30/06/2016 | Makhado | All municipal areas | INCOME | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | TECH
Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming B9, T8, A21 and G23/24 by 31 March 2016 | Low voltage to medium voltage in Rural Farming B9,T8 and A21 | N/A | Low voltage to medium voltage in Rural Farming B9,T8 and A21 upgraded | 2015-01-07 | 30/06/2016 | Makhado | All municipal areas | INCOME | 250000 | 358000 | Target achieved | Low voltage to medium voltage in Rural Farming B9,T8 and A21 is upgraded | None | None | Project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | Mini Subs replacement | N/A | Mini Subs replaced | 2015-01-07 | 31/12/2015 | Makhado | All municipal areas | INCOME | 900000 | 444000 | Target Achieved | Mini Subs is replaced | None | None | Specification, orders, delivery notes | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | MV Cable 95mm 22kV replacement | N/A | MV Cable 95mm 22kV replaced | 2015-01-07 | 31/12/2015 | Makhado | All municipal areas | INCOME | 150000 | 117000 | Target Achieved | MV Cable 95mm 22kV is replaced | None | None | Specification, orders, delivery notes | TECH
Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | Recloser and controllers whole network purchase | N/A | Recloser and controllers whole network procured | 2015-01-07 | 30/06/2016 | Makhado | All municipal areas | INCOME | 700000 | 700000 | Target not achieved -Service provider appointed. No progress due to SP not able to supply anymore | Recloser and controllers whole network not procured | SP not able to supply equipment's anymore | Re-allocated for next financial year | Specification, orders, delivery notes, progress report, completion certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | Remote control of switch gear Tshipise & Levubu purchase | N/A | Remote control of switch gear Tshipise & Levubu procured | 2015-01-07 | 30/06/2016 | Makhado | All municipal areas | INCOME | 120000 | 180000 | Target achieved | Remote control of switch gear Tshipise & Levubu is procured | None | None | Specification, advertisement, appointment letter, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | Ring Main Units 11 kV ( RMU) purchase | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | 2015-01-07 | 31/03/2016 | Makhado | All municipal areas | INCOME | 300000 | 306740 | Target Achieved | Ring Main Units 11 kV ( RMU) is delivered and installed | None | None | Specification, order, delivery note, project progress report, payment certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter perimeter wall by 31 March 2016 | Standby quarter perimeter wall | N/A | Standby quarter perimeter wall completed | 2015-01-07 | 31/03/2016 | Makhado | All municipal areas | INCOME | 60000 | 300000 | Target Achieved | Standby quarter perimeter wall is completed | None | None | Specification, advertisement, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | Standby quarter guard room construction | N/A | Standby quarter guard room completed | 2015-01-07 | 30/06/2016 | Makhado | All municipal areas | INCOME | 250000 | 250000 | Target not achieved - Standy quarter guardroom at roof level | Standby quarter guard room not completed | Labour unrest and retrenchment of the municipal Builder | Project to be rolled over to 2016/17 FY | Specification, advertisement, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 471 households at Wisagalaza 2 & Chitasi village by 30 June 2016 | Wisagalaza 2 & Chitasi village electrification | Site establishment | Wisagalaza 2 & Chitasi village 471 households connection completed | 2015-01-07 | 30/06/2016 | Wisagalaza village | 8 | INEP | 7771500 | 8826487.19 | Target not achieved | 185 households at Wisagalaza 2 & Chitasi village connected. | None | None | Appointment letter, project progress report, completion certificate | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 87 households at SUKANI by 30 June 2016 | SUKANI electrification | N/A | Site handover to contractor, planting of poles. | 2015-01-07 | 30/06/2016 | SUKANI | Ward 8 | INEP | 1392000 | 1392000 | Target achieved | Site handover to contractor done , planting of poles done. | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 102 electricity at TSHIVHULANA by 30 June 2016 | TSHIVHULANA zone 5 electrification | N/A | Tshivulana 102 connections completed | 2015-01-07 | 30/06/2016 | TSHIVHULANA zone 5 | Ward 1 | /INCOME INEP | 1632000 | 0 | N/A | Adjusted during budget adjustment | Project taken over by Eskom | Adjusted during budget adjustment | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 150 households at Ratombo/ by 30 June 2016 | RATOMBO electrification | N/A | Stringing of MV and LV conductors done | 2015-01-07 | 30/06/2016 | RATOMBO | 32 | INEP /income | 1472000 | 1472000 | Target achieved | Stringing of MV and LV conductors done | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To connect 53 households at Freedom and Lusaka (Tshivhuyuni) by 30 June 2016 | Freedom and Lusaka (Tshivhuyuni) electrification | N/A | Site handover and planting of poles. | 2015-01-07 | 30/06/2016 | Freedom and Lusaka (Tshivhuyuni) | 12 | INEP | 1040000 | 1040000 | Target achieved | Site handover done and planting of poles completed. | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
Electricity Provision | Accessible basic and infrastructure services | To electrify Rabali Stadium by 30 June 2016 | Electrification Rabali Stadium electrification | N/A | Electrification Rabali Stadium facility completed | 2015-01-07 | 31/03/2016 | Rabali stadium | Ward32 | Income | 150000 | 150000 | Target Achieved | Electrification Rabali Stadium facility completed | None | None | Specifications, Advertisement, Appointment letter, delivery notes, | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Tshikota Access/Pretorius Street access road (6.5km) by 30 June 2016 | Upgrading of Tshikota access road/Pretorius street upgraded | Gravel road | Tshikota access road/Pretorius street upgraded | 2015-01-07 | 30/09/2015 | Makhado Municipality |  | MIG | 1936405 | 1793613.68 | Target achieved | Tshikota access road/Pretorius street is upgraded (6.5km) | None | None | Project progress report, Completion certificate, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Magau road (4.5km) phase 2 by 30 June 2016 | Magau road phase 1 construction | Gravel road | Magau road phase 2 completed | 2015-01-07 | 31/03/2016 | Magau | Ward 23 | MIG | 22000000 | 21848466.41 | Target achieved | Magau road phase 2 completed (4.5km) | None | None | Project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To pay the contractor for construction of Tshivhulana to Tshilaphala access road (4.5km) by 30 June 2016 (R2931397.97) | Tshivhulana to Tshilaphala access road construction | Payment outstanding | Payment of the contractor for Tshivhulana to Tshilaphala access road done | 2015-01-07 | 30/06/2016 | Tshivhulana to Tshilaphala | Ward 01 | MIG | 13976988.13 | 3000000 | Target Achieved | Payment of contractor for the construction of Tshivhulana to Tshilaphala access road done ((R2931397.97) | None | None | Proof of payment | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road(6.6km) by 30 June 2016 | Ledig road upgrading | Gravel road | Ledig road completed | 2015-01-07 | 31/12/2015 | Ledig | Ward 21 | MIG | 9387156 | 15403183.1 | Target Achieved | Ledig road completed | None | None | Site establishment report, project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road(3.5km) by 30 June 2016 | Robert Khoza /Chabani Bungeni road construction | N/A | Robert Khoza /Chabani Bungeni road completed | 2015-01-07 | 30/06/2016 | Robert Khoza /Chabani Bungeni road | Ward 13 | MIG | 23000000 | 19689296.81 | Target not achieved | Surfacing completed and project not handed over | Slow progress by the contractor | Construction is in progress. Kerbs and V-Drains are being done. Construction of the bridge and road is completed | Site establishment report, project progress report, handover report | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road(4.3km) phase 1 by 30 June 2016 | Tshivhazwaulu to Rasivhetshela road phase 1 construction | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 4 | MIG | 23811987.67 | 22420672.11 | Target achieved | (4.3km) Tshivhazwaulu to Rasivhetshela road phase 1 completed | None | None | Advertisement copy, appointment letter, design report. | TECH
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads and bridge projects by 30 June 2016 | Planning of Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 25, 25, 36,30,3,15,12, | MIG | 1 600 000 | 1 600 000 | Target achieved -Design completed and advertised for appointment of contractors | Planning done for the following roads: for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage. | None | None | Advertisement copy, appointment letter, design report. | TECH
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | Planning for Waterval sports facility. | N/A | Planning for Waterval sports facility completed. | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 | Target achieved | Planning for Waterval sports facility is completed. | None | None | Advertisement copy, appointment letter, design report. | TECH
Sports Facilities | Accessible basic and infrastructure services | To construct ablution facility by 30 June 2016 (Waterval Stadium) | Upgrading of Vuwani sports facilities | N/A | Provision of Waterval stadium ablution facility completed | 2015-01-07 | 30/06/2016 | Makhado Municipality | Ward 16 | MIG | 300000 | 0 | N/A | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Advertisement copy, appointment letter, project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct 8 graveyards fencing by 30 June 2016 | Graveyard fencing (Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | N/A | 8 Graveyards fencing completed | 2015-01-07 | 30/06/2016 | Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | Ward 35, 25, 1,12,8,27,32,20 | MIG | 2000000 | 2000000 | Target not achieved -only Three (3) graveyards (Madodonga, tshivhuyuni, Tshituni) were fenced due to financial constraints. | 8 Graveyards fencing not completed | Available budget could only cover 3 graveyards. | Project will be finalised in 2016/17. Tender advertised for 5 graveyards in 2016/17 FY | Advertisement copy, appointment letter, project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | Fencing Vuwani Cemetery | N/A | Graveyard fencing completed | 2015-01-07 | 30/06/2016 | Vuwani | Ward 3 | Income | 300000 | 300000 | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Material has been purchased and delivered. The project to be finalised in the first quarter of 2016/17 | Advertisement copy, appointment letter, project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | Vuwani Cemetery ( Toilet ) | N/A | Vuwani cemetery Ablution Facility completed | 2015-01-07 | 30/06/2016 | Vuwani | Ward 3 | Income | 70000 | 70000 | Target not achieved - Contractor appointed. No progress on site | Vuwani cemetery Ablution Facility not completed | Public protest/unrest | Material has been purchased and delivered. The project to be finalised in the first quarter of 2016/17 | Advertisement copy, appointment letter, project progress report, handover report | TECH
Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | Fencing grave yard +sliding gate(Dzanani cemetery) | N/A | Graveyard fencing completed | 2015-01-07 | 30/06/2016 | Dzanani township | Ward 35 | Income | 300000 | 300000 | Target achieved | Graveyard fencing is completed | None | None | Advertisement copy, appointment letter, project progress report, handover report | TECH

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets ( | Start Date | End date | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio Of Evidence | Dept.
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies review | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | 1/1/2016 | 30/6/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | Revenue enhancement policies was reviewed | None | None | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T
Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget | Draft budget was tabled to council | Draft budget tabled to council | 1/1/2016 | 31/3/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | Draft budget was tabled to council | None | None | Draft budget and Council Resolution | B&T
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget | Final budget was submitted to council | Final budget submitted to council | 1/4/2016 | 31/5/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | Final budget was submitted to Council | None | None | Final budget and Council Resolution | B&T
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2015 | Financial statements | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | 1/7/2015 | 31/8/2015 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | Financial statements was compiled and submit to AG | None | None | Copy of Financial statements | B&T
Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | Section 71 report submission | 12 | 12 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | 12 section 71 reports were submitted to Treasury within 10 days after the end of the month | None | None | Copy of acknowledgement of receipt by Treasuries | B&T
Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | Tender adjudication | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | 100/100 tenders adjudicated/# of tenders closed and due for adjudication) | None | None | Monthly Tender Reports | B&T
Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | Quotations | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target not achieved | 84/84 of quotations processed/# of quotations received) | DELAY S IN PROCESSING THEM | REGULAR MEETING FOR QUOTATION COMMITTEE | Quotations Report | B&T
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | Asset Register | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | Operational | Operational | Target achieved | GRAP compliant Asset Register was updated | None | None | Schedules of Asset Register movement | B&T

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets | Start Date | End Date | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio Of Evidence | Dept.
5.4. LOCAL ECONOMIC DEVELOPMENT (L0WER SDBIP)
Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2016 | Makhado N1 Information and Caravan Recreational/Entertainment centre | N/A | Development of Makhado information and recreational centre completed | 01/01/2016 | 30/06/2016 | Makhado Municipality | Ward 20 | Income | 500000 | 100000 | Target achieved | Development of specifications, Advertisement of the project. The project was completed on time at a cost of R498 000,00 | None | None | Specifications, Appointment letter (contractor) | DEVP
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2015 | Annual Show | Makhado annual show was hosted | Makhado annual show hosted | 1/7/2015 | 30/9/2015 | Makhado Municipality | Ward 20 | Income | 159300 | 159300 | Target achieved | Makhado Annual Show hosted | None | N/a | Annual Show Report and Audited Financial Statements | DEVP
Local Economic Development | Invest in local economy | # of LED projects supported by 30th June 2016 | LED Strategy | 9 | 10 | 1/7/2015 | 30/9/2016 | Makhado Municipality | All wards | Income | Operational | Operational | Target not achieved | 6 LED/community based poverty alleviation projects funded | Delay in supply chain processes | To finalise specifications and advertise on time to avoid delay in procurement of goods and services. | LED strategy implementation report | MM and DEVP

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Project Name | Baseline (2014/2015) | Annual Targets | Start Date | End date | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment Budget | Performance remarks | Actual performance | Challenges | Measures taken to improve/ proposed intervention | Portfolio Of Evidence | Dept.
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (LOWER SDBIP)
Fraud and Anti - Corruption | Good governance and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | 100% (1/1) | None | None | Case Register | MM
Public Participation | Good governance and Administrative Excellence | To develop the public participation policy by 31 March 2016 | Public Participation Policy | No policy | Public Participation policy approved by Council | 1/7/2015 | 31/3/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target not achieved | Public Participation on policy was not approved by Council | None | None | Approved policy Programmes and attendance register Final approve policy and advert for public comment | CORP
Public Participation | Good governance and Administrative Excellence | To coordinate 456 ward committee meetings by 3o June 2016 | Support services for monthly ward committee meetings | 456 | 456 | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | OPEX | OPEX | Target achieved | 456 ward committee meetings were coordinated | None | None | Minutes, Attendance register, Ward committee quarterly report | CORP
Public Participation | Good governance and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | Training of ward committees | 2 | 2 | 1/7/2015 | 30/6/2016 | Makhado Municipality | All wards | Income | OPEX | OPEX | Target achieved | 2 ward committee training were done | None | None | Training attendance register; training curriculum | CORP
Policies and By Laws | Good governance and Administrative Excellence | To review 6 by laws by 30 June 2016 | Reviewing of Municipal By-laws | 7 by laws reviewed | 4 by laws reviewed | 01/07/2015 | 30/06/2016 | Makhado Municipality | All wards | Income | 1/7/2015 | OPEX | Target achieved | 4 by laws were reviewed | None | None | 4 draft bylaws Provisional approved by Council , newspaper notice, attendance registers for public consultation, Final council resolutions and Promulgation notice for the 4 by laws in the provincial gazzete | CORP
Internal Auditing | Good governance and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Internal Audit 3 Year Plan | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | 1/4/2015 | 30/6/2015 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | Three year rolling Audit plan is approved by APAC | None | None | Copy of the plan | MM
Internal Auditing | Good governance and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | Internal Audit Plan | 100% | 100% | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target not achieved | 86% (12/14) Audit project performed | Delay in SCM processes to finalise the appointment of service provider | Appointment of service provider | Internal Audit report to Audit and Performance Audit Committee | MM
Internal Auditing | Good governance and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | Audit and Performance Audit Committee | 7 | 7 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | 100% (7/7) | None | None | Minutes, Attendance register, invitations | MM
Internal Auditing | Good governance and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | Audit and Performance Audit Committee Reports | 4 | 4 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | 100%(4/4) | None | None | Council resolution, Attendance register | MM
Internal Auditing | Good governance and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | IAA and APAC Assessment report | 2 | 2 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | (1/1) | None | None | Report, Council Resolution | MM
Information Technology | Good governance and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Upgrade municipal call center | Manual system | Computerized call center system | 1/7/2015 | 30/6/2016 | Civic Center | Administration | Income | R3000,000 | 0 | Target not achieved | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | CORP
Information Technology | Good governance and Administrative Excellence | To complete upgrade of network infrastructure by 31 December 2015 | Upgrade network infrastructure | Phase 1 done | Complete network upgrades | 1/7/2015 | 31/3/2016 | Civic Center and regional offices | Administration | Income | R200,000 | 159226 | Target achieved | Network upgrades were completed | None | None | Orders, Payment certificate and installation report | CORP
Information Technology | Good governance and Administrative Excellence | To upgrade the internet data line by 31 March 2016 | Internet data line upgrade | Existing data line too slow | Internet data line upgraded | 1/7/2015 | 31/3/2016 | Civic center | Administration | Income | R150,000 | R150,000 | Target achieved | Internet data line was upgraded | None | None | Approved memorandum, TELKOM agreement, Close out report, Proof of payment | CORP
Information Technology | Good governance and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Replace UPS in server room | Unacceptable standard of server room | Acceptable server room conditions | 1/7/2015 | 31/3/2016 | Civic Center | Administration | Income | R70,000 | 161816 | Target achieved | Acceptable server room conditions | None | None | Approved memorandum purchase order, signed service maintenance plan | CORP
Information Technology | Good governance and Administrative Excellence | To procure video editing software by 31 December 2015 | Procure video editing software | N/A | Procure video editing software | 1/7/2015 | 2015-01-12 | Civic Center | Administration | Income | R10,000 | 14500 | Target achieved | Video editing software was procured | None | None | Appointment letter, Installation, report; payment certificates, | CORP
Information Technology | Good governance and Administrative Excellence | To procure ICT office equipment 31 March 2016 | Procure ICT office equipment | 2014/15 critical needs only | According to needs analysis | 1/7/2015 | 31/12/2015 | Civic Center | Administration | Income | R200,000 | 155500 | Target not achieved | No ICT equipment was procured | Suitable service provide was not obtained | Review the approach of procuring ICT equipment | Quotation Committee minutes and non-compliance by their selected supplier which is in possession of SCM section | CORP
Information Technology | Good governance and Administrative Excellence | To procure hand held communication radios 30 September 2015 | Hand held communication radios | N/A | 2 | 1/7/2015 | 30/9/2015 | Civic Center | Administration | Income | R10,000 | R10,000 | Target achieved | 2 Radio and base radio was procured, installed and commissioned | None | None | Appointment letter, payment certificates, | CORP
Council Services | Good governance and Administrative Excellence | # of Council meeting convened by 30 June 2016 | Council meeting | 15 | 6 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | Thirteen (13) Council meetings were convened | None | None | Minutes, Attendance register, notice of invitations. | CORP
Council Services | Good governance and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | Executive Committee Meetings | 25 | 24 | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | Twenty four (24) Executive Committee meetings were convened | None | None | Minutes, Attendance register, notice of invitations. | CORP
Communication | Good governance and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | Television sets | N/A | 2 | 1/7/2015 | 30/9/2015 | Civic Center | Administration | Income | R20,000.00 | OPEX | Target achieved | 2 x television sets procured | None | None | TVs and payment certificates | CORP
Communication | Good governance and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | Decoders | N/A | 2 | 1/7/2015 | 30/9/2015 | Civic Center | Administration | Income | OPEX | OPEX | Target achieved | 2 X decoders by procured | None | None | Decoders and payment certificates | CORP
Communication | Good governance and Administrative Excellence | To procure 2 X radios of regional broadcasting stations by 30 June 2016 | Radios | N/A | 2 | 1/7/2015 | 30/9/2015 | Civic Center | Administration | Income | R800.00 | 2656 | Target achieved | 2 X radios of regional broadcasting stations procured | None | None | Radios and payment certificates | CORP
Communication | Good governance and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | Reviewed Bathopele service standards | 1 | Reviewed BathoPele Service Standards | 1/7/2015 | 30/6/2016 | Makhado Municipality | Administration | Income | OPEX | OPEX | Target achieved | Reviewed BathoPele Service Standards | None | None | Approved 2015 Batho Pele Service Standards | CORP
Communication | Good governance and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | Comprehensive website policy | N/A | Council approved website policy | 1/7/2015 | 30/9/2015 | Civic Center | Administration | Income | OPEX | OPEX | Target achieved | Website policy was approved by Council | None | None | Council approval of policy | CORP
Public Participation | Good governance and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | Imbizo Feedback Session | 1 | 1 | 1/7/2015 | 30/9/2015 | Makhado Municipality | All wards | Income | OPEX | OPEX | Target not achieved | Imbizo feedback session not convened | None availability of the Mayor | To be done during financial year 2016/17 | Attendance register and program | CORP
Public Participation | Good governance and Administrative Excellence | To review Makhado Stakeholders Management Framework BY 30 September 2016 | Review of Stakeholders Management Framework | Stakeholders Management Framework | Stakeholders Management Framework reviewed | 1/7/2015 | 30/9/2015 | Income | Administration | Income | OPEX | OPEX | Target achieved | Stakeholders Management Framework was reviewed | None | None | Approved Stakeholders management Framework and council resolution | CORP
Public Participation | Good governance and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Review of Communication Strategy | Communication Strategy | Communication Strategy reviewed | 1/7/2015 | 30/9/2015 | Income | Administration | Income | OPEX | OPEX | Target achieved | Communication Strategy was reviewed | None | None | Approved Communication strategy and council resolution policy and council resolution | CORP

## SERVICE PROV PERF 1516
Dept. | Tender number | Project name | Name of Service provider | Source of funding | Starting date | Completion date | Progress to date | Challenges and interventions | Assessment of service provider
(Scale 1-5) 1 - Poor 2 - Fair 3 -Average 4 - Good 5 - Excellent
[9 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
DDP | 37/2013 | Padkamp Town Establishment | Nhlatse Consulting | Income | July 2014 - June 2015 | 2015-06-15 | The project is at ninety percent (90%). Awaiting General plan from Surveyor General. | None | 4 | 4 | 4 | 5
| 46/2012 | Formalisation of 700 sites at Matshavhawe | Pieterse Dutoit & Associates Town and Regional Planners | Income | July 2014 - June 2015 | 2015-06-15 | The project is at ninety percent (90%). Awaiting General plan from Surveyor General. | None | 4 | 4 | 4 | 5
| 42/2012 | Demarcation of 100 sites at Tiyani &Ribungwani | Land Mark Consulting | Income | July 2014 - June 2015 | 2015-06-15 | The project is at ninety percent (90%). Awaiting General plan from Surveyor General. | None | 4 | 3 | 4 | 4
| 45/2012 | Demarcation of 200 sites at Hamasia Tshikwarani | Land Mark Consulting | Income | July 2014 - June 2015 | 2015-06-15 | The project is at ninety percent (90%). Awaiting General plan from Surveyor General. | None | 4 | 3 | 5 | 5
| 43/2012 | Demarcation of 300 sites at Muananzhele Communal Property Association | Vutsila Consulting | Income | July 2014 - June 2015 | 2015-06-15 | The project is at ninety percent (90%). Awaiting General plan from Surveyor General. | None | 4 | 3 | 4 | 4
| 29/2011 | Piesanghoek to Khunda Road | Tshashu Consulting Engineers | MIG | 2014-07-01 | 2016-01-30 | 91% complete | none | 4 | 4 | 3 | 5
| 23/2014 | Vuwani sports field | Thiko Consulting Engineers | MIG | 2014-10-30 | 2015-11-30 | 78% complete | none | 4 | 4 | 3 | 2
| 22/2014 | Vuwani sports field | Nduvho / Ddzindake JV | MIG | 2014-10-30 | 2015-11-30 | 78% complete | none | 3 | 4 | 4 | 2
| 20/2014 | Robert khoza to chavhani road | Mont Consulting Engineers | MIG | 2015-06-15 | 2016-03-30 | 68% complete | none | 5 | 4 | 4 | 5
|  | Robert khoza to chavhani road | Gorogang civil construction | MIG | 2015-06-15 | 2016-03-30 | 68% complete | none | 4 | 4 | 3 | 5
| 19/2014 | Madzuwa bridge and access road | Morula Consulting Engineers | MIG | 2015-04-01 | 2015-10-31 | 95% complete | none | 4 | 4 | 4 | 5
| 49/2014 | Madzuwa bridge and access road | Nkomazi / madevha JV | MIG | 2015-04-01 | 2015-10-31 | 95% complete | none | 3 | 3 | 4 | 3
| 33/2015 | Electrification of Mamburu | Machavi Bukuta Electrical | INEP | 2015-10-14 | 2016-06-30 | 100% complete | none | n/a | 4 | 4 | 4
| 33/2015 | Electrification of Ratombo | Brightside Electrical | INEP | 2015-10-14 | 2017-06-30 | 65% complete | none | n/a | 3 | 3 | 4
| 33/2015 | Electrification of Sukani | Kingki Electrical | INEP | 2015-10-14 | 2017-06-30 | 30% complete | late commencement | n/a | n/a | n/a | 3
| 33/2015 | Electrification of Freedom & Lusaka | Kingki Electrical | INEP | 2015-10-14 | 2017-06-30 | 30% complete | late commencement | n/a | n/a | n/a | 3
| 26/2015 | Electrification of Tshiozwi & Gogobole | Humphrey Electrical and Construction | INCOME | 2015-10-14 | 30/6/2017 | Work in progress | none | n/a | 3 | 3 | 2
| 25/2016 | Electrification of Magau/Makhitha/Tshikodobo/Zamekom | Madz Electrical | INCOME | 2015-10-14 | 30/6/2018 | 98% complete | none | n/a | 3 | 4 | 4
| 28/2015 | Electrification of Manavhela & Madodonga | Rivisi Electrical Contractors | INCOME | 2015-10-14 | 30/6/2019 | 100% complete | none | n/a | 4 | 4 | 4
| 27/2015 | Electrification of Ramahantsha & Riverside | Bvelela Engineering CC. | INCOME | 2015-10-14 | 30/6/2020 | 100% complete | none | n/a | 4 | 4 | 4
| 68/2015 | Mudimeli Bridge | Tshedza Consulting | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 5 | 5
| 69/2015 | Vuvha Access Road | Victory Development | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 4 | 5
| 70/2015 | Tshikwarani/Manavhela/Zamekomste Access Raod | Mont Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 5 | 5
| 71/2015 | Tshirolwe/Matsa/Manyii Access Road | Morula Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 4 | 5
| 72/2015 | Gombita/Tshivhuyuni/Mphagi Access Road | TM Africa Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 4 | 5
| 73/2015 | Xitacini/Jiweni Access Road | Dikgabo Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 3 | 5
| 74/2015 | Waterval Sport Facility | Botshabelo Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 5 | 5
| 89/2015 | Vyeboom Access Road | MVE Consulting Engineers | MIG | 24/03/2016 | 30/06/2016 | Design stage | none | n/a | n/a | 4 | 5
FINANCE |  | Printing of consumer statements | SA Post office | Income | 1/6/2014 | 31/5/2017 | Consumer statements are not sent | Late delivery of statements | 2 | 2 | 2 | 2
| 7/2013 | Short term insurance portfolio for a period of three years | Lateral Unison Insurance Brokers (PTY)LTD | Income | 2013-10-01 | 2016-09-30 | satisfactory |  | 4 | 4 | 4 | 4
| 46/2010 | Provision of banking services for period of 60 months. | First National Bank | Income | 2011-07-01 | 2016-06-30 | Satisfactory |  | 3 | 3 | 4 | 4
| 41/2013 | GRAP Compliant Assets register | Musanda Chartered Accounts (PTY)LTD | Income | 2014-03-01 | 2017-29-02 | Satisfactory |  | 4 | 4 | 4 | 4
| 61/2010 | Proposal card fleet management | Wesbank | Income | 2011-11-01 | 2013/10/31 extended | Satisfactory |  | 5 | 5 | 5 | 5
| 3/2011 | Rendering of meter reading services for period of three (3) years | Bires/UMS | Income | 2011-06-29 | 2014/05/30 extended | satisfactory |  | 2 | 2 | 3 | 3
| 56 /2008 | 4X10000 Water tankers | Cooper Eagle Trading 327 CC | Income | 2009-02-12 | 2019-02-28 | Satisfactory |  | 3 | 3 | 3 | 3
| 14/2013(section 32 ) | MMs sent statement for municipal accounts | Ntsumi Telecommunications | Income | 01/03/2015 | 28/02/2018 |  |  | 2 | 2 | 2 | 2
| 19/2015 | Supply ad delivery of electrical materials | Several service providers | income | 1/12/2015 | 30/11/2018 | High prices of some items |  | n/a | n/a | 3 | 2
COMMUNITY SERVICES | 5/2013 | Provision of Security Services for property | Veteran Security Services | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 3 | 3 | 4 | 4
| 5/2013 | Provision of Security Services for property | Backline Security & Cleaning Services | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 2 | 3 | 3 | 4
| 5/2013 | Provision of Security Services for property | GNS Security | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 3 | 3 | 3 | 3
| 5/2013 | Provision of Security Services for property | Vhugi Protection Services | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 4 | 4 | 3 | 4
| 5/2013 | Provision of Security Services for property | Majojo Trading | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 3 | 3 | 4 | 4
| 5/2013 | Provision of Security Services for property | 2RM Security T/A Analytical Risk MX | Income | 01/08/2013 | 31/7/2016 | Satisfactory |  | 2 | 3 | 3 | 4
| 105/2010 | Parking Meter Management System | Rirhothe Trading and Investment | Income | 01/12/2012 | 30/11/2015 | In progress |  | 2 | 3 | 3 | 3
| 2/2011 | Cash-In-Transit | G4S Security | Income | 01/09/2011 | 31/01/2016 | In progress |  | 1 | 1 | 1 | 1
CORPORATE SERVICES | 37/ 2006 | One day per month on site service support with Collaborator electronic document movement as per Annual Service Level Agreement | Business Engineering (Pty) Ltd | Income | 1/5/2015 | 30/6/2016 | According to contractual provisions | None | 5 | 5 | 5 | 4
| Existing service provider per contract for ICT Support services | ICT software applications and technical support service | ITNA (Pty) Ltd | Income | As per Service Level Agreement | As per Service Level Agreement | According to contractual provisions | None | 5 | 5 | 5 | 5
| Existing service provider per contract for Munsoft Financial Management Support services | Continuous daily support services on Munsoft Financial Management services, including upgrade of software and training on operational level as well as Software License Agreement | Munsoft (Pty) Ltd | Income | As per Service Level Agreement | As per Service Level Agreement | According to contractual provisions | None | 5 | 5 | 5 | 5
| Various Software Licenses Agreements | Software Applications on the Information Technology Systems | Various software application service providers | Income | negotiated | negotiated | According to contractual agreements | None | 5 | 5 | 5 | 5
| 41/2014 | Supply and delivery of stationery for three years | Londola Trades , Ludricks Construction and Projects | Income | 1/11/2014 | 30/10/2017 | According to contractual provisions | none | 5 | 5 | 5 | 5
| 38/2014 | Supply and delivery of photocopying papers for three years | TCL Group Pty(Ltd) | Income | 1/10/2014 | 30/09/2017 | According to contractual provisions | none | 5 | 5 | 5 | 5
| 25/2014 | Medical services: Occupational medical therapist for employees | Chitandani Medical Clinic | Income | 1/7/2014 | 31/5/2017 | According to contractual provisions | none | 5 | 5 | 5 | 5
| 35/2012 | Medical Services: Psychology for period of three years | Matswaisa Trading Enterprise | Operational budget | 13/02/2013 | 13/02/2016 |  | None | 5 | 5 | 5 | 5
| 33/ 2013 | Rental of photocopiers | *Palesa Tech (Pty) Ltd and Fintech Bank (Pty) Ltd NOTE: The company has ceded its business to a successor in title , ITEC Impact, who has taken over the technical support service on 12 rental copiers with effect of 5 April 2016 | Income | 1/5/2014 | 30/4/2017 | According to contractual provisions During March 2016 the technical support service was not according to contract. Palesa Tech Pty Ltd has since ceded their business rights to a successor ITEC Impact | None | 5 | 5 | *2 | 2

## CONCLUSION
7. CONCLUSION
In the financial year 2015/2016 Makhado Municipality has done well in terms of completing service delivery project. The municipality achieved 100% spending in terms of INEP and MIG conditional grants. This reports promotes the principles of transparency and accountability to the community and other stakeholders. It depicts the development character of the municipality at all spheres, enhancing participatory democracy and cooperative governance and responds to the principles of the Constitution, Batho Pele, White Paper on Local Government, Municipal Systems Act and the Municipal Finance Management Act.