## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
FOURTH QUARTER PERFORMANCE
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER AND LOWER SDBIP)
FOR
2015/2016 FINANCIAL YEAR
AFTER ADJUSTMENT BUDGET

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vison and Mission
3. Departments
4. HIGHER LEVEL SDBIP
4.1. Municipal Transformation and Organisational Development
4.2. Baisc service Delivery
4.3. Local Economic Development
4.4. Municipal Finance Management and Viability
4.5. Good Governance and Public Participation
5. LOWER LEVEL SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. Monthly Revenue and Expenditure
7. Monthly Revenue and Expenditure by Vote
8. Capital Cashflow
9. Capital Cashflow by Vote
10. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1)(c) of MFMA states that 54. (1) On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must— (a) consider the statement or report; (b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan; (c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget; (d) issue any appropriate instructions to the accounting officer to ensure— (i) that the budget is implemented in accordance with the service delivery and budget implementation plan; and (ii) that spending of funds and revenue collection proceed in accordance with the budget; (e) identify any financial problems facing the municipality, including any emerging or impending financial problems; and (f) in the case of a section 72 report, submit the report to the council by 31 January of each year.
In terms of MFMA Circular 13, the SDBIP is a layered plan, with the top layer of the plan dealing with consolidated service delivery targets and in-year deadlines, and linking such targets to top management. Once the top-layer targets are set, the top management is then expected to develop the next (lower) layer of detail of the SDBIP, by providing more detail on each output for which they are responsible for, and breaking up such outputs into smaller outputs and linking these to each middle-level and junior manager. Much of this lower layer detail will not be made public nor tabled in council – whilst the municipal manager has access to such lower layer detail of the SDBIP, it will largely only be the senior manager in charge who will be using such detail to hold middle-level and junior-level managers responsible for various components of the service delivery plan and targets of the municipality. Only the highest layer of information of the SDBIP will be made public or tabled in the council. Such high-level information should also include per ward information, particularly for key expenditure items on capital projects and service delivery – this will enable each ward councilor and ward committee to oversee service delivery in their ward.

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## HIGH LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward/Dept | Funding Source | Budget 15/16 R'000 | Adjustment budget | Start Date | End Date | 4th Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | No
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | Target achieved | IDP review for 2016/2017 completed and approved by Council | None | None | IDP Review | Makhado Municipality | N/A | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Final IDP submitted to council for adoption by 31 May 2016 | Target achieved | Final IDP submitted was to council for adoption by 31 May 2016 | None | None | Council resolutions, Draft IDP, Attendance register, Invitations for strategic plan, IDP Consultation attendance register. | MM | 1
Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | Target achieved | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | None | None | SDBIP Development | Makhado Municipality | N/A | Income | Operational | Operational | 1/4/2015 | 30/6/2016 | SDBIP signed by the Mayor within 28 days after approval of the budget | Target achieved | SDBIP was signed by the Mayor within 28 days after approval of the budget | None | None | Signed SDBIP | MM | 2
Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2016 | 114 | 135 | Target achieved | 147 | None | none | Training | Makhado Municipality | N/A | Income | Operational | Operational | 1/4/2015 | 30/6/2016 | 3 | Target achieved | 18 | None | None | Proof of attendance | CORP | 3
Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2016 | 61 | 75 | Target achieved | 16 councilors were trained | None | none | Training | Makhado Municipality | N/A | Income | Operational | Operational | 1/4/2015 | 30/6/2016 | 75 | Target achieved | 16 | None | None | Proof of attendance | CORP | 4
Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Target achieved | Adopted by Council | none | none | Organogram review | Makhado Municipality | N/A | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Submit the final Draft Organogram to Council for approval | Target achieved | Final Draft Organogram was submitted to Council for approval | None | None | Minutes and attendance register, Council resolutions, | CORP | 5
Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | 3 | 4 | Target not achieved | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Recruitment in terms of EE Plan | Makhado Municipality | N/A | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 4 | Target not achieved | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Appointment letters | CORP | 6
Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | 49 events done in 2014/15 | 43 for 2015/16 | Target achieved | 48 events was done | None | None | Special Programs | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 12 | Target achieved | 12 meetings were held under the special programs for q4 | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP | 8
Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2016 (Dzanani) | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Target not achieved | Service provider appointed delayed in terms of completing the project | Delay by the appointed service provider | Follow up with the service provider to complete printing of street name plates and poles to enable the municipality to install | Street Naming (Dzanani) | Makhado Municipality | 33 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Street names completed for R293 Towns (Dzanani) | Target not achieved | Street names not completed | Appointed service provider is not responsice,there is delay in completion of the project. | Recommendations will be made to finance for consideration of the second highest responsive service provider | Expenditure Report | DEVP | 24
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Target achieved | 19149 | None | None | Waste Management | Makhado Town, Tshikota Township, Vleifontein, Waterval Township, Dzanani township, Vuwani Township, Kutama-Sinthumule Area, Brambos | Ward 20, 21, 22, 23, 24, 25, 26. | INCOME | Operational | Operational | 1/7/2015 | 30/6/2016 | 19149 (non cumulaitve) | Target achieved | 19149 | None | None | Proof of collection from the affected stakeholders. | MM and COMM | 8
Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2016 | 2 | 3 | Target achieved | 3 parks were developed | None | None | Development of Parks | 5047 park,Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 12000000 | 1/7/2015 | 30/6/2016 | 3 | Target achieved | 3 parks were developed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 9
Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2016 | 1047 | 1180 | Target achieved | 1042 | Some of the connection ermarked for the 4th quarter were completed on third quarter | None | Electrification of households | Magau, Tshiozwi, Ramantsha, Madodonga,Mamburu, Makushu, Wisagalaza, Sukani, Mamburu, Gogobole, Tshivhulana, Ratombo, Fredom, Lusaka, Tshivhuyuni. | Ward 23,25,03 | INCOME | 21824299 | 22199786 | 1/7/2015 | 30/6/2016 | 1001 | Target not achieved | 963 connections were done | Makushu connections were delayed due to the service provider not fianlising designs. | To complete the project in the 1st quarter of 15/16 fiancial year. | Proof of connections to targeted households | MM and TECH | 10
Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads upgraded from gravel to tar/paving by 30 June 2016 | 26km | 18.9km | Target achieved | 18.9km | 21.9km roads upgraded from gravel tar/paving | None | Upgrading of roads | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 79361617 | 1/7/2015 | 30/6/2016 | 7.8km | Target achieved | 9.5km | None | None | Project progress report, Certificate of completion | TECH | 11
Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/18 | Upgrading of Vuwani sports facilities | Makhado Municipality | Ward 3 | MIG | 2492678 | 4492677.57 | 1/7/2015 | 30/6/2016 | Construction of roof structure and completion. | Target not achieved | Construction of roof structure and completion not completed | Construction of roof structure and completion not completed due to community protest | To be completed during 2016/17 FY | Project progress report, handover report | TECH | 12
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | N/A | Planning for Waterval sports facility completed. | Target achieved | Design completed and advertised for appointment of contractors | None | None | Planning for Waterval sports facility. | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 | 1/7/2015 | 30/6/2016 | Finalisation of designs and advertisemnet for appointment of Contractors | Target achieved | Design completed and advertised for appointment of contractors | None | None | Advertisement copy, appointment letter, design report. | TECH | 13
Building and Construction | Accessible basic and infrastructure services | # of graveyards to be developed by 30 June 2016 | 1 | 10 | Target not achieved | 4 graveyards were developed | 5 graveyards were not fenced due to financial constraints and Contractor appointed. No progress on site | Tender advertised for graveyards in 2016/17 FY | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing (Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein, Vuwani, Dzanani) | Ward 35, 25, 1,12,8,27,32,20 | MIG | 26700000 | 26700000 | 1/7/2015 | 30/6/2016 | 10 | Target not achieved | 4 graveyards were developed | 5 graveyards were not fenced due to financial constraints and Contractor appointed. No progress on site | Tender advertised for graveyards in 2016/17 FY | Advertisement copy, appointment letter,project progress report, handover report | TECH | 14
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Financial Statements | Sound Financial Management and viability | To obtain unqualified audit opinion by 31 December 2015 | Unqualified audit opinion | Unqualified audit opinion obtained | Target not achieved | Qualified audit opinion | SCM ,Valuation roll community chalenges Asset and revenue roads imapirment | Compliance , improve methodogy in imapirment and completing the capturing of Coghta outocme on valuation roll appeal hearing | Auiting of financial statements | Makhado Municipality | Aministration | Income | N/A | 169,734,677.34 | 1/7/2015 | 30/6/2016 | Unqualified audit opinion | Target not achieved | Qualified audit opinion | SCM ,Valuation roll community chalenges Asset and revenue roads imapirment | compliance , improve methodogy in imapirment and completing the capturing of Coghta outocme on valuation roll appeal hearing |  | MM and All Directors | 15
Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Target achieved | 94% of Capital budget spent. (159156491.4/169315416) | NONE | NONE | Capital Budget | Makhado Municipality | Aministration | Income | 163938800.12 | 169,734,677.34 | 1/7/2015 | 30/6/2016 | 100% | Target achieved | 94% of Capital budget spent. (159156491.4/169315416) | NONE | NONE | Quarterly Financial Report | MM and All Directors | 16
Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | Target achieved | 100% of MIG spent (112264000) | NONE | NONE | MIG | Makhado Municipality | Aministration | Income | 112264000 | 112264000 | 1/7/2015 | 30/6/2016 | 100% | Target achieved | 100% of MIG spent (112264000) | NONE | NONE | Quarterly Financial Report | MM | 17
Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | Target achieved | 100% of INEP Spent (17000000) | NONE | NONE | INEP | Makhado Municipality | Aministration | Income | 17000000 | 17000000 | 1/7/2015 | 30/6/2016 | 100% | Target achieved | 100% of INEP Spent (17000000) | NONE | NONE | Quarterly Financial Report | MM | 18
Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | Target achieved | 100% of FMG Spent (1600000) | NONE | NONE | FMG | Makhado Municipality | Aministration | Income | 1600000 | 1600000 | 1/1/2016 | 31/3/2016 | N/A | Target achieved | 100% of FMG Spent (1600000) | NONE | NONE | Expenditure Report | B&T | 19
Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Target achieved | 96% of Revenue collected (27850683.76/29114673.61%) | NONE | Move into restructiored tariffs once energy audit is completed in munciplaity | Revenue Collection | Makhado Municipality | Aministration | Income | 342227123 | 342227123 | 1/7/2015 | 30/6/2016 | 90% | Target achieved | 96% of Revenue collected (27850683.76/29114673.61%) | NONE | move into restructiored tariffs once energy audit is completed in munciplaity | Section 71 report (c1 schedule) | B&T | 20
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | Target achieved | 1600 LED job opportunities created | None | None | LED job opportunities | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/06/2016 | 800 | Target achieved | 134000% | None | None | EPWP, CWP, and Community Projects reports | MM and DEVP | 21
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Risk Management | Good governace and Administrative Excellence | # of risk activities cordinated by 30 June 2016 | 13 | 13 | Target achieved | 13 risk activities were cordinated | None | None | Risk Management activities | Makhado Municipality | Aministration | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 5 | Target achieved | 5 risk activities were cordinated | None | None | Risk Management Register and Reports | MM | 22
Policies and By Laws | Good governace and Administrative Excellence | # of by laws to be reviewed by 30 June 2016 | 7 | 4 | Target achieved | 4 by laws were reviewed | None | None | Reviewing of Municipal By-laws | Makhado Municipality | Aministration | Income | 1/7/2015 | OPEX | 01/07/2015 | 30/06/2016 | 4 | Target achieved | 4 by laws were approved by council and also promulgated wit provincial gazzete | None | None | Council resolutions, Copies of approved by laws. | CORP | 23
Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Target achieved | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | None | None | Internal Audit Charter | Makhado Municipality |  | Income | OPEX | OPEX | 1/4/2015 | 30/6/2015 | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval by 30th June 2015 | Target Achieved | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval by 30th June 2015 | None | None | Council Resolution, Copy of the plan | MM | 92
Information Technology | Good governace and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Phase 1 done | Complete server upgrade project | Target achieved | Server upgrade were completed | None | None | Upgrade of servers | Civic Center |  | income | R200,000 | 148958 | 1/7/2015 | 31/3/2016 | Call for quotations and award the project | N/A | N/A | N/A | N/A | Appointment letter, Project agreement, installation report and payment certicate | CORP | 100
Council Services | Good governace and Administrative Excellence | # of Council meetings convened by 30 June 2016 | 15 | 6 | Target achieved | Thirteen (13) Council meetings were convened | None | None | Council meetings | Makhado Municipality | Aministration | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 2 | Target achieved | 2 Council meetings | None | None | Minutes, Attendance register, notice of invitations. | CORP | 26
Communication | Good governace and Administrative Excellence | # of communication indicators/activities/projects implemented by 30 June 2016 | 5 | 5 | Target achieved | 5 communication indicators / activity /projects were implememnted | None | None | Communication projects | Civic Center | Ward 20 | Income | R20,000.00 | N/A | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP | 27
Public Participation | Good governace and Administrative Excellence | # of public participation indicators/activities/projects implemented by 30 June 2016 | 7 | 7 | Target not achieved | 5 public participation indicators/activities/projects were implemented | Imbizo feedback session not convened and Public Participatuion policy was not approved by Council | To be done during financial year 2016/17 | Public Participation | Makhado Municipality | All wards | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 4 | Target not achieved | 3 public participation indicators/activities/projects were implemented | Public Participation Policy was submited to Council for approval | The meeting that was supposed to be held didn’t happen | None | CORP | 28

## LMTOD
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Start Date | End Date | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | 16/17 R'000 | 17/18 R'000 | Portfolio Of Evidence | Dept | NO
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (LOWER SDBIP)
Performance Management | Good governance and administrative excellence | # of organisational performance reports developed and submitted to Council by 30 June 2016 | 8 | 8 | Target achieved | 8 organisational performance reports developed and submitted to Council | None | None | Quarterly performance reports | Makhado Municipality | 21 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 | Operational | Operational | Target achieved | 1 | None | None | Operational | Operational | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM | 1
Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2016 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% (6/6) | Target achieved | 100% (6/6) Section 57 Managers signed performance agreements | None | None | Performance agreements | Makhado Municipality | 21 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% | Operational | Operational | Target achieved | 100% (6/6) Section 57 Managers signed performance agreements | None | None | Operational | Operational | Signed Performance Agreements | MM | 2
Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conducted by 30 June 2016 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Target achieved | 4 section 57 managers individual assessment conducted | None | None | Individual Performance Assessment | Makhado Municipality | 21 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 1 (Informal Assessment 2014/2015) | Operational | Operational | Target achieved | 1 (Informal Assessment conducted | None | None | Operational | Operational | Scorecards, Attendance Register | MM | 3
Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2016 | 67 employees appointed | 30 | Target not achieved | The recruitment procees was done up to receiving appllication. 25 Employees appointed as roll over from 2014/2015 FY. 8 Interns were advertised and appointed | Adjusted during budget adjustment due to MEC rullind due to redermination of municipal boundries in Vhembe District | Adjusted during budget adjustment due to MEC . The exemption was requested to fill the critical post which was not approved | Personnel Recruitment | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Target notachieved | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Adjusted during budget adjustment due to MEC declaration | Operational | Operational | Adjusted during budget adjustment due to MEC declaration | CORP | 4
Human Resources and Organizational Development | Invest in human capital | # of employee assistance programmes events conducted by 30 June 2016 | 6 events | 6 events | Target achieved | 6 employee assistance programmes events were conducted | None | None | Employee Assistance Campaigns | Makhado Municipality | 21 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 2 events |  |  | Target achieved | 2 employee assistance programmes events were conducted | None | None | Operational | Operational | Invitations, attendance registers and close-out report | CORP | 5
Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Target achieved | Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy scheduled to be adopted by Council on the 14th July 2016 | None | None | Development of 3 outstanding HR policies | Makhado Municipality | 21 | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Submit the final darft poicies to Council for approval. (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) |  |  | Target not achieved | Draft Leave Policy, 2016; Draft Tobacco Control Policy, 2016; Draft Occupational Health &Safety Policy, 2016 was included in Executive Committee agenda for 23 June 2016; t | Meeting did not form a quorum and was adjourned to July 2016 | The 3 policies will be further considered in Q1 of 2016/17 at the scheduled Council meeting of 14 July 2016 | Operational | Operational | Exco Agenda of 404th meeting for 23 June 2016 with draft Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP | 6
Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | Target achieved | 15 bursaries were awarded | None | None | External Bursary Award | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Bursary committee meeting to evaluate progress | Operational | Operational | Target achieved | Bursary Committee meeting was held to evaulate progress | None | None | Operational | Operational | Advert, List of qualifying leaners and Letters of bursary awards | CORP | 7
Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Target Achived | 100% (35/35 of application received/(35/35 of application attended to within 90 days). | None | None | Permission to Occupy | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of application received/(# of application attended to within 90 days). |  |  | Target achieved | 100% (10/10of application received/(10/10 of application attended to within 90 days). | None | None | Operational | Operational | Site inspection report, Register of applications | DEVP | 9
Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Target Achived | 100% (383/383 of housing queries attended within 30 days/# of received) | None | None | Housing Coordination | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of housing queries attended within 30 days/# of received) |  |  | Target achieved | 326/326 title deeds issued. | None | None | Operational | Operational | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP | 10
Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2016 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Target Achived | 100% processed | None | None | Building Plans | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of building plans assessed/# of building plans received) | Operational | Operational | Target achieved | 100% (149/149 of building plans assessed /149/149 of building plans received) 72 | None | None | Operational | Operational | Building plans register | DEVP | 11
Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2016 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Target Achived | 100% (53/53 of applications processed/53/53 applications received) | None | None | Zoning of land | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Target achieved | 100% (7/7 of applications processed/7/7 applications received) | None | None | Operational | Operational | Zoning certificates issued | DEVP | 12
Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2016 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Target Achived | 100% (102 of applications processed/102/102 applications received) | None | None | Rezoning of land | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Target achieved | 100% (34/34 of applications processed/34/34 applications received) | None | None | Operational | Operational | EXCO resolutions | DEVP | 13
Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Target Achived | 100% (79/79 of application for land use rights inspection conducted within 14 days/79/79 of application received) | None | None | Land Use Management | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) |  |  | Target achieved | 100% (8/8 of application for land use rights inspection conducted within 14 days/8/8 of application received) | None | None | Operational | Operational | Site inspection report, Register of applications | DEVP | 14
Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2016 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Target Achived | 100% (32/32of applications processed/32/32 of applications received) | None | None | Occupancy of land | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Operational | Operational | Target achieved | 100% (6/6 of applications processed/6/6 of applications received) | None | None | Operational | Operational | Copy of occupancy certificates issued | DEVP | 15
Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target Achived | 100% (203/203 of applications processed/203/203 of applications received) | None | None | Pegging Applications | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | Application Assessment Report, Register of applications |  |  | Target achieved | 34 applications assessed and , Registered | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 16
Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target Achived | 100% (58/58 of applications processed/58/58 of applications received) | None | None | Demarcation of sites | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target achieved | 100% (10/10 of applications processed/10/10 of applications received) | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 17
Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target Achived | 100% (17/17 of applications processed/17/17 of applications received) | None | None | Property application | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target achieved | 100% (4/4 of applications processed/4/4 of applications received) | None | None | Operational | Operational | Application Assessment Report, Register of applications | DEVP | 18
Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Target Achived | 100% (174/174 of applications processed/174/174 of applications received) | None | None | Property application | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target achieved | 100% (38/38 of applications processed/38/38 of applications received) | None | None | Operational | Operational | Bookings register | DEVP | 19
Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Target Achived | 100% (1/1of queries processed/1/1 of queries received) | None | None | Land Claims | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of queries processed/# of queries received) |  |  | Target achieved | No quiries has been processed or received | None | None | Operational | Operational | Correspondence letters and emails. | DEVP | 20
Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | Target Achived | 100% (38/38 of contravention notices issued within 5 days/38/38 of contravention identified) | Continuation of illegal activities by clients | Continuous involvement with legal division to instititute legal proceedings | By Law Enforcement | Makhado Municipality | All wards | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | 100% (# of contravention notices issued within 5 days/# of contravention identified) |  |  | Target achieved | 100% (9/9 of contravention notices issued within 5 days/ 9/9 contravention identified) | Continuation of illegal activities by clients | Continuous involvement with legal division to instititute legal proceedings | Operational | Operational | Duplicate notices | DEVP | 21
Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2016 | 240 | 240 | Target Achived | 299 routine inspection conducted | None | None | Routine Inspection | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 60 |  |  | Target achived | 89 routine inspection conducted | None | None | Operational | Operational | Inspection form, Register | DEVP | 22
Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Target Achieved | 100% (446/446 of site inspections conducted within 24 hours/446/446 of site inspections application received) | None | None | Site Inspection | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) |  |  | Target achieved | 100% (81/81 of site inspections conducted within 24 hours/81/81 of site inspections application received) | None | None | Operational | Operational | Inspection form, Register | DEVP | 23

## LBSD
Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjusted budget | Start Date | End date | 4th Quarter | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio of Evidence | Dept | NO
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (LOWER SDBIP)
Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Target Achieved | Disaster Management Plan was reviewed and included to the IDP for 2016/2017 | None | None | Annual Revision of the Disaster Management Plan | Community Services - disaster Management Unit | N/A | Income | Operational | Operational | 2015-01-07 | 30/06/2016 | Submission of the Disaster Management Plan to the IDP Manager for submission to Council | Target achieved | Disaster Management Plan was submitted through IDP Manager to Council | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM | 25
Library Services | Promote community and environmental welfare | To do designs for refurbishment of the library roof by 30 June 2016 | Roof damaged | Designs for Refurbishment of the library building completed | Target Achieved | Designs for Refurbishment of the library building was completed and quotations for material obtained in preparation for 2016/17. | None | None | Designs for Refurbishment of library building | Community Services - Library Services Unit | Ward 20 | Income | 1000000 | 200000 | 2015-01-07 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Project Progress report | TECH | 26
Waste Management | Promote community and environmental welfare | To develop Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre not completed | Target not achieved | Landfill site makhado + recycling centre not completed. The service provider has been appointed to start the project around June 2016 | Delays in terms of appointent of service proider ( Readvertisement) | The project to be completed during first quarter 2016/17 financial year | Development of | Tshikota | Ward 21 | MIG | 5 000 000.00 - | 5599366.72 | 2015-01-07 | 30/06/2016 | Construction of recycling centre (20m x 40m). Complete the project. | Target not achieved | The service provider has been appointed to start the project around June | Delays in terms of appointent of service proider ( Readvertisement) | Th e project to be completed during first quarter 2016/17 financial year | Approval memo, Specifications, Advertisement copy, Appointment letter, Project progress report | COMM | 27
Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | N/A | Landfill site rehabilitatation completed. | Target not achieved | Completion of the evaporation ponds and V-drains not done. Planting of vegetation and grass not done. The service provider has been appointed for the supplier tippertruck and excavator , for the supplier of the the soil to cover the compected waste body | Specification 0f the the advitised tender has been revised | Scope of the work has been ammended | Rehabilitation of the existing Landfill site (Vondelling) | Makhado Municipality | 21 | INCOME | 4000000 | 3083000 | 2015-01-07 | 30/06/2016 | Completion of the evaporation ponds and V-drains. Planting of vegetation and grass. | Target not achieved | Completion of the evaporation ponds and V-drains not done. Planting of vegetation and grass not done. The service provider has been appointed for the supplier tippertruck and excavator , for the supplier of the the soil to cover the compected waste body | Specification 0f the the advitised tender has been revised | Scope of the work has been ammended | Project Progress Report. | TECH | 28
Parks and Recreation | Promote community and environmental welfare | To develop 5047 Park by 30 June 2016 | N/A | Development of 5047 Park completed | Target Achieved | Development of 5047 Park completed | None | None | Development of 5047 Park | 5047 Park | Ward 20 | INCOME | 700000 | 700000 | 2015-01-07 | 30/06/2016 | Development of the park in line with the proposal. Complete the development of the park | Target achieved | Service provider has been appointed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 29
Parks and Recreation | Promote community and environmental welfare | To pay the service provider for development of the N1 recreational park by 30 June 2016 (R436842.11) | N/A | Payment of service provider for Development of N1 recreational park done (R436842.11) | Target Achieved | The payment of service provider has been done for N1 recreational park | None | None | Payment for Development of N1 recreational park | Makhado Municipality | Ward 21 | INCOME | 1000000 | 500000 | 2015-01-07 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | Proof of payment | COMM | 30
Parks and Recreation | Promote community and environmental welfare | To refurbish and upgrade Civic Centre Park+ Meerkat park by 30 June 2016 | N/A | Refurbishment and Upgrading of Civic Centre Park+Meerkat park completed | Target achieved | Refurbishment and Upgrading of Civic Centre Park+Meerkat park completed. | None | None | Refurbishment and Upgrading of Civic Centre Park and Meerkat Park | Civic Centre Park | Ward 20&21 | INCOME | 500000 | 500000 | 2015-01-07 | 30/06/2016 | Development of the park in line with the proposal. Complete the development of the park | Target achieved | Development of the park in line with the proposal is completed. Complete the development of the park | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM | 31
Electricity Provision | Accessible basic and infrastructure services | To connect 50 households at Magau by 30 June 2016 | N/A | 50 households at Magau connected | Target achieved | 50 households at Magau connected | None | None | MAGAU | Magau | Ward 23 | INCOME | 935201.32 (INCOME) 712 000 (INEP) | 935201.32 (INCOME) 712 000 (INEP) | 2015-01-07 | 30/06/2016 | Connect and energise 50 households. | Target achieved | 52 households were connected and energise | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 32
Electricity Provision | Accessible basic and infrastructure services | To connect 40 households at TSHIOZWI /GOGOBOLE by 30 June 2016 | N/A | 40 households connected at TSHIOZWI /GOGOBOLE | Target achieved | 40 households connected at TSHIOZWI /GOGOBOLE | None | None | TSHIOZWI & GOGOBOLE | Tshiozwi Gogobole | Ward 23 | INCOME | 2101576 | 2101576 | 2015-01-07 | 30/06/2016 | Connect and energise 40 households. | Target achieved | 40 households were connected and energise | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 33
Electricity Provision | Accessible basic and infrastructure services | To connect 96 households at Ramantsha/Riverside by 30 June 2016 | N/A | 96 households at Ramahantsha /Riverside connected | Target Achieved | 97 households at Ramahantsha /Riverside connected | None | None | RAMANTSHA/RIVERSIDE | RAMANTSHA/RIVERSIDE | Ward 23 | INCOME | 1281962 | 1281962 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 34
Electricity Provision | Accessible basic and infrastructure services | To connect 83 households at Madodonga/Manavhela by 30 June 2016 | N/A | 83 households at Madodonga/Manavhela connected | Target Achieved | 83 households at Madodonga/Manavhela connected | None | None | MADODONGA | MADODONGA | Ward 25 | INCOME | 1681261 | 1681261 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 35
Electricity Provision | Accessible basic and infrastructure services | To connect 120 households at Mamburu by 30 June 2016 | N/A | 120 households at Mamburu cconnected | Target achieved | 180 households at Mamburu cconnected | None | None | Mamburu | Mamburu | Ward 25 | INEP | 2250000 | 2250000 | 2015-01-07 | 30/06/2016 | Stringing of MV and LV conductors. Complete and energise 120 households. | Target achieved | Stringing of MV and LV conductors was done and 180 households were completed and energise | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 36
Electricity Provision | Accessible basic and infrastructure services | To connect 30 households at Makhushu by 30 June 2016 | N/A | 30 households at Makhushu connected | Target not achieved | 30 households at Makhushu not connected. Project commenced, contractor on site, materials on site. No construction. | Delay in submission of designs and establishment of new households during planning and design period. The actual required number of connections is 123 and costing approximately R3million rands. | Project to continue next financial year | MAKUSHU | MAKUSHU | Ward 25 | INEP | 490000 | 490000 | 2015-01-07 | 30/06/2016 | Stringing of MV and LV conductors. Complete and energise 30 households. | Target not achieved | Project commenced, contractor on site, materials on site. No construction. | Delay in submission of designs and establishment of new households during planning and design period. The actual required number of connections is 123 and costing approximately R3million rands. | Project to continue next fin year | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | 37
Electricity Provision | Accessible basic and infrastructure services | To do designs for Vyeboom 2016/2017 electrification projects ) by 30 June 2016 | N/A | Designs for Vyeboom 2016/2017 electrification projects completed | Target achieved | Designs for Vyeboom 2016/2017 electrification projects completed and project was handed over to Eskom | None | None | Designs for Vyeboom 2016/2017 electrification projects | Vyeboom village | Ward 3 | INEP | 952500 | 952500 | 2015-01-07 | 30/06/2016 | Completion of designs, designs approval by ESKOM, technical electrification forum meeting, | Target achieved | Designs completed, approval by ESKOM done, technical electrification forum meeting was held and project was handed over to Eskom | none | n/a | Specifications, Advertisement, appointment letter, Designs, Minutes of of technical forum meeting | TECH | 38
Electricity Provision | Accessible basic and infrastructure services | To upgrade 3km Industrial line by 30 June 2016 | N/A | Upgrading 3km Industrial line completed | Target not achieved | Upgrading 3km Industrial line not completed. Phase 1 is completed. About 30% of poles planted in ph2. No conductor strining no closing spans. | Labour unrest in Mar/Apr 2016. Due to time and financial constraints, SP could not be appointed to speed up the project. Funds were transfered to finance the EPWP workers who are on 12 months contract with the municipality | Project to continue in the next financial year | Upgrading 3km Industrial line | Makhado Municipality | Ward 21 | INCOME | 250000 | 250000 | 2015-01-07 | 30/06/2016 | Dress and plant poles phase 2, stringing of conductors phase 2, closing spans phase 2. Complete the project. | Target not achieved | Phase 1 is completed. About 30% of poles planted in ph2. Stringing of conductors not done , closing spans not done. | Labour unrest in Mar/Apr 2016. Due to time and financial constraints, SP could not be appointed to speed up the project. Funds were transfered to finance the EPWP workers who are on 12 months contract with the municipality | Project to continue in the next financial year | Designs, Appointment letter for labourers, Project progress report, | TECH | 39
Electricity Provision | Accessible basic and infrastructure services | To upgrade 4.5km Shefeera Line by 30 June 2016 | N/A | Upgrade 4.5km Shefeera Line completed | Target achieved | 4.5km Shefeera Line upgraded. | None | None | Upgrade 4.5km Shefeera Line | Makhado Municipality | Ward 21 | INCOME | 600000 | 512999 | 2015-01-07 | 30/06/2016 | Stringing of conductors, closing spans, completion of the project | Target achieved | Stringing of conductors done , closing spans done, project completed | None | None |  | TECH | 40
Electricity Provision | Accessible basic and infrastructure services | To appoint the contractor for upgrade of Urban Substations by 30 June 2016 | N/A | Appointment of contractor and site handover. | Target achieved | Appointment of contractor and site handover was done on the 29/4/16. | None | None | Upgrade Urban Substations | Makhado Municipality | Ward 20 | INCOME | 2500000 | 2500000 | 2015-01-07 | 30/06/2016 | Appointment of contractor and site handover. | Target achieved | Appointment of contractor was done and site handover was done on the 29/4/16. | None | None |  | TECH | 41
Electricity Provision | Accessible basic and infrastructure services | To upgrade 5km Mountain line by 30 June 2016 | N/A | Upgrading 5km Mountain line completed | Target not achieved | Upgrading 5km Mountain line not completed. Some of the poles wrel delivered on site and holes dug. No physical progress. Some of the resourses were used at Industrial line Ph2. | Labour unrest Mar/Apr. Due to time and financial constraints, SP could not be appointed to speed up the project. Funds were transfered to finance the EPWP workers who are on 12 months contract with the municipality | Project to continue in next fin year | Upgrading 5km Mountain line | Makhado Municipality | Ward 30 | INCOME | 250000 | 250000 | 2015-01-07 | 30/06/2016 | Dress and plant poles, stringing of conductors, closing spans. Completion of project. | Target not achieved | Some of the poles were delivered on site and holes dug. No physical progress. Some of the resourses were used at Industrial line Ph2. | Labour unrest Mar/Apr. Due to time and financial constraints, SP could not be appointed to speed up the project. Funds were transfered to finance the EPWP workers who are on 12 months contract with the municipality | Project to continue in next financial year |  | TECH | 42
Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute 2.2km Beaufort West line by 30 June 2016 | N/A | Upgrade and reroute 2.2km Beaufort West line completed | Target achieved | 2.2km Beaufort West line completed | None | None | Upgrade and reroute 2.2km Beaufort West line | Beaufort West line | Ward 30 | INCOME | 1500000 | 1500000 | 2015-01-07 | 30/06/2016 | Site establishment and appointment of labour,survying of the pole holes and excavating pole holes. Dress and plant poles, strining of conductors, switching on and project completion | Target achieved | Site establishment and appointment of labour done ,survying of the pole holes and excavating pole holes done. Dress and plant poles done , stringing of conductors and switching on done and project completed | None | None | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH | 43
Electricity Provision | Accessible basic and infrastructure services | To replace oil curcuit breaker by 30 June 2016 | N/A | Replacement of oil curcuit breaker completed | Target achieved | Oil curcuit breaker replaced and the project completed | None | None | Oil curcuit breaker replacement | Main substation | Ward 21 | INCOME | 400000 | 400000 | 2015-01-07 | 30/06/2016 | Delivery, Installation and project completion | Target achieved | Delivery and, Installation done and project completed | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 44
Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | N/A | Replacement of channel cover completed | Target not achieved | Project Amended | Project Amended | Project Amended | Substation channel cover replacements | Makhado Municipality | All wards | INCOME | 0 | 0 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | N/A | N/A | N/A | N/A | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 45
Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | N/A | Standby generator installed | Target Achieved | Standby generator installed | None | None | Standby (Backup) Electricity Power Generator-Dzanani | Dzanani | 33 | INCOME | 250000 | 250000 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH | 46
Electricity Provision | Accessible basic and infrastructure services | % air conditioners replaced by 30 June 2016 (# replaced/# requested) | N/A | Air Conditioners replaced | Target achieved | Have replaced 22 airconditioining units to date | None | None | Air Conditioners | Municipal area | All municipal office | INCOME | 150000 | 450000 | 2015-01-07 | 30/06/2016 | 100% | Target achieved | Have replaced 22 airconditioining units to date | None | None | Orders, job cards, photos, invoices, payment certificates | TECH | 47
Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | N/A | CT VT Units 11kv & 22kv replaced | Target not Achieved | Project Amended | Project Amended | Project Amended | CT VT Units 11kv & 22kv | Makhado | All municipal areas | INCOME | 300000 | 300000 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | N/A | N/A | N/A | N/A | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH | 48
Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming B9, T8, A21 and G23/24 by 31 March 2016 | N/A | Low voltage to medium voltage in Rural Farming B9,T8 and A21 upgraded | Target achieved | Low voltage to medium voltage in Rural Farming B9,T8 and A21 upgraded | None | None | Low voltage to medium voltage in Rural Farming B9,T8 and A21 | Makhado | All municipal areas | INCOME | 250000 | 358000 | 2015-01-07 | 30/06/2016 | Escavating pole holesdress and plant hole, streeing the conductor, closing span, low voltage installation G23/24 | Target achieved | Escavating pole holesdress and plant hole done, stringing the conductor done, closing span done , low voltage installation G23/24 done | None | None | Project progress report | TECH | 49
Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | N/A | Mini Subs replaced | Target Achieved | Mini Subs replaced | None | None | Mini Subs | Makhado | All municipal areas | INCOME | 900000 | 444000 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH | 50
Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | N/A | MV Cable 95mm 22kV replaced | Target Achieved | MV Cable 95mm 22kV replaced | None | None | MV Cable 95mm 22kV | Makhado | All municipal areas | INCOME | 150000 | 117000 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH | 51
Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | N/A | Recloser and controllers whole network procured | Target not achieved | Service provider appointed. No progress due to SP not able to supply anymore | SP not able to supply equipments anymore | Re-alocated for next financial year | Recloser and controllers whole network | Makhado | All municipal areas | INCOME | 700000 | 700000 | 2015-01-07 | 30/06/2016 | Project competion and payment certificate | Target not achieved | Service provider appointed. No progress due to SP not able to supply anymore | SP not able to supply equipments anymore | Re-alocated for next financial year | Specification, orders, delivery notes, progress report, completion certificate | TECH | 52
Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | N/A | Remote control of switch gear Tshipise & Levubu procured | Target achieved | Remote control of switch gear Tshipise & Levubu procured | None | None | Remote control of switch gear Tshipise & Levubu | Makhado | All municipal areas | INCOME | 120000 | 180000 | 2015-01-07 | 30/06/2016 | Completion and payment certificate | Target achieved | Project competed and payment certificate was done | None | None | Specification, advertisement, appointment letter, payment certificate | TECH | 53
Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | Target Achieved | Ring Main Units 11 kV ( RMU) delivered and installed | None | None | Ring Main Units 11 kV ( RMU) | Makhado | All municipal areas | INCOME | 300000 | 306740 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specification, order, delivery note, project progress report, payment certificate | TECH | 54
Electricity Provision | Accessible basic and infrastructure services | To constuct Standby quarter perimeter wall by 31 March 2016 | N/A | Standby quarter perimeter wall completed | Target Achieved | Standby quarter perimeter wall completed | None | None | Standby quarter perimeter wall | Makhado | All municipal areas | INCOME | 60000 | 300000 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specification, advertisement, project progress report | TECH | 55
Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | N/A | Standby quarter guard room completed | Target not achieved | Standy quarter guardroom at roof level | Labour unrest and retrenchment of the municipal Builder | Project to be rolled over to 2016/17 FY | Standby quarter guard room | Makhado | All municipal areas | INCOME | 250000 | 250000 | 2015-01-07 | 30/06/2016 | Plastering, painting, roof and ceiling | Target not achieved | Standy quarter guardroom at roof level | Labour unrest and retrenchment of the municipal Builder | Project to be rolled over to 2016/17 FY | Specification, advertisement, project progress report | TECH | 56
Electricity Provision | Accessible basic and infrastructure services | To connect 471 households at Wisagalaza 2 & Chitasi village by 30 June 2016 | Site establishment | Wisagalaza 2 & Chitasi village 471 households connection completed | Target achieved | 471 households at Wisagalaza 2 & Chitasi village connected. | None | None | Wisagalaza 2 & Chitasi village | Wisagalaza village | 8 | INEP | 7771500 | 8826487.19 | 2015-01-07 | 30/06/2016 | Handover and customer data, AS build drawings/ENS, closing of spans, energising and testing, Switching on, final handover and completion certicicate | Target achieved | Project completed. 471 connections completed. | None | None | Appointment letter, project progress report, completion certificate | TECH | 57
Electricity Provision | Accessible basic and infrastructure services | To connect 87 households at SUKANI by 30 June 2016 | N/A | Site handover to contractor, planting of poles. | Target achieved | Site handover to contractor done , planting of poles done. | None | None | SUKANI | SUKANI | Ward 8 | INEP | 1392000 | 1392000 | 2015-01-07 | 30/06/2016 | Site handover to contractor, planting of poles. The project will roll over to the 2016/2017 financial year. | Target achieved | Site handover to contractor done , planting of poles done. The project will roll over to the 2016/2017 financial year. | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 58
Electricity Provision | Accessible basic and infrastructure services | To connect 102 electricity at TSHIVHULANA by 30 June 2016 | N/A | Tshivulana 102 connections completed | N/A | Project taken over by Eskom | None | None | TSHIVHULANA zone 5 | TSHIVHULANA zone 5 | Ward 1 | /INCOME INEP | 1632000 | 0 | 2015-01-07 | 30/06/2016 | Adjusted during budget adjustment | N/A | N/A | N/A | N/A | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 59
Electricity Provision | Accessible basic and infrastructure services | To connect 150 households at Ratombo/ by 30 June 2016 | N/A | Stringing of MV and LV conductors done | Target achieved | Stringing of MV and LV conductors done | None | None | RATOMBO | RATOMBO | 32 | INEP /income | 1472000 | 1472000 | 2015-01-07 | 30/06/2016 | Stringing of MV and LV conductors. The project will roll over to the 2016/2017 finacial year. | Target achieved | MV & LV stringing completed. | SP was waiting for meters | n/a | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 60
Electricity Provision | Accessible basic and infrastructure services | To connect 53 households at Freedom and Lusaka (Tshivhuyuni) by 30 June 2016 | N/A | Site handover and planting of poles. | Target achieved | Site handover done and planting of poles completed. | None | None | Freedom and Lusaka (Tshivhuyuni) | Freedom and Lusaka (Tshivhuyuni) | 12 | INEP | 1040000 | 1040000 | 2015-01-07 | 30/06/2016 | Site handover and planting of poles. The project will roll over to the 2016/2017 finacial year. | Target achieved | 53 households at Freedom and Lusaka (Tshivhuyuni) connected | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH | 61
Electricity Provision | Accessible basic and infrastructure services | To electrify Rabali Stadium by 30 June 2016 | N/A | Electrification Rabali Stadium facility completed | Target Achieved | Electrification Rabali Stadium facility completed | None | None | Electrification Rabali Stadium | Rabali stadium | Ward32 | Income | 150000 | 150000 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Specifications, Advertisement, Apointment letter, delivery notes, | TECH | 62
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgarde Tshikota Access/Pretoriuos Street access road (6.5km) by 30 June 2016 | Gravell road | Tshikota access road/Pretoriuos street upgraded | Target achieved | Tshikota access road/Pretoriuos street upgraded | None | None | Upgrading of Tshikota access road/Pretoriuos street upgraded | Makhado Municipality |  | MIG | 1936405 | 1793613.68 | 2015-01-07 | 30/09/2015 | N/A | N/A | N/A | N/A | N/A | Project progress report, Completion certificate, handover report | TECH | 63
Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To upgrade Magau road (4.5km) phase 2 by 30 June 2016 | Gravell road | Magau road phase 2 completed | Target achieved | Magau road phase 2 completed | None | None | Magau road phase 1 | Magau | Ward 23 | MIG | 22000000 | 21848466.41 | 2015-01-07 | 31/03/2016 | N/A | N/A | N/A | N/A | N/A | Project progress report, handover report | TECH | 64
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhulana to Tshilaphala access road (4.5km) by 30 June 2016 | Gravell road | Tshivhulana to Tshilaphala access road constructed to a base level. | Target not Achieved | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Tshivhulana to Tshilaphala access road | Tshivhulana to Tshilaphala |  | MIG | 13976988.13 | 3000000 | 2015-01-07 | 30/06/2016 | Construction of base, stormwater drainages, finalisation of the base. | N/A | Project adjusted during adjustment budget | None | None | Specifications, advertisement, appointment letter, project progress report | TECH | 65
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road(6.6km) by 30 June 2016 | Gravell road | Ledig road completed | Target Achieved | Ledig road completed | None | None | Ledig road | Ledig | Ward 21 | MIG | 9387156 | 15403183.1 | 2015-01-07 | 31/12/2015 | N/A | N/A | N/A | N/A | N/A | Site establishment report, project progress report, handover report | TECH | 66
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road(3.5km) by 30 June 2016 | N/A | Robert Khoza /Chabani Bungeni road completed | Target not achieved | Surfacing completed and project not handed over | Slow progress by the contractor | Project to be completed in 2016/17 FY | Robert Khoza /Chabani Bungeni road construction | Robert Khoza /Chabani Bungeni road | Ward 13 | MIG | 23000000 | 19689296.81 | 2015-01-07 | 30/06/2016 | Surfacing and handover | Target not achieved | Surfacing completed and project not handed over | Slow progress by the contractor | Project to be completed in 2016/17 FY | Site establishment report, project progress report, handover report | TECH | 67
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road(4.3km) phase 1 by 30 June 2016 | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | Target achieved | (4.3km) Tshivhazwaulu to Rasivhetshela road phase 1 constructed | None | None | Tshivhazwaulu to Rasivhetshela road phase 1 | Makhado Municipality | Ward 4 | MIG | 23811987.67 | 22420672.11 | 2015-01-07 | 30/06/2016 | Completion and handover. | Target achieved | Completion and handover done | None | None | Advertisement copy, appointment letter, design report. | TECH | 68
Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads and bridge projects by 30 June 2016 | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road completed | Target achieved | Design completed and advertised for appointment of contractors | None | None | Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road | Makhado Municipality | Ward 25, 25, 36,30,3,15,12, | MIG | 1 600 000 | 1 600 000 | 2015-01-07 | 30/06/2016 | Finalisation of designs and advertisemnet for appointment of Contractors | Target achieved | Designs completed and advertisement for appointment of contractors done | None | None | Advertisement copy, appointment letter, design report. | TECH | 69
Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | N/A | Planning for Waterval sports facility completed. | Target achieved | Design completed and advertised for appointment of contractors | None | None | Planning for Waterval sports facility. | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 | 2015-01-07 | 30/06/2016 | Finalisation of designs and advertisemnet for appointment of Contractors | Target achieved | Designs completed and advertisement for appointment of contractors done | None | None | Advertisement copy, appointment letter, design report. | TECH | 70
Sports Facilities | Accessible basic and infrastructure services | To construct ablution facility by 30 June 2016 (Waterval Stadium) | N/A | Provision of Waterval stadium ablution facility completed | N/A | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Project adjusted during adjustment budget | Construction of ablution facility at Waterval stadium | Makhado Municipality | Ward 16 | MIG | 300000 | 0 | 2015-01-07 | 30/06/2016 | Adjusted and combined with palisade for Waterval stadium during budget adjustment | N/A | N/A | N/A | N/A | Advertisement copy, appointment letter,project progress report, handover report | TECH | 71
Building and Construction | Accessible basic and infrastructure services | To construct 8 graveyards fencing by 30 June 2016 | N/A | Graveyard fencing completed | Target not achieved | Three (3) graveyards were fenced due to financial constraints. Tender advertised for 5 graveyards in 2016/17 FY | Available budget could cover 3 graveyards only | Project will be finalised in 2016/17 | Graveyard fencing (Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | Tshituni Mawoni, Madodonga,Hanani, Tshivhuyuni, Hlanganani, Tsianda, Ndouvhada, Vleifontein. | Ward 35, 25, 1,12,8,27,32,20 | MIG | 2000000 | 2000000 | 2015-01-07 | 30/06/2016 | Setting out and construction of fence Finalisation of the fence. Handing over | Target not achieved | Three (3) graveyards were fenced due to financial constraints. Tender advertised for 5 graveyards in 2016/17 FY | Available budget could cover 3 graveyards only | Project will be finalised in 2016/17 | Advertisement copy, appointment letter,project progress report, handover report | TECH | 72
Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/17 | Fencing Vuwani Cemetery | Vuwani | Ward 3 | Income | 300000 | 300000 | 2015-01-07 | 30/06/2016 | Evaluation, Adjudication and Appointment of Contractor. Setting out and construction of fence Finalisation of the fence. Handing over | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/17 | Advertisement copy, appointment letter,project progress report, handover report | TECH | 73
Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | N/A | Vuwani cemetry Ablution Facility completed | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/18 | Vuwani Cemetery (Toilet) | Vuwani | Ward 3 | Income | 70000 | 70000 | 2015-01-07 | 30/06/2016 | Setting out and construction of fence Finalisation of the fence. Handing over | Target not achieved | Contractor appointed. No progress on site | Public protest/unrest | Project to be finalised in 2016/18 | Advertisement copy, appointment letter,project progress report, handover report | TECH | 74
Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | N/A | Graveyard fencing completed | Target achieved | Project completed and handed over done | None | None | Fencing grave yard +sliding gate(Dzanani cemetery) | Dzanani township | Ward 35 | Income | 300000 | 300000 | 2015-01-07 | 30/06/2016 | Handing over | Target achieved | Project completed and handed over done | None | None | Advertisement copy, appointment letter,project progress report, handover report | TECH | 75

## LMFMV
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets ( | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Start Date | End date | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | N0
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Target achieved | Revenue enhancement policies was reviewed | None | None | Revenue enhancement policies review | Makhado Municipality | Administration | Income | Operational | Operational | 1/1/2016 | 30/6/2016 | Final Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Debts Collection) | N/A | N/A | Target achieved | Revenue enhancement policies was reviewed | None | None | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T | 76
Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to council | Target achieved | Draft budget was tabled to council | None | None | Draft budget | Makhado Municipality | Administration | Income | Operational | Operational | 1/1/2016 | 31/3/2016 | N/A | N/A | N/A | Target achieved | Draft budget was tabled to council | None | None | Draft budget and Council Resolution | B&T | 77
Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget was submitted to council | Final budget submitted to council | Target achieved | Final budget was submitted to Council | None | None | Final budget | Makhado Municipality | Administration | Income | Operational | Operational | 1/4/2016 | 31/5/2016 | Final budget | N/A | N/A | Target achieved | Final budget was submitted to Council | None | None | Final budget and Council Resolution | B&T | 78
Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2015 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Target achieved | Financial statements was compiled and submit to AG | None | None | Financial statements | Makhado Municipality | Administration | Income | Operational | Operational | 1/7/2015 | 31/8/2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Copy of Financial statements | B&T | 79
Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Target achieved | 12 section 71 reports were submitted to Treasury within 10 days after the end of the month | None | None | Section 71 report submission | Makhado Municipality | Administration | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 3 | N/A | N/A | Target achieved | 3 Section 71 reports were submitted to Treasury within 10 days after the end of the month | None | None | Copy of acknowledgement of receipt by Treasuries | B&T | 80
Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Target achieved | 100/100 tenders adjudicated/# of tenders closed and due for adjudication) | None | None | Tender adjudication | Makhado Municipality | Administration | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | N/A | N/A | Target achieved | 100/100 tenders adjudicated/# of tenders closed and due for adjudication) | None | None | Monthly Tender Reports | B&T | 81
Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | Target not achieved | 84/84 of quotations processed/# of quotations received) | DELAY S IN PROCESSING THEM | REGULAR MEETING FOR QUOTATION COMMITTEE | Quotations | Makhado Municipality | Administration | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | 100% (# of quotations processed/# of quotations received) | N/A | N/A | Target not achieved | 84/84 of quotations processed/# of quotations received) | DELAY S IN PROCESSING THEM | REGULAR MEETING FOR QUOTATION COMMITTEE | Quotations Report | B&T | 82
Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Target achieved | GRAP compliant Asset Register was updated | None | None | Asset Register | Makhado Municipality | Administration | Income | Operational | Operational | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | N/A | N/A | Target achieved | GRAP compliant Asset Register was updated | None | None | Schedules of Asset Register movement | B&T | 83

## LLED
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Start Date | End Date | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | No
5.4. LOCAL ECONOMIC DEVELOPMENT (L0WER SDBIP)
Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2016 | N/A | Development of Makhado information and recreational centre completed | Target achieved | Development of specifications, Advertisement of the project.The project was completed on time at a cost of R498 000,00 | None | None | Makhado N1 Information and Caravan Recreational/Entertainment centre | Makhado Municipality | Ward 20 | Income | 500000 | 100000 | 01/01/2016 | 30/06/2016 | Development of specifications, Advertisement of the project | Evaluation and adjudication of the tender, Appointment of the contractor | Removed during budget adjustment | Target achieved | Development of specifications, Advertisement of the project.The project was completed on time at a cost of R498 000,00 | None | None | Specifications, Appointment letter (contrcator) | DEVP | 84
Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2015 | Makhado annual show was hosted | Makhado annual show hosted | Target achieved | Makhado Annual Show hosted | None | N/a | Annual Show | Makhado Municipality | Ward 20 | Income | 159300 | 159300 | 1/7/2015 | 30/9/2015 | N/A | 168698.7 | 177 977.13.13 | N/A | N/A | N/A | N/A | Annual Show Report and Audited Financial Statements | DEVP | 85
Local Economic Development | Invest in local economy | # of LED projects supported by 30th June 2016 | 9 | 10 | Target not achieved | 6 LED/community based poverty elleviation projects funded | Delay in supply chain processes | To finalise specifications and advertise on time to avoid delay in procurement of goods and services. | LED Strategy | Makhado Municipality | All wards | Income | Operational | Operational | 1/7/2015 | 30/9/2016 | 10 | 100 | Project implementation plan, Project report | Target not achieved | 6 LED/community based poverty elleviation projects funded | Delay in supply chain processes | To finalise specifications and advertise on time to avoid delay in procurement of goods and services. | LED strategy implementation report | MM and DEVP | 86

## LGGPP
Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2014/2015) | Annual Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Project Name | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment Budget | Start Date | End date | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept | No
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (LOWER SDBIP)
Risk Management | Good governace and Administrative Excellence | To cordinate 13 risk management activities by 30 June 2016 | 13 activities were cordinated | 13 |  |  |  |  | Risk management activities | Makhado Municipality | OPEX | 1/7/2015 | 30/6/2016 | OPEX | 1/7/2015 | 30/6/2016 | 2 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Risk Management Committee Meeting held) | 3 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Operational Risk Assessment Report developed, Risk Management Committee Meeting held) | 3 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Strategic Risk Assessment for 2016/2017 done, Risk Management Committee Meeting held) | 5 risk activities (Risk Management Plan 2016/2017 developed, Review Risk Management Policy and Strategy, Fraud Policy Reviewed, Fraud Response Plan developed, Risk Management Committee Meeting held) | OPEX | Attendance register, Minutes and Programme |  |  |  |  | Attendance register, Minutes and Programme | MM | 86 A
Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Target achieved | 100% (1/1) | None | None | Fraud and Anti - Corruption | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | N/A | N/A | Target Achieved | 100% (0/0) | None | None | Case Register | MM | 87
Public Participation | Good governace and Administrative Excellence | To develop the public participation policy by 31 March 2016 | No policy | Public Participatuion policy approved by Council | Target not achieved | Public Participation on policy was not approved by Council | None | None | Public Participation Policy | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 31/3/2016 | Compile public participation policy and submit to Council for approval of Draft Policy | Finalise the draft policy. | Submit the draft to council. Advertise the policy for public comment. | Submit the final version of the Public Participation Policy to Council for approval |  |  | Target not achieved | Public Participation Policy was submited to Council for approval | The meeting that was supposed to be held didn’t happen | None | Approved policy Programmes and attendance register Final approve policy and advert for public comment | CORP | 88
Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 3o June 2016 | 456 | 456 | Target achieved | 456 ward committee meetings were coordinated | None | None | Support services for monthly ward committee meetings | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | 369,884 | 390,227 | Target achieved | 114 ward committee meetings and quarterly ward committees' report were submitted to Council | None | None | Minutes, Attendance register, Ward committee quarterly report | CORP | 89
Public Participation | Good governace and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | 2 | 2 | Target achieved | 2 ward comminttee training were done | None | None | Training of ward committees | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Approval of the memorandum by MM (1st training) | Training of 38 ward committees Compile a close out report (1st training) | Approval of the memorandum by MM (2nd training) | Training of 38 ward committees Compile a close out report (2nd training) |  |  | Target achieved | 38 ward committees were trained close out report (2nd training) compiled | None | None | Training attendance register; training curriculum | CORP | 90
Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 4 by laws reviewed | Target achieved | 4 by laws were reviewed | None | None | Reviewing of Municipal By-laws | Makhado Municipality |  | Income | 1/7/2015 | OPEX | 01/07/2015 | 30/06/2016 | Development of the 4 draft bylaws | Submit 4 draft bylaws to Council for provisional approval | Workshopping of Councillors and Public Participation on draft by laws | Final submission of the 4 bylaws to Council for final approval and publishing in Provincial Gazette | 900000 | 949000 | Target achieved | 4 by laws were approved by council and also promulgated wit provincial gazzete | None | None | 4 draft bylaws Provisional approved by Council , newspaper notice, attendance registers for public consultation, Final council resolutions and Promulgation notice for the 4 by laws in the provincial gazzete | CORP | 91
Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Target achieved | Three year rolling Audit plan is approved by APAC | None | None | Internal Audit 3 Year Plan | Makhado Municipality |  | Income | OPEX | OPEX | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | Approved three (3) year Internal Audit rolling plan and Annual plan | N/A | N/A | Target Achieved | Three year rolling Audit plan is approved by APAC | None |  | Copy of the plan | MM | 93
Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Target not achieved | 86% (12/14) Audit project performed | Delay in SCM processes to finalise the appointment of service provider | Appointment of service provider | Internal Audit Plan | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | 100% (# of projects executed/# of projects in the action plan) | N/A | N/A | Target not achieved | 67% (4/6) | Delay in SCM processes to finalise the appointment of service provider | Appointment of service provider | Internal Audit report to Audit and Performance Audit Committee | MM | 94
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | 7 | 7 | Target achieved | 100% (7/7) | None | None | Audit and Performance Audit Committee | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 3 | 2 | 1 | 1 | N/A | N/A | Target Achieved | 100% (1/1) | None |  | Minutes, Attendance register, invitations | MM | 95
Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | 4 | 4 | Target achieved | 100%(4/4) | None | None | Audit and Performance Audit Committee Reports | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | 1 | 1 | 1 | N/A | N/A | Target Achieved | 100% (1/1) | None |  | Council resolution, Attendance register | MM | 96
Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 2 | 2 | Target achieved | (1/1) | None | None | IAA and APAC Assessment report | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | N/A | 1 | N/A | 1 | N/A | N/A | Target Achieved | 100% (1/1) | None |  | Report, Council Resolution | MM | 97
Information Technology | Good governace and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Manual system | Computerized call center system | Target not achieved | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Upgrade municipal call center | Civic Center |  | Income | R3000,000 | 0 | 1/7/2015 | 30/6/2016 | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | Municipal call centre adjusted during budget adjustment | N/A | N/A | N/A | Municipal call centre adjusted during budget adjustment | CORP | 98
Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 december 2015 | Phase 1 done | Complete network upgrades | Target achieved | Network upgrades were completed | None | None | Upgrade network infrastructure | Civic Center and regional offices |  | Income | R200,000 | 159226 | 1/7/2015 | 31/3/2016 | Call for quotations and award the project | Install the networks hubs, switching and commissioning of the project | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Orders, Payment certificate and intallation report | CORP | 99
Information Technology | Good governace and Administrative Excellence | To upgrade the internet dataline by 31 March 2016 | Existing dataline too slow | Internet dataline upgraded | Target achieved | Internet dataline was upgraded | None | None | Internet dataline upgrade | Civic center |  | Income | R150,000 | R150,000 | 1/7/2015 | 31/3/2016 | Memorandum approval by the MM in terms TELKOM quotations | Official order to TELKOM and commissioning of upgrade | TELKOM complete the upgarde and payment out | N/A |  |  | N/A | N/A | N/A | N/A | Approved memorandum, TELKOM agrement, Close out report, Proof of payment | CORP | 101
Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Target achieved | Acceptable server room conditions | None | None | Replace UPS in server room | Civic Center |  | Income | R70,000 | 161816 | 1/7/2015 | 31/3/2016 | N/A | Appoint the service provider to supply ,deliver, install and commisioning UPS. | Signing off, sign service mantainance plan | N/A |  |  | N/A | N/A | N/A | N/A | Approved memorandumpurchase order, signed service mantainance plan | CORP | 102
Information Technology | Good governace and Administrative Excellence | To procure video editing software by 31 December 2015 | N/A | Procure video editing software | Target achieved | Video editing software was procured | None | None | Procure video editing software | Civic Center |  | Income | R10,000 | 14500 | 1/7/2015 | 2015-01-12 | Call for quotations | Award, procure and install | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Appointment letter, Installation, report; payment certificates, | CORP | 103
Information Technology | Good governace and Administrative Excellence | To procure ICT office equipment 31 March 2016 | 2014/15 critical needs only | According to needs analysis | Target not achieved | No ICT equipment was procured | Suitable service provide was not obtained | Review the approach of procuring ICT equipment | Procure ICT office equipment | Civic Center |  | Income | R200,000 | 155500 | 1/7/2015 | 31/12/2015 | Memorandum to MM for approval to standardise equipment and suace a single service provider registered in the field. | Evaluation of service providers sauced through SCM and appointment. Determine the institutional need and place order with the appointed service provider | Receive ordered equipments and allocate to users | N/A |  |  | Target not achieved | The selected sp was not registered in the SCM data base and could not furnish the compliance documents to be issued with an official municipal order; the closing date for any further procurement was 15 June 2016; we could not procure after finding that the preferred supplier was not able to comply | Quotation Committee did not entertain the DCS information at first that the selected supplier quoted for equipment that did not exist in the industry | DCS was not able to take any corrective measures as it is SCM prerogative; procurement of the listed equipment will start anew in Q1 of 2016/17 | Quotation Committee minutes and non-compliance by their selected supplier which is in posession of SCM section | CORP | 104
Information Technology | Good governace and Administrative Excellence | To procure hand held communication radios 30 September 2015 | N/A | 2 | Target achieved | 2 Radio and base radio was procured, installed and commissioned | None | None | Hand held communication radios | Civic Center |  | Income | R10,000 | R10,000 | 1/7/2015 | 30/9/2015 | Call for quotations and procure | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Appointment letter, payment certificates, | CORP | 105
Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Target achieved | Thirteen (13) Council meetings were convened | None | None | Council meeting | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | 1 | 2 | 2 | Operational | Operational | Target achieved | 3 Council meeting were convened | None | None | Minutes, Attendance register, notice of invitations. | CORP | 106
Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Target achieved | Twenty four (24) Executive Committee meetings were convened | None | None | Executive Committee Meetings | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 6 | 6 | 6 | 6 | Operational | Operational | Target achieved | 6 Executive Committee meeting scheduled | The Executive Committee meeting scheduled for 23 June 2016 did not form a quorum - the agenda stands over to Q1 of 2016/17 | None | Minutes, Attendance register, notice of invitations. | CORP | 107
Communication | Good governace and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | N/A | 2 | Target achieved | 2 x television sets procured | None | None | Television sets | Civic Center |  | Income | R20,000.00 | OPEX | 1/7/2015 | 30/9/2015 | Call quotations and procure | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP | 108
Communication | Good governace and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | N/A | 2 | Target achieved | 2 X decoders by procured | None | None | Decoders | Civic Center |  | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | Call quotations and procure | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Decoders and payment certificates | CORP | 109
Communication | Good governace and Administrative Excellence | To procure 2 X radios of regional broadcasting stations by 30 June 2016 | N/A | 2 | Target achieved | 2 X radios of regional broadcasting stations procured | None | None | Radios | Civic Center |  | Income | R800.00 | 2656 | 1/7/2015 | 30/9/2015 | Call quotations and procure | Concluded | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Radios and payment certificates | CORP | 110
Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Target achieved | Reviewed BathoPele Service Standards | None | None | Reviewed Bathopele service standards | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | Distribute for comments of all departments | Submit reviewed Service Standards to Council for approval | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Approved 2015 Batho Pele Service Standards | CORP | 111
Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Target achieved | Website policy was approved by Council | None | None | Comprehensive website policy | Civic Center |  | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | Submit to Council for approval | Implement website policy | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Council approval of policy | CORP | 112
Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Target achieved | 4 imbizos convene | None | None | Public Participation | Makhado Municipality |  | Income | OPEX | OPEX | 1/7/2015 | 30/6/2016 | 1 | 1 | 1 | 1 | N/A | N/A | Target achieved | Mayoral imbizo was convened | None | None | Attendance register and Programme | CORP | 113
Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Target not achieved | Imbizo feedback session not convened | None availability of the Mayor | To be done during financial year 2016/17 | Imbizo Feedback Session | Makhado Municipality | All wards | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | 1 | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Attendance register and program | CORP | 114
Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework BY 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Target achieved | Stakeholders Management Framework was reviewed | None | None | Review of Stakeholders Management Framework | Income | Ward 20 | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | 1 | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Approved Stakeholders management Framework and council resolution | CORP | 115
Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Target achieved | Communication Strategy was reviewed | None | None | Review of Communication Strategy | Income | Ward 20 | Income | OPEX | OPEX | 1/7/2015 | 30/9/2015 | 1 | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | Approved Communication strategy and council resolution policy and council resolution | CORP | 116