## COVER PAGE
MAKHADO LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
(HIGHER AND LOWER SDBIP)
FOR
2015/2016 FINANCIAL YEAR
AFTER ADJUSTMENT BUDGET

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction
2. Strategic Map, Vison and Mission
3. Departments
4. HIGHER LEVEL SDBIP
4.1. Municipal Transformation and Organisational Development
4.2. Baisc service Delivery
4.3. Local Economic Development
4.4. Municipal Finance Management and Viability
4.5. Good Governance and Public Participation
5. LOWER LEVEL SDBIP
5.1. Municipal Transformation and Organisational Development
5.2. Baisc service Delivery
5.3. Local Economic Development
5.4. Municipal Finance Management and Viability
5.5. Good Governance and Public Participation
6. Monthly Revenue and Expenditure
7. Monthly Revenue and Expenditure by Vote
8. Capital Cashflow
9. Capital Cashflow by Vote
10. Approval By The Mayor
Annexure A: Technical Indicator Description

## INTRO AND LEGISLATION
1. INTRODUCTION AND LEGISLATION
The SDBIP provides the vital link between the Mayor, Council (executive) and the Administration, and facilitates the process for holding management accountable for its performance. It is a management, implementation and monitoring tool that will assist the Mayor, Councilor, Municipal Manager, Senior Managers and community. A properly formulated SDBIP will ensure that appropriate information is circulated internally and externally for purpose of monitoring the execution of the budget, performance of senior management and achievement of the strategic objectives set by council. It enables the Municipal Manager to monitor the performance of Senior Managers; the Mayor to monitor the performance of the Municipal Manager; and the Ccommunity to monitor the performance of the Municipality. The SDBIP should therefore determine (and be consistent with) the performance agreements between the Mayor and the Municipal Manager and the Municipal Manager and Senior Managers determined at the start of every financial year and approved by the Mayor. Section 53 of the Municipal Finance Management act (Act no 56 of 2003), states that the Mayor of a municipality must- take all reasonable steps to ensure that the municipality approves its annual budget before the start of the budget and that the municipality's service delivery and budget implementation plan is approved by the mayor within 28 days after the approvaolf the budget.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system.
Section 54 (1)(c) of MFMA states that 54. (1) On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must— (a) consider the statement or report; (b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan; (c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget; (d) issue any appropriate instructions to the accounting officer to ensure— (i) that the budget is implemented in accordance with the service delivery and budget implementation plan; and (ii) that spending of funds and revenue collection proceed in accordance with the budget; (e) identify any financial problems facing the municipality, including any emerging or impending financial problems; and (f) in the case of a section 72 report, submit the report to the council by 31 January of each year.
In terms of MFMA Circular 13, the SDBIP is a layered plan, with the top layer of the plan dealing with consolidated service delivery targets and in-year deadlines, and linking such targets to top management. Once the top-layer targets are set, the top management is then expected to develop the next (lower) layer of detail of the SDBIP, by providing more detail on each output for which they are responsible for, and breaking up such outputs into smaller outputs and linking these to each middle-level and junior manager. Much of this lower layer detail will not be made public nor tabled in council – whilst the municipal manager has access to such lower layer detail of the SDBIP, it will largely only be the senior manager in charge who will be using such detail to hold middle-level and junior-level managers responsible for various components of the service delivery plan and targets of the municipality. Only the highest layer of information of the SDBIP will be made public or tabled in the council. Such high-level information should also include per ward information, particularly for key expenditure items on capital projects and service delivery – this will enable each ward councilor and ward committee to oversee service delivery in their ward.

## VIS MISS STRA MAP
2. VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Makhado Local Municipality is: “A dynamic hub for socio – economic development by 2025" The Mission of Makhado Local Municipality is: To ensure effective utilization of economic resources to address socio- economic imperatives through mining, tourism and agriculture Makhado Muncipality has identified 8 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:

## DEPARTMENTS
3. MAKHADO MUNICIPALITY DEPARTMENTS
Makhado Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3. Development Planning, 4. Budget and Treasury, 5. Technical Services, 6. Community Services

## HIGH LEVEL SDBIP
INDICATOR NO | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End Date | 3rd Q Targets | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
4.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
1 | Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2016/2017 completed and approved by Council by 31 May 2016 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2016, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2016 | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Draft IDP completed and submitted to Council for adoption by 31 March 2016 |  |  |  |  | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM
2 | Performance Management | Good governance and administrative excellence | To develop the SDBIP 2016/2017 and submit to the Mayor for signature within 28 days after approval of the budget | SDBIP 2015/2016 was developed and submitted to the Mayor within 28 days after approval of the budget | SDBIP 2016/2017 developed and submitted to the Mayor for signature within 28 days after approval of the budget | SDBIP Development | Collect information from departments, Develop a draft SDBIP, Submit to departments for inputs, Incorporate inputs and submit to council for approval by 31 March 2015. Submit to the Mayor for signature, Submit to council for noting. | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/4/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Signed SDBIP | MM
3 | Human Resources and Organizational Development | Invest in human capital | # of employee trained through WSP by 30 June 2016 | 114 | 135 | Training | Procure a dervice provider.Organise training venues.Monitor the project implementation. | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/4/2015 | 30/6/2016 | 3 |  |  |  |  | Proof of attendance | CORP
4 | Human Resources and Organizational Development | Invest in human capital | # of councilors trained through WSP by 30 June 2016 | 61 | 75 | Training | Procure a dervice provider.Organise training venues.Monitor the project implementation. | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/4/2015 | 30/6/2016 | 19 |  |  |  |  | Proof of attendance | CORP
5 | Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Organogram 2015/2016 was approved | Approved Organogram by may 2016 | Organogram review | Request department to make inpits. Consult with labour union. Submit to council for approval. | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Submit the draft organogram to Council for provisional approval. Consultation with organised labour | Target achieved | Organogram reviewed Approved by Council Resolution A.8.28.01.16 | None | None | Invitations to the depts, Minutes and attendance register, Council resolutions, | CORP
6 | Human Resources and Organizational Development | Invest in human capital | # of people from EEP target groups employed in three highest levels of management in compliance with approved EE Plan | 3 | 4 | Recruitment in terms of EE Plan | Appoint personel at the three highest level following the EE Plan | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Appointment letters | CORP
7 | Spatial and Town Planning | Advance Spatial Planning | % achievements of spatial programs indicators/targets per quarter | 100% (10/10) | 100% (16/16) | Permission to Occupy | Application received, Site visits, Stand demarcated and compile a report | Makhado Municipality | Administration | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (16/16) | Targert achieved | 100% (9/9 of application received/(9/9 of application attended to within 90 days). | None | None | Activity reports | DEVP
4.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
| Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Collection of waste in all the villages in ward 22, 23, 24, 25 and 26 | Magau,Ramantsa, | Ward 22, 23, 24, 25, 26. | INCOME | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 19149 (non cumulaitve) |  |  |  |  | Proof of collection from the affected stakeholders. | MM and COMM
8 | Parks and Recreation | Promote community and environmental welfare | # of parks to be developed by 30 June 2016 | 2 | 3 | Development of Parks | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | 5047 park,Civic Centre Park+ Tshirululuni/Meerkat | 20 & 21 | INCOME | 12000000 | 12000000 |  | 1/7/2015 | 30/6/2016 | N/A | Target achieved | Service provider has been appointed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
9 | Electricity Provision | Accessible basic and infrastructure services | # of households to be connected with electricity by 30 June 2016 | 1047 | 890 | Electrification of households | Implement all households connection project | Magau, Tshiozwi, Ramantsha, Madodonga,Mamburu, Makushu, Wisagalaza. | Ward 23,25,03 | INCOME | 21824299 | 22199786 |  | 1/7/2015 | 30/6/2016 | 179 |  |  |  |  | Proof of connections to targeted households | MM and TECH
10 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | Km of roads tarred by 30 June 2016 | 26km | 18.9km | Upgrading of roads from gravel to tar | Upgrading of roads from gravel to tar | Magau, Ledig, Chabani, Tshivhadzwaulu. | Ward 23, 21, 13,04 | MIG | 78199143.67 | 79361617 |  | 1/7/2015 | 30/6/2016 | 4.5km |  |  |  |  | Project progress report, Certificate of completion | TECH
11 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | # of bridges planned for construction by 30 June 2016 | 2 | 1 | Mudimeli bridge | Planning for construction of Mudimeli bridge | Mudimeli | Ward 37 | MIG | 5 758 786. - | 458786.11 |  | 1/7/2015 | 30/6/2016 | N/A | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Specifications, advertisement, appointment letter, project progress report | TECH
12 | Sports Facilities | Accessible basic and infrastructure services | # of sports facilities upgraded by 30 June 2016 | 2 | 1 | Upgrading of Vuwani sports facilities | Upgrading of Vuwani sports facilities | Vuwani | Ward 03 | MIG | 3892678 | 5592678 |  | 1/7/2015 | 30/6/2016 | N/A | Target achieved | Concrete pavillion completed | None | None | Project progress report, handover report | TECH
13 | Sports Facilities | Accessible basic and infrastructure services | # of sports facilities planned by 30 June 2016 | 1 | 1 | Planning of Waterval sports facilities | Planning of Waterval sports facilities | Waterval | Ward 16 | MIG | 1100000 | 1100000 |  | 1/7/2015 | 30/6/2016 | N/A | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Project progress report, handover report | TECH
14 | Building and Construction | Accessible basic and infrastructure services | # of graveyards to be developed by 30 June 2016 | 1 | 11 | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing | Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Ward 35, 25, 1,12,8,27,32,20 | MIG | 26700000 | 26700000 |  | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A | N/A | N/A | Advertisement copy, appointment letter,project progress report, handover report | TECH
4.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
15 | Expenditure management | Sound Financial Management and viability | % Capital budget spent by 30 June 2016 (Total budget spent/Total budget) | 75% (Total budget spent/Total budget) | 75 (Total budget spent/Total budget) | Capital Budget | Capture spending on capital project. Compile spending report in terms of section 71 report. | Makhado Municipality | Aministration | Income | 163938800.12 | 169,734,677.34 |  | 1/7/2015 | 30/6/2016 | 70% |  |  |  |  | Quarterly Financial Report | MM and All Directors
16 | Expenditure management | Sound Financial Management and viability | % MIG spent by 30 June 2016 | 75% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | MIG | Capture spending on MIG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Aministration | Income | 112264000 | 112264000 |  | 1/7/2015 | 30/6/2016 | 70% |  |  |  |  | Quarterly Financial Report | MM
17 | Expenditure management | Sound Financial Management and viability | % INEP Grants spent by 30 June 2016 | 100% (Total budget spent/Total budget) | 100% (Total budget spent/Total budget) | INEP | Capture spending on INEP project. Compile spending report in terms of section 71 report. | Makhado Municipality | Aministration | Income | 17000000 | 17000000 |  | 1/7/2015 | 30/6/2016 | 70% |  |  |  |  | Quarterly Financial Report | MM
18 | Expenditure management | Sound Financial Management and viability | % FMG by 30 June 2016 | 100% | 100% | FMG | Capture spending on FMG project. Compile spending report in terms of section 71 report. | Makhado Municipality | Aministration | Income | 1600000 | 1600000 |  | 1/1/2016 | 31/3/2016 | 100% (80000) |  |  |  |  | Expenditure Report | B&T
19 | Revenue Management | Sound financial management and viability | % revenue collected by 30 June 2016 | 90% | 90% (308004300) | Revenue Collection | Collection of payment for services such as electricity, property rates, refuse removal | Makhado Municipality | Aministration | Income | 342227123 | 342227123 |  | 1/7/2015 | 30/6/2016 | 70% |  |  |  |  | Section 71 report (c1 schedule) | B&T
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
20 | Local Economic Development | Invest in local economy | # of LED job opportunities created | 600 | 800 | LED job opportunities | Community works programme, Expanded public works programme, Community projects | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/06/2016 | N/A | N/A | N/A | N/A | N/A | EPWP, CWP, and Community Projects reports | MM and DEVP
4.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
21 | Risk Management | Good governace and Administrative Excellence | To cordinate 13 risk management activities by 30 June 2016 | 13 activities were cordinated | 13 risk activities cordinated | Risk Management project | Facilitate and coordinate risk management meetings | Makhado Municipality | Aministration | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 3 risk activities (Develop Quarterly Strategic Monitoring Risk Report, Strategic Risk Assessment for 2016/2017 done, Risk Management Committee Meeting held) |  |  |  |  | Attendance register, Minutes and Programme | MM
22 | Policies and By Laws | Good governace and Administrative Excellence | No of by laws to be reviewed by 30 June 2016 | 7 by laws reviewed | 4 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool, Pound, rationalise street trading, hawkers and markets into one bylaw. Street and diverse (public nuisance). | Makhado Municipality | Aministration | Income | 1/7/2015 | OPEX |  | 01/07/2015 | 30/06/2016 | Workshopping of Councillors and Public Participation on draft by laws | Target achieved | Workshopping of Councillors and Public Participation on draft by laws was held on 24 february 20 16 councilor briefing/ 9 March 2016 Dzanani/ 8 March 2016 Makahdo/ 1 March 2016 Ha Mutsha / 2 March Bungeni | Only challenge was in makhado nobody showup | None | 4 draft bylaws Provisional approved by Council , newspaper notice, attendance registers for public consultation, Final council resolutions and Promulgation notice for the 4 by laws in the provincial gazzete | CORP
23 | Internal Auditing | Good governace and Administrative Excellence | No of AG queries resolved by 30 June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality | Aministration | Income | OPEX | OPEX |  | 1/4/2015 | 30/6/2015 | N/A |  |  |  |  | Council Resolution, Copy of the plan | MM
24 | Internal Auditing | Good governace and Administrative Excellence | No of internal audit projects implemented | 9 | 9 | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality | Aministration | Income | OPEX | OPEX |  | 1/4/2015 | 30/6/2016 | N/A |  |  |  |  | Copy of the plan | MM
25 | Information Technology | Good governace and Administrative Excellence | No of IT projects implimented by 30 June 2016 | 8 | 8 | Upgrade municipal call center | Upgrade municipal call center from manual system to computerized logging, recording and referencing system and audio recording system according to needs of business units Phase 1 2015/2016 - the logging and referencing system Phase 2 - Audio recording system for 2016/2017 | Civic Center | Aministration | Income | R3000,000 |  |  | 1/7/2015 | 31/3/2016 | Adusted during budget adjustment |  |  |  |  | Advertisement for RFP | CORP
26 | Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality | Aministration | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 2 | Targert achieved | 2/2 of Council meeting convened | None | None | Minutes, Attendance register, notice of invitations. | CORP
27 | Communication | Good governace and Administrative Excellence | No of communication projects to be implemented by 30 June 2016 | 5 | 5 | Television sets | Procure and install television sets in the Office of the Speaker and the Office of the Chief Whip | Civic Center | Ward 20 | Income | R20,000.00 | N/A |  | 1/7/2015 | 30/9/2015 | N/A | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP
28 | Public Participation | Good governace and Administrative Excellence | No of public participation to be implemented by 30 June 2016 | 7 | 7 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality | All wards | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 1 | Target achieved | 1 imbizos convened on the 19 February 2016 at Mashau Village. | None | None | Attendance register and Programme | CORP

## LMTOD
INDICATOR NO | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expendindure | Start Date | End Date | 3rd Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (LOWER SDBIP)
1 | Integrated Development Planning | Good governance and administrative excellence | To review the IDP for 2015/2016 financial year by 31 May 2015 | IDP review for 2014/2015 was completed and approved by Council before 31 May 2014 | IDP review for 2015/2016 completed and approved by Council by 31 May 2015 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2016, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2016 | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Draft IDP completed and submitted to Council for adoption by 31 March 2016 | [6 empty] | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | MM
2 | Performance Management | Good governance and administrative excellence | Number of organisational performance reports developed and submitted to Council by 30 June 2015 | 8 | 8 | Quarterly performance reports | Develop a reporting template and send to departments, Receive completed template and consolidate into one report. Organise SDBIP Management meeting to consider the report. Submit the report to Council for approval. | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 4 (Mid Year Budget and Performance Assessment Report 2015/2016 in terms of section 72 MFMA, Draft and Final Annual Report 2014/2015, Oversight Report 2014/2015) | Operational | Operational |  |  |  |  | Draft Annual Report, Fourth Quarter SDBIP Report 2014/2015, First Quarter SDBIP Report 2015/2016, Mid Year Performance Report 2015/2016, Oversight, Final Annual Report, Council Resolutions | MM
3 | Performance Management | Good governance and administrative excellence | % Section 57 Managers with signed performance agreements by 30 June 2015 (# of managers with signed performance agreements/# of managers appointed) | 100% (3/3) | 100% | Performance agreements | Develop draft performance agreements. Engage the relevant Section 57 Managers. Submit the final performance agreement to Municipal Manager for signing. Submit the signed agreement to MEC for Cooperative Governance Human Settlement and Traditional Affairs. | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% | Operational | Operational |  |  |  |  | Signed Performance Agreements | MM
4 | Performance Management | Good governance and administrative excellence | # of section 57 managers individual assessment conucted by 30 June 2015 | 4 section 57 managers individual assessment conducted | 4 section 57 managers individual assessment conducted | Individual Performance Assessment | Write a memorandum for approval of panel members and dates. Invite the participate Conduct assessment and compile assessment report. | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 1 (Formal Assessment 2014/2015) | Operational | Operational |  |  |  |  | Scorecards, Attendance Register | MM
5 | Human Resources and Organizational Development | Invest in human capital | # of people from employment equity target groups employed in the three highest levels of management in compliance with a municipality's approved employment equity plan; |  | 4 |  |  | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | N/A |  |  | None | None | None | None | Employment equity | CORP
6 | Human Resources and Organizational Development | Invest in human capital | To review the Organogram by 30 June 2016 | Draft Organogram 2015/2016 | Approved Organogram by may 2016 | Organogram review | Reviewing of organizational structure | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Submit the draft organogram to Council for provisional approval. Consultation with organised labour | Operational | Operational | Target achieved | Organogram reviewed Approved by Council Resolution A.8.28.01.16 | None | None | Invitations to the depts, Minutes and attendance register, Council resolutions, | CORP
7 | Human Resources and Organizational Development | Invest in human capital | # of posts filled in terms of the approved priority list by 30 June 2015 | 67 employees appointed | 30 | Personnel Recruitment | Personnel Recruitment as per priority list | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | N/A | Advertisement and appointment letter |  | None | None | None | None | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP
8 | Human Resources and Organizational Development | Invest in human capital | # of employee programmes events conducted by 30 June 2016 | 6 events | 6 events | Employee Assistance Campaigns | Orgnanize and present Employee Assistance campaigns for all staff in all regions | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 1 event |  |  | Target achieved | 1 event was conducted date to be provided | None | None | Invitations, attendance registers and close-out report | CORP
9 | Human Resources and Organizational Development | Invest in human capital | To develop 3 outstanding HR policies by 30 June 2016 | No Tobacco Control Policy, Occupational Health & Safety Policy and Leave Policy | All 3 outstanding HR policies developed | Development of 3 outstanding HR policies | Compile Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy and submit to Council for approval- then implement | Makhado Municipality | 21 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Submit the draft policies to LLF for consultation |  |  | Target achieved | Policies were approved by LLF and then processed as recommended to Council | None | None | Approved 3 policies and the council resolutions (Tobacco Control Policy, Occupational Health & Safety Policy, and Leave Policy) | CORP
10 | Special Programs | Promote community and environmental welfare | To award 15 bursaries to qualifying learners by 30 June 2016 | 10 bursaries were awarded in 2014/15 | 15 bursaries awarded | External Bursary Award | 15 awards of bursary | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Award 15 bursaries to qualifying applicants | Operational | Operational | Target achieved | 1. Makhado Local Municipality Busary Committee meeting was held on the 22 February 2016 at Makhado Municipality Exco Chamber 19 bursaries were awarded | None | None | Advert, List of qualifying leaners and Letters of bursary awards | CORP
11 | Special Programs | Promote community and environmental welfare | # of activities conducted on special programs by 30 June 2016 | 49 events done in 2014/15 | 43 for 2015/16 | Special Programs | Organize and conduct the special programs undertaken in the different desks of the Special Programs Unit | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 12 | Operational | Operational | Target achieved | 12 events were done youth forum meeting forum were held on 31 March 2016 | None | None | Attendance registers, Signed minutes, Invitations, programs Close out report | CORP
12 | Spatial and Town Planning | Advance Spatial Planning | % application for PTO attended to within 90 days after receival. | 100% (# of application received/(# of application attended to within 90 days). | 100% (# of application received/(# of application attended to within 90 days). | Permission to Occupy | Application received, Site visits, Stand demarcated and compile a report | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of application received/(# of application attended to within 90 days). |  |  | Targert achieved | 100% (9/9 of application received/(9/9 of application attended to within 90 days). | None | None | Site inspection report, Register of applications | DEVP
13 | Spatial and Town Planning | Advance Spatial Planning | % Housing queries attended to within 30 days after receival. | 100% (# of housing queries attended within 30 days/# of received) | 100% (# of housing queries attended within 30 days/# of received) | Housing Coordination | Receive housing queries and attend to them in a form of meetings or written correspondence | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of housing queries attended within 30 days/# of received) |  |  | Targert achieved | 100% (25/25 of housing queries attended within 30 days/25/25 of received) | None | None | Complaints letters, Accounts applications, Corresponded letters with CFO | DEVP
14 | Spatial and Town Planning | Advance Spatial Planning | % building plans assessed by 30 June 2015 (# of building plans assessed/# of building plans received) | 100% processed | 100% | Building Plans | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Response to applicant in writing | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of building plans assessed/# of building plans received) | Operational | Operational | Targert achieved | 100% (116/116 of building plans assessed/116/116 of building plans received) | None | None | Building plans register | DEVP
15 | Spatial and Town Planning | Advance Spatial Planning | % of zoning certificates issued by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Zoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Targert achieved | 100% (7/7 of applications processed/7/7 applications received) | None | None | Zoning certificates issued | DEVP
16 | Spatial and Town Planning | Advance Spatial Planning | % rezoning, subdivision, special consent and consolidation applications assessed by 30 June 2015 (# of applications processed/# applications received) | 100% processed | 100% (# of applications processed/# applications received) | Rezoning of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# applications received) | Operational | Operational | Targert achieved | 100% (15/15 of applications processed/15/15 applications received) | None | None | EXCO resolutions | DEVP
17 | Spatial and Town Planning | Advance Spatial Planning | % application for land use rights inspection conducted within 14 days | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) | Land Use Management | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of application for land use rights inspection conducted within 14 days/# of application received) |  |  | Targert achieved | 100% (7/7 of application for land use rights inspection conducted within 14 days/7/7 of application received) | None | None | Site inspection report, Register of applications | DEVP
18 | Spatial and Town Planning | Advance Spatial Planning | % certificates of occupancy issued by 30 June 2015 (# of applications processed/# of applications received) | 100% processed | 100% (# of applications processed/# of applications received) | Occupancy of land | Application received, Site visits, for assessment. Development plan committee sit and check the plan. Submit the report to Council for approval. Response to applicant in writing. | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of applications processed/# of applications received) | Operational | Operational | Targert achieved | 100% (4/4 of applications processed/4/4 of applications received) | None | None | Copy of occupancy certificates issued | DEVP
19 | Spatial and Town Planning | Advance Spatial Planning | % application for pegging attended to within 15 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Pegging Applications | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Targert achieved | 100% (99/99 of applications processed/ 99/99 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
20 | Spatial and Town Planning | Advance Spatial Planning | % application for demarcation of new site attended to within 30 days after receival. | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Demarcation of sites | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Targert achieved | 100% (24/24 of applications processed/24/24 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
21 | Spatial and Town Planning | Advance Spatial Planning | % property application processed within 30 days of receival | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Application received, Site visits, development plan committee sits, Generate report to council, Notify the client | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Targert achieved | 100% (7/7 of applications processed/ 7/7 of applications received) | None | None | Application Assessment Report, Register of applications | DEVP
22 | Spatial and Town Planning | Advance Spatial Planning | % request for use municipal property processed within 5 days | 100% (# of applications processed/# of applications received) | 100% (# of applications processed/# of applications received) | Property application | Receive application, Send to MM for approval, Notify the applicants to go and pay, After receiving the proof of payment a venue is booked. | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of applications processed/# of applications received) |  |  | Target achieved | 100% (65/65 of applications processed/ 65/65 of applications received) | None | None | Bookings register | DEVP
23 | Spatial and Town Planning | Advance Spatial Planning | % land claims queries coordinated within 30 days after receival | 100% (# of queries processed/# of queries received) | 100% (# of queries processed/# of queries received) | Land Claims | Receive complaints, Liaise with the commissioner and complainant, Arrange a meeting if need | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of queries processed/# of queries received) |  |  | Target achieved | 100% (1/1 of queries processed/ 1/1 of queries received) | None | None | Correspondence letters and emails. | DEVP
24 | Spatial and Town Planning | Advance Spatial Planning | % by law contraventions notices issued within 5 days after identification | 100% (# of contravention notices issued within 5 days/# of contravention identified) | 100% (# of contravention notices issued within 5 days/# of contravention identified) | By Law Enforcement | Conduct inspection, Upon identifying a contravention a notice is issued | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | 100% (# of contravention notices issued within 5 days/# of contravention identified) |  |  | Target achieved | 100% (13/13 of contravention notices issued within 5 days/13/13 of contravention identified) | None | None | Duplicate notices | DEVP
25 | Spatial and Town Planning | Advance Spatial Planning | # of routine inspection conducted by 30 June 2015 | 240 | 240 | Routine Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 60 |  |  | Target achieved | Routine inspections conducted | None | None | Inspection form, Register | DEVP
26 | Spatial and Town Planning | Advance Spatial Planning | % site inspection applications done within 24 hours | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) | Site Inspection | Inspect the area, If find contravention issues notice, If no respond final notice issued, If no response a fine is written, if no response the matter is taken to legal | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of site inspections conducted within 24 hours/# of site inspections application received) |  |  | Target achieved | 100% (57/57 of site inspections conducted within 24 hours/# of site inspections application received) | None | None | Inspection form, Register | DEVP
27 | Spatial and Town Planning | Advance Spatial Planning | To name the streets in the R293 townships by 30 June 2015 (Dzanani) | Consultation/ Establishment of committees/Some names completed | Provision of street names for R293 towns completed | Street Naming (Dzanani) | Conduct public consultation on street names. Compile a list of street names for approval by Council. | Makhado Municipality | 33 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Draft Street Names | 200000 | 200000 | Target not achieved | Advert done , non responsive bidders quoted | Non responsive bidders | Re advert done after non responsive bidders quoted | Expenditure Report | DEVP

## LBSD
INDICATOR NO | Priority Issue | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjusted budget | Expenditure | 3rd quarter | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio of Evidence | Dept
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (LOWER SDBIP)
28 | Disaster Management | Promote community and environmental welfare | To review the Disaster Management Plan and by 30 June 2016 | Disaster Management Plan was reviewed and included to the IDP for 2015/2016 | Disaster Management Plan reviewed and included to the IDP for 2016/2017 | Annual Revision of the Disaster Management Plan | Write a request letter to sector departments and municipal regional offices. Requesting information about new buildings and new employees in key positions e.g circuit managers. Receiving information form stakeholders. Update received informkation into the Disaster Management Plan. Draft Disaster Management Plan completed. Submission of the Disaster Management Plan to the IDP Manager for submission to Council | Makhado Municipality | Ward 20 | Income | Operational | Operational |  | Update received information into the Disaster Management Plan. Draft Disaster Management Plan completed. | Target achieved | Disaster management plan updated | None | None | Letter of request Copies of received information Draft Disaster Management Plan Final Reviewed Disaster Management Plan | COMM
29 | Library Services | Promote community and environmental welfare | To Refurbish the library roof by 30 June 2016 | Roof damaged | Refurbishment of the library building completed | Refurbish library building | Development of specifications, Advertisement for Contractor. Evaluation, Adjudication and Appointment of Contractor. Construction of roof. Finalisation of the roof and handing over | Makhado Municipality | Ward 20 | Income | 1000000 | 200000 |  | Construction of roof | Target not achieved | Designs for the roof are available | Insufficient budget for construction. Budget was reduced to cater for designs in the current FY | To advertise for construction in 2016/17 | Project Progress report | TECH
30 | Waste Management | Promote community and environmental welfare | # of households with access to refuse removal | 46637 | 19149 | Waste Management | Coolection of waste in all the villages in ward 22, 23, 24, 25 and 26 | MADODONGA | Ward 22, 23, 24, 25, 26. | Income | Operational | Operational |  | N/A | N/A | N/A | N/A | N/A | Monthly collection reports | MM and COMM
31 | Waste Management | Promote community and environmental welfare | To develop the Landfillsite and recycling centre by 30 June 2016 | N/A | Landfill site makhado + recycling centre is completed | Development of | Approval to commence with the project from the MM, Development of specification and submit to SCM. Advertisent for tendering. Evaluation, Adjudication and appointment of a service provider. Development of designs and drawings, Construction of 1 x evaporation ponds (excavation, levelling, linning) | Tshikota | Ward 21 | MIG | 5 000 000.00 - | 5599366.72 |  | Development of designs and drawings (Geotechnical report) | Target achieved | Tender advertised done | None | None | Approval memo, Specifications, Advertisement copy, Appointment letter, Geaotech report | COMM
32 | Waste Management | Promote community and environmental welfare | To rehabilitate the landfill site by 30 June 2016 | N/A | Landfill site rehabilitated ompleted | Rehabilitation of the existing Landfill site (Vondelling) | Write memorandum of approval to MM. Development of specifications and submit to the BSC. Advertisement of the tender. Evaluationa nd Adjudication of tenders. Appointment of a service provider. Seek quotation for levelling and caping waste with soil and complete the process. Inustallation of leachete collection pipes. Construction of leachete collection dam. | Makhado Municipality | 21 | INCOME | 4000000 | 3083000 |  | Seek quotation for levelling and caping waste with soil. | Target achieved | Camping and levelling done | None | None | Geotechnical report | TECH
33 | Parks and Recreation | Promote community and environmental welfare | To development of 5047 Park by 30 June 2016 | N/A | Development of 5047 Park completed | Development of 5047 Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | 5047 Park | Ward 20 | INCOME | 700000 | 700000 |  | Appointment of service provider. | Target achieved | Service provider appointed done | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
34 | Parks and Recreation | Promote community and environmental welfare | To develop the N1 recreational park by 30 June 2016 | N/A | Development of N1 recreational park completed | Development of N1 recreational park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Makhado Municipality | Ward 21 | INCOME | 0 | 0 |  | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Approval memo. RFP, appointment letter, Completion certificate | COMM
35 | Parks and Recreation | Promote community and environmental welfare | Refurbishment and Upgrading of Civic Centre Park+ Meerkat park | N/A | Refurbishment and Upgrading of Civic Centre Park+Meerkat park completed | Refurbishment and Upgrading of Civic Centre Park and Meerkat Park | Approval to commence with the project from the MM. Request for proposal from service providers.Appointment of service providers. Development of the park in line with the proposal. Complete the development of the park | Civic Centre Park | Ward 20&21 | INCOME | 500000 | 500000 |  | Appointment of service providers. | Target achieved | Service provider has been appointed | None | None | Approval memo. RFP, appointment letter, Completion certificate | COMM
36 | Electricity Provision | Accessible basic and infrastructure services | To connect 50 households at Magau by 30 June 2016 | N/A | 50 households at Magau completed | MAGAU | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, switching on and completion of the project | Magau | Ward 23 | INCOME | 935201.32 (INCOME) 712 000 (INEP) | 935201.32 (INCOME) 712 000 (INEP) |  | Complete MV and LV networks. | Target achieved | MV and LV networks completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
37 | Electricity Provision | Accessible basic and infrastructure services | To connect 40 households at TSHIOZWI /GOGOBOLE by 30 June 2016 | N/A | 40 households connected at TSHIOZWI /GOGOBOLE | TSHIOZWI & GOGOBOLE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on. Completion of the project | Tshiozwi Gogobole | Ward 23 | INCOME | 2101576 | 2101576 |  | Completion of MV and LV networks. | Target not achieved | MV and LV networks completed at Tshiozwi and still busy at Gogobole | Slow progress | Impose penalties | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH | TECH
38 | Electricity Provision | Accessible basic and infrastructure services | To connect 96 houuseholds at Ramantsha/Riverside by 30 June 2016 | N/A | 96 households at Ramahantsha /Riverside completed | RAMANTSHA/RIVERSIDE | Development of specifications, approval of specs, Advertisement for appointment contractor, Evaluation, Adjudication and appointment. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | RAMANTSHA/RIVERSIDE | Ward 23 | INCOME | 1281962 | 1281962 |  | 96 Service connections completed, Switching on and completion of the project | Target achieved | 97 house connections completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
39 | Electricity Provision | Accessible basic and infrastructure services | To connect 83 households at Madodonga/Manavhela by 30 June 2016 | N/A | 83 households at Madodonga/Manavhela completed | MADODONGA | Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate. Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors. Service connections, Switching on and completion of the project | MADODONGA | Ward 25 | INCOME | 1681261 | 1681261 |  | 83 Service connections completed, Switching on and completion of the project | Target achieved | 83 house connections completed | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
40 | Electricity Provision | Accessible basic and infrastructure services | To connect 120 households at Mamburu by 30 June 2016 | N/A | 120 households at Mamburu completed | Mamburu | Development of specifications, Advertisement for engineer and contractor, Evaluation and Adjudication. Appointment of engineer and contractor, Site handover to contractor, site establishment, appointment of labour, Surveying of pole holes. Excavating the pole holes dresing and planting of poles, stringing of conductors. Partial handover certificate, AS build drawings, Closing of spans, energising and testing, switching on and final handover and completion certificate | Mamburu | Ward 25 | INEP | 2250000 | 2250000 |  | Planting of poles. | Target achieved | Poles were planted | None | None | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
41 | Electricity Provision | Accessible basic and infrastructure services | To connect 30 households at Makhushu by 30 June 2016 | N/A | 30 households at Makhushu completed | MAKUSHU | Development specification for contractor, materials and works, Approval of specification, advertisement, evaluation, adjudication and appointment. Site handover to the contractor, site establishment, appointmnet of labour, survying pole holes, excavating poleholes, dress and plant pole holes and string of conductors. Service connections. Switching on and completion of the project | MAKUSHU | Ward 25 | INEP | 490000 | 490000 |  | Planting of poles, | Target not achieved | Planting of poles in progress | Delays in submission of designs | Designs were submitted | Specifications, Advertisement, Contractor appointment letter, Site handover minutes or report, Project report | TECH
42 | Electricity Provision | Accessible basic and infrastructure services | Designs for Vyeboom 2016/2017 electrification projects ) by 30 June 2016 | N/A | Designs for Vyeboom 2016/2017 electrification projects completed | Designs for Vyeboom 2016/2017 electrification projects | Development of specification for engineer, approval of specs, Advertisement. Evaluation, Adjudicationa nd appointment of the engineer.Completion of designs, designs approval by ESKOM, technical electrification forum meeting. | Vyeboom village | Ward 3 | INEP | 952500 | 952500 |  | Evaluation, Adjudicationa nd appointment of the engineer. | Target achieved | Project was handed over to ESKOM with complete designs | None | To be removed from list of MLM projects | Specifications, Advertisement, appointment letter, Designs, Minutes of of technical forum meeting | TECH
43 | Electricity Provision | Accessible basic and infrastructure services | To upgrade 3km Industrial line by 30 June 2016 | N/A | Upgrading 3km Industrial line | Upgrading 3km Industrial line | Planning and designs, appointment of labour, procurement of PPE, prepare alternative supply, bush clearing phase 1, pegging phase 1, excavating of pole holes for phse 1. Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. bush clearing phase 2, pegging phase 2, excavating pole holes phase 2.Dress and plant poles phase 2, strining of conductors phase 2, closing spans phase 2 | Makhado Municipality | Ward 21 | INCOME | 250000 | 250000 |  | Dress and plant poles phase 1, stringing of conductors phase 1, closing spans phase 1, prepare alternative supply. | Target not achieved | In the process of delivering poles | Breakdown of pole truck | Truck was repaired | Designs, Appointment letter for labourers, Project progress report, | TECH
44 | Electricity Provision | Accessible basic and infrastructure services | To upgrade 4.5km Shefeera Line by 30 June 2016 | N/A | Upgrade 4.5km Shefeera Line | Upgrade 4.5km Shefeera Line | Upgrade Shefeera Line. Appointment of labour, procurement of PPE, bush clearing and pegging. Excavating pole holes, dress and plant poles. Stringing of conductors, closing spans | Makhado Municipality | Ward 21 | INCOME | 600000 | 512999 |  | Stringing of conductors. | Target achieved | Stringing of conductors completed | None | None |  | TECH
45 | Electricity Provision | Accessible basic and infrastructure services | To upgrade Urban Substations by 30 June 2015 | N/A | Upgrade Urban Substations | Upgrade Urban Substations | Upgrade Urban Substations. Completion of upgarde designs, contractor specification compilation. Advertisent for tendering. Evaluation. Adjudication and appointment of contractor.Procurement of upgrade equipment fo Stubb street substation | Makhado Municipality | Ward 20 | INCOME | 2500000 | 2500000 |  | Evaluation and adjudication . | Target achieved | Evaluation and adjudication completed | Inadequate funds | Funds moved to electrification |  | TECH
46 | Electricity Provision | Accessible basic and infrastructure services | To upgrade 5km Mountain line by 30 June 2016 | N/A | Upgrading 5km Mountain line | Upgrading 5km Mountain line | Planning and designs, appointment of labour, procurement of PPE, bush clearing and, pegging, excavating of pole holes. Dress and plant poles, stringing of conductors. closing spans, pegging, exate pole holes. Dress and plant poles, strining of conductors, closing spans | Makhado Municipality | Ward 30 | INCOME | 250000 | 250000 |  | Dress and plant poles. | Target not achieved | In the process of delivering poles | Breakdown of pole truck | Truck was repaired |  | TECH
47 | Electricity Provision | Accessible basic and infrastructure services | To upgrade and reroute 2.2km Beaufort West line by 30 June 2016 | N/A | Upgrade and reroute 2.2km Beaufort West line completed | Upgrade and reroute 2.2km Beaufort West line | Surveying of the pole holes and excavating pole holes | Beaufort West line | Ward 30 | INCOME | 1500000 | 1500000 |  | Appointment and site handover. | Target achieved | Appointment and site handover completed | None | None | Specification, approved memo, appointment letter, site establishment report, project progress report | TECH
48 | Electricity Provision | Accessible basic and infrastructure services | To replace oil curcuit breaker by 30 June 2016 | N/A | Replacement of oil curcuit breaker completed | Oil curcuit breaker replacement | Replace oil curcuit breaker | Main substation | Ward 21 | INCOME | 400000 | 400000 |  | Appointment of supplier. | Target achieved | Two OCBs were delivered. Await delivery of the 3rd OCB from the manufacturer | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
49 | Electricity Provision | Accessible basic and infrastructure services | To replace channel cover by 30 June 2016 | N/A | Replacement of channel cover completed | Substation channel cover replacements | Replacement of channel cover | Makhado Municipality | All wards | INCOME | 0 | 0 |  | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH
50 | Electricity Provision | Accessible basic and infrastructure services | To install the Standby (Backup) Electricity Power Generator-Dzanani by 30 June 2016 | N/A | Standby generator installed | Standby (Backup) Electricity Power Generator-Dzanani | Installation of standby generator | Dzanani | 33 | INCOME | 250000 | 250000 |  | Appointment of service provider and completion of project. | Target achieved | Project completed | None | None | Specification, Approval memo, Advertisement, appointment letter, project progress report | TECH
51 | Electricity Provision | Accessible basic and infrastructure services | To replace air conditioner by 30 Septemeber 2015 | N/A | Air Conditioners replaced | Air Conditioners | Replacement of air conditioner | Municipal area | All municipal office | INCOME | 150000 | 450000 |  | Quotations , Installations and invoice | Target achieved | Completed 258 units major service | None | None | Orders and project progress report | TECH
52 | Electricity Provision | Accessible basic and infrastructure services | To replace CT VT Units 11kv & 22kv by 30 June 2016 | N/A | CT VT Units 11kv & 22kv replaced | CT VT Units 11kv & 22kv | Replacement of CT VT Units 11kv & 22kv | Makhado | All municipal areas | INCOME | 300000 | 300000 |  | Adjusted during budget adjustment | n/a | Funds re-allocated |  |  | Specification, Approval memo, Advertisement, appointment letter, project progress report, payment certificate | TECH
53 | Electricity Provision | Accessible basic and infrastructure services | To upgrade Low voltage to medium voltage in Rural Farming B9, T8, A21 and G23/24 by 31 March 2016 | N/A | Low voltage to medium voltage in Rural Farming B9,T8 and A21 Vupgraded | Low voltage to medium voltage in Rural Farming B9,T8 and A21 | Ugrading Low voltage to medium voltage , B9,T8 and A21 | Makhado | All municipal areas | INCOME | 250000 | 358000 |  | A21 completed | Target achieved | Completed A21 | None | None | Project progress report | TECH
54 | Electricity Provision | Accessible basic and infrastructure services | To replace Mini Subs by 31 December 2015 | N/A | Mini Subs replaced | Mini Subs | Replacement of Mini Subs | Makhado | All municipal areas | INCOME | 900000 | 444000 |  | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH
55 | Electricity Provision | Accessible basic and infrastructure services | To replace MV Cable 95 mm 22kv by 31 December 2015 | N/A | MV Cable 95mm 22kV replaced | MV Cable 95mm 22kV | Replacement of MV Cable 95mm 22kV | Makhado | All municipal areas | INCOME | 150000 | 117000 |  | N/A | N/A | N/A | N/A | N/A | Specification, orders, delivery notes | TECH
56 | Electricity Provision | Accessible basic and infrastructure services | To procure Recloser and controllers whole network 31 December 2015 | N/A | Recloser and controllers whole network procured | Recloser and controllers whole network | Procure, supply and delivery of recloser and controllers whole network | Makhado | All municipal areas | INCOME | 700000 | 700000 |  | Delivery of materilals. | Target not achieved | SP appointed and ordered the material | SP awaiting delivery of material | Follow-up with the supplier | Specification, orders, delivery notes, progress report, completion certificate | TECH
57 | Electricity Provision | Accessible basic and infrastructure services | To procure Remote control of switch gear Tshipise & Levubu by 30 June 2016 | N/A | Remote control of switch gear Tshipise & Levubu procured | Remote control of switch gear Tshipise & Levubu | Procure, supply and delivery of remote control of switch gear Tshipise & Levubu | Makhado | All municipal areas | INCOME | 120000 | 180000 |  | Appointment of supplier and delivery | Target not achieved | SP appointed and ordered the material | SP awaiting delivery of material | Follow-up with the supplier | Specification, advertisement, appointment letter, payment certificate | TECH
58 | Electricity Provision | Accessible basic and infrastructure services | To replace Ring Main Units 11 kV ( RMU) by 31 March 2016 | N/A | Ring Main Units 11 kV ( RMU) delivered and installed | Ring Main Units 11 kV ( RMU) | Replacement of Ring Main Units 11 kV (RMU) | Makhado | All municipal areas | INCOME | 300000 | 306740 |  | Project competion and payment certificate | Target achieved | Completed | None | None | Specification, order, delivery note, project progress report, payment certificate | TECH
59 | Electricity Provision | Accessible basic and infrastructure services | To constuct Standby quarter perimeter wall by 31 March 2016 | N/A | Standby quarter perimeter wall compeleted | Standby quarter perimeter wall | Construction of standby quarter perimeter wall | Makhado | All municipal areas | INCOME | 60000 | 300000 |  | Plastering and painting | Target not achieved | Building in progress | No Bricklayer and Service Worker assisting | Fill the vacancy of the Bricklayer | Specification, advertisement, project progress report | TECH
60 | Electricity Provision | Accessible basic and infrastructure services | To construct Standby quarter guard room by 31 March 2016 | N/A | Standby quarter guard room completed | Standby quarter guard room | Construction of standby quarter guard room | Makhado | All municipal areas | INCOME | 250000 | 250000 |  | Construction of brickwork (internal staff). Wall completion | Target not achieved | Part of the perimeter wall project | No Bricklayer and Service Worker assisting | Fill the vacancy of the Bricklayer | Specification, advertisement, project progress report | TECH
61 | Electricity Provision | Accessible basic and infrastructure services | To connect 471 households at at Wisagalaza village by 30 June 2015 | Site establishment | Wisagalaza village 471 connection completed | Wisagalaza 2 & Chitasi village | Electricity connections | Wisagalaza village | 8 | INEP | 7771500 | 8826487.19 |  | Service connections | Target achieved | Service connections completed | None | None | Appointment letter, project progress report, completion certificate | TECH
62 | Electricity Provision | Accessible basic and infrastructure services | To connect 87 households at SUKANI by 30 June 2016 | N/A | Planting of poles done for SUKANI 87 connections. | SUKANI | Electricity connections | SUKANI | Ward 8 | INEP | 1392000 | 1392000 |  | Completion of designs. | Target achieved | Designs completed. Site handover done and work in progress | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
63 | Electricity Provision | Accessible basic and infrastructure services | To connect electricity at TSHIVHULANA by 30 June 2016 | N/A | TSHIVHULANA connection completed | TSHIVHULANA zone 5 | Electricity connections | TSHIVHULANA zone 5 | Ward 1 | /INCOME INEP | 1632000 | 0 |  | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
64 | Electricity Provision | Accessible basic and infrastructure services | To connect 150 households at Ratombo/ by 30 June 2016 | N/A | Stringing of MV and LV conductors done for RATOMBO 150 connections. | RATOMBO | Electricity connections | RATOMBO | 32 | INEP /income | 1472000 | 1472000 |  | Planting of poles, | Target achieved | Poles were planted | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
65 | Electricity Provision | Accessible basic and infrastructure services | To connect 53 households at Freedom and Lusaka (Tshivhuyuni) by 30 June 2016 | N/A | planting of poles done for Freedom and Lusaka (Tshivhuyuni) 53 households connections | Freedom and Lusaka (Tshivhuyuni) | Electricity connections | Freedom and Lusaka (Tshivhuyuni) | 12 | INEP | 1040000 | 1040000 |  | Completion of designs. | Target achieved | Designs completed. Site handover done and work in progress | None | None | Specifications, advertisement, appointment letter, Designs, Minutes of site handover, labourer appointment report, project progress report | TECH
66 | Electricity Provision | Accessible basic and infrastructure services | Electrification Rabali Stadium by 30 June 2016 | N/A | Electrification Rabali Stadium facility completed | Electrification Rabali Stadium | Electrification Rabali Stadium | Rabali stadium | Ward32 | Income | 150000 | 150000 |  | Appointment of service provider and completion of project. | Target achieved | Completed | None | None | Specifications, Advertisement, Apointment letter, delivery notes, | TECH
67 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To process payment (300000) for construction of Tshikota/Pretorious access road by 30 June 2016 | Gravell road | Payment for construction of Tshikota/ Pretorious access road done. (300000) | Payment of Tshikota/Pretorious construction of streets | Process payment for Tshikota/Pretorius construction of streets | Makhado and Tshikota towns | Ward 21 | MIG | 1936405 | 1936405 |  | N/A | N/A | N/A | N/A | N/A | Project progress report, handover report | TECH
68 | Roads, Bridges and Stormwater | Accessible basic and infrastructure services | To upgrade Magau road (4.5km) phase 2 by 30 June 2016 | Gravell road | Magau road phase 2 completed | Magau road phase 1 | Magau road phase 1 | Magau | Ward 23 | MIG | 22000000 | 21848466.41 |  | Surfacing of the road and handing over. | Target not achieved | Handing over re-scheduled due to snag list | None | None | Project progress report, Completion certificate, handover report | TECH
69 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To process payment (300000) for construction of Tshivhulana to Tshilaphala access road by 30 June 2016 | Gravell road | Payment for construction of Tshivhulana to Tshilaphala access road done. (3000000) | payment of Tshivhulana to Tshilaphala construction of streets | Process payment for Tshivhulana to Tshilaphala construction of streets | Tshivhulana and Tshilaphala | Ward 1 | MIG | 4576988 | 3000000 |  | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Adjusted during budget adjustment | Specifications, advertisement, appointment letter, project progress report | TECH
70 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Ledig road(6.6km) by 30 June 2016 | Gravell road | Ledig road completed | Ledig road | Ledig road construction | Ledig | Ward 21 | MIG | 9387156 | 15403183.1 |  | N/A | N/A | N/A | N/A | N/A | Project progress report, handover report | TECH
71 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To upgrade Robert Khoza /Chabani -Bungeni road(3.5km) by 30 June 2016 | N/A | Robert Khoza /Chabani Bungeni road completed | Robert Khoza /Chabani Bungeni road construction | Robert Khoza /Chabani Bungeni road | Robert Khoza /Chabani Bungeni road | Ward 13 | MIG | 23000000 | 19689296.81 |  | Construction of bridge structure and deck. Finalising roadbase | Target not achieved | Bridge not complete | Slow progress | To complete the project by 30/06/2016 | Site establishment report, project progress report, handover report | TECH
72 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct Tshivhazwaulu to Rasivhetshela road(4.3km) phase 1 by 30 June 2016 | N/A | Tshivhazwaulu to Rasivhetshela road phase 1 completed | Tshivhazwaulu to Rasivhetshela road phase 1 | Tshivhazwaulu to Rasivhetshela road phase 1 | Makhado Municipality | Ward 4 | MIG | 23811987.67 | 22420672.11 |  | Surfacing of the road and stormwater drains | Target achieved | Surfacing and stormwater drains complete | None | None | Site establishment report, project progress report, handover report | TECH
73 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To construct a new bridge at Mudimeli by 2018 | N/A | Mudimeli bridge completed by 2018 | Mudimeli bridge | Construction of Mudimeli bridge | Makhado Municipality | Ward 37 | MIG | 5 758 786. - | 458786.11 |  | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Specifications, advertisement, appointment letter, project progress report | TECH
74 | Roads, Bridges and Storm water | Accessible basic and infrastructure services | To do planning for roads and bridge projects by 30 June 2016 | N/A | Planning for Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road completed | Tshikwarani to Zamkomst Tshirolwe, Matsa to Manyii , Tshedza to Vuvha ,Sibudi to Vyeboom, access road Gombiti,Tshivhuyuni, Muwaweni to Mphage road | Planning of new road/bridges | Makhado Municipality | Ward 25, 25, 36,30,3,15,12, | MIG | 1 600 000 | 1 600 000 |  | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Advertisement copy, appointment letter, design report. | TECH
75 | Sports Facilities | Accessible basic and infrastructure services | To upgrade of Vuwani sports facilities by 30 June 2016 | N/A | Upgrading of Vuwani sports facilities completed | Upgrading of Vuwani sports facilities | Upgrading of Vuwani sports facilities | Makhado Municipality | Ward 3 | MIG | 2492678 | 4492677.57 |  | Completion of concrete pavillion | Target achieved | Concrete pavillion completed | None | None | Project progress report, handover report | TECH
76 | Sports Facilities | Accessible basic and infrastructure services | To do planning for Waterval sports facility by 30 June 2016 | N/A | Planning for Waterval sports facility completed. | Planning for Waterval sports facility. | Planning for Waterval sports facility. | Makhado Municipality | Ward 16 | MIG | 1100000 | 1100000 |  | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of SP completed | None | None | Advertisement copy, appointment letter, design report. | TECH
77 | Sports Facilities | Accessible basic and infrastructure services | To construct ablution facility by 30 June 2016 (Waterval Stadium) | N/A | Provision of Waterval stadium ablution facility completed | Construction of ablution facility at Waterval stadium | Construction of ablution facility at Waterval stadium | Makhado Municipality | Ward 16 | MIG | 300000 | 0 |  | Adjusted and combined with palisade for Waterval stadium during budget adjustment | Adjusted and combined with palisade for Waterval stadium during budget adjustment | Adjusted and combined with palisade for Waterval stadium during budget adjustment | Adjusted and combined with palisade for Waterval stadium during budget adjustment | Adjusted and combined with palisade for Waterval stadium during budget adjustment | Advertisement copy, appointment letter, design report. | TECH
78 | Building and Construction | Accessible basic and infrastructure services | To construct 8 graveyards fencing by 30 June 2016 | N/A | Graveyard fencing completed | Graveyard fencing(Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Graveyard fencing | Tshituni Mawoni,Madodonga,Hanani,Tshivhuyuni,Hlanganani,Tsianda,Ndouvhada,Vleifontein | Ward 35, 25, 1,12,8,27,32,20 | MIG | 2000000 | 2000000 |  | Evaluation, Adjudication and Appointment of Contractor. | Target achieved | Evaluation, Adjudication and Appointment of Contractor done | Insufficient budget for the project | Appoint within available budget | Advertisement copy, appointment letter,project progress report, handover report | TECH
79 | Building and Construction | Accessible basic and infrastructure services | To construct graveyard fencing by 30 June 2016 | N/A | Graveyard fencing completed | Fencing Vuwani Cemetery | Fencing Vuwani Cemetery | Vuwani | Ward 3 | Income | 300000 | 300000 |  | Advertisement for appointment of Contractors. | Target not achieved | Awaits evaluation | Slow SCM processes | Facilitate BEC meeting | Advertisement copy, appointment letter,project progress report, handover report | TECH
80 | Building and Construction | Accessible basic and infrastructure services | To construct Vuwani cemetery Ablution Facility 30 June 2016 | N/A | Vuwani cemetry Ablution Facility completed | Vuwani Cemetery ( Toilet ) | Vuwani Cemetry ( Toilet ) | Vuwani | Ward 3 | Income | 70000 | 70000 |  | Advertisement for appointment of Contractors. Evaluation, Adjudication and Appointment of Contractor. | Target not achieved | Awaits evaluation | Slow SCM processes | Facilitate BEC meeting | Advertisement copy, appointment letter,project progress report, handover report | TECH
81 | Building and Construction | Accessible basic and infrastructure services | To fence grave yard +sliding gate a by 30 June 2016 | N/A | Graveyard fencing completed | Fencing grave yard +sliding gate(Dzanani cemetery) | Fencing grave yard +sliding gate(Dzanani cemetery) | Dzanani township | Ward 35 | Income | 300000 | 300000 |  | Setting out and construction of fence Finalisation of the fence | Target not achieved | Contractor appointed | Contractor reluctant to start with the project due to under-pricing | Contractor to withdraw from the project | Advertisement copy, appointment letter,project progress report, handover report | TECH

## LMFMV
Indicator | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline (2015/2015) | Annual Targets ( | Project Name | Project Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End date | 3rd Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
82 | Revenue Management | Sound financial management and viability | To review the revenue enhancement policies by 30 June 2016 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed | Revenue enhancement policies review | Send the policies for inputs by other department. Present the draft review to management. Submit to council for approval. | Makhado Municipality |  | Income | Operational | Operational |  | 1/1/2016 | 30/6/2016 | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | N/A | N/A |  |  |  |  | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T
83 | Budget and Reporting | Sound financial management and viability | To table the draft budget to council by 31 March 2016 | Draft budget was tabled to council | Draft budget tabled to council | Draft budget | Collect budget from departments, Consolidate the budget, Present the draft to management, Submit to council for approval | Makhado Municipality |  | Income | Operational | Operational |  | 1/1/2016 | 31/3/2016 | Draft budget tabled to council | N/A | N/A |  |  |  |  | Draft budget and Council Resolution | B&T
84 | Budget and Reporting | Sound financial management and viability | To submit the final budget to council by 31 May 2016 | Final budget was submitted to council | Final budget submitted to council | Final budget | Take the draft budget for public participation with the IDP. Incorporate inputs and submit the budget for final approval | Makhado Municipality |  | Income | Operational | Operational |  | 1/4/2016 | 31/5/2016 | N/A | N/A | N/A |  |  |  |  | Final budget and Council Resolution | B&T
85 | Budget and Reporting | Sound financial management and viability | To submit the Financial statements submitted to AG by 31 August 2016 | Financial statements was compiled and submit to AG | Financial statements compiled and submit to AG | Financial statements | Compile the financial statement. Review the compiled financial statement. Present to management meeting. Submit to AG for auditing. | Makhado Municipality |  | Income | Operational | Operational |  | 1/7/2015 | 31/8/2015 | N/A | N/A | N/A |  |  |  |  | Copy of Financial statements | B&T
86 | Budget and Reporting | Sound financial management and viability | Number of section 71 reports submitted to Treasury within 10 days after the end of the month | 12 | 12 | Section 71 report submission | Compile the section 71 report. Submit to treasury within 10 days after month end. Submit to council for approval. | Makhado Municipality |  | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 3 | N/A | N/A |  |  |  |  | Copy of acknowledgement of receipt by Treasuries | B&T
87 | Supply Chain Management | Sound financial management and viability | % of tenders adjudicated within 90 days of closure period (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | Tender adjudication | Set date for adjudication committee. Adjudicate tenders within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality |  | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# tenders adjudicated/# of tenders closed and due for adjudication) | N/A | N/A |  |  |  |  | Monthly Tender Reports | B&T
88 | Supply Chain Management | Sound financial management and viability | % quotations processed within 18 days after approval by Accounting Officer (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | 100% (# of quotations processed/# of quotations received) | Quotations | Set date for quotation committee. Assess the quotation within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Makhado Municipality |  | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | 100% (# of quotations processed/# of quotations received) | N/A | N/A |  |  |  |  | Quotations Report | B&T
89 | Asset Management | Sound financial management and viability | To update a GRAP compliant Asset Register by 30 June 2016 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated | Asset Register | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Makhado Municipality | Ward 20 | Income | Operational | Operational |  | 1/7/2015 | 30/6/2016 | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | N/A | N/A |  |  |  |  | Schedules of Asset Register movement | B&T

## LLED
Indicator | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment budget | Expenditure | Start Date | End Date | 3rd Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.4. LOCAL ECONOMIC DEVELOPMENT (L0WER SDBIP)
90 | Local Economic Development | Invest in local economy | To develop Makhado information and recreational centre by 30 June 2015 | N/A | Development of Makhado information and recreational centre completed | Makhado N1 Information and Caravan Recreational/Entertainment centre | Advrtisement of the project. Evaluation and Adjudication, Appointment of a contractor. | Makhado Municipality | Ward 20 | Income | 500000 | 100000 |  | 01/01/2016 | 30/06/2016 | N/A | Evaluation and adjudication of the tender, Appointment of the contractor | Removed during budget adjustment | N/A | N/A | N/A | N/A | Specifications, Appointment letter (contrcator) | DEVP
91 | Local Economic Development | Invest in local economy | To host Makhado annual show by 30 September 2014 | Makhado annual show was hosted | Makhado annual show hosted | Annual Show | Identify the officials to serve Host Makhado annual show | Makhado Municipality | Ward 20 | Income | 159300 | 159300 |  | 1/7/2015 | 30/9/2015 | N/A | 168698.7 | 177 977.13.13 | N/A | N/A | N/A | N/A | Annual Show Report and Audited Financial Statements | DEVP
92 | Local Economic Development | Invest in local economy | # of LED projects supported 30th June 2014 | 9 | 10 | LED Strategy | Community works programme, Transnet/Furniture, Salaunavhe Poultry farm, Nthabalala Agriculture, Phaphama Agricultural, ,Mulima Pfananani, Kutama Clinic Greenery, Zamenkomste, Poultry, Vumatshelo Farming, Thirabeli Agricultural, Tshivhulani Community Garden | Makhado Municipality | All wards | Income | Operational | Operational |  | 1/7/2015 | 30/9/2016 | N/A | 100 | Project implementation plan, Project report | N/A | N/A | N/A | N/A | LED strategy implementation report | MM and DEVP

## LGGPP
Indicator | Priority Issue/Programme | Development Objective | Key Performance Indicators/Measurable Objective | Baseline | Annual Targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 15/16 R'000 | Adjustment Budget | Expenditure | Start Date | End date | 3rd Q Targets | 15/16 R'000 | 16/17 R'000 | Perfomance remarks | Actual perfomance | Challenges | Measures taken to improve/ proposed lintervention | Portfolio Of Evidence | Dept
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (LOWER SDBIP)
93 | Fraud and Anti - Corruption | Good governace and Administrative Excellence | % Fraud and Anti - Corruption cases attended by 30 June 2016 (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | 100% (# of cases attended/# of cases reported) | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 100% (# of cases attended/# of cases reported) | N/A | N/A |  | 100% (# of cases attended/# of cases reported) |  |  | Case Register | MM
94 | Public Participation | Good governace and Administrative Excellence | To develop the public participation policy by 31 March 2016 | No policy | Public Participatuion policy approved by Council | Public Participation Policy | Compile Public Participation Policy and submit to Council for approval | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 31/3/2016 | Submit the draft to council. Advertise the policy for public comment. |  |  |  | Submit the draft to council. Advertise the policy for public comment. |  |  | Approved policy Programmes and attendance register Final approve policy and advert for public comment | CORP
95 | Public Participation | Good governace and Administrative Excellence | To cordinate 456 ward committee meetings by 3o June 2016 | 456 | 456 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 38 wards | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. | 369,884 | 390,227 |  | Coordinate 114 ward committee meetings and submit quarterly ward committees' report to Council. |  |  | Minutes, Attendance register, Ward committee quarterly report | CORP
96 | Public Participation | Good governace and Administrative Excellence | To provide 2 trainings sessions for 38 ward committees by 30 June 2016 | 2 | 2 | Training of ward committees | Arrange and coordinate training event of all ward committees for at least 2 events | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | Approval of the memorandum by MM (2nd training) |  |  |  | Approval of the memorandum by MM (2nd training) |  |  | Training attendance register; training curriculum | CORP
97 | Policies and By Laws | Good governace and Administrative Excellence | To review 6 by laws by 30 June 2016 | 7 by laws reviewed | 4 by laws reviewed | Reviewing of Municipal By-laws | Review of the following by laws: Swimming pool, Pound, rationalise street trading, hawkers and markets into one bylaw. Street and diverse (public nuisance). | Makhado Municipality |  | Income | 1/7/2015 |  |  | 01/07/2015 | 30/06/2016 | Workshopping of Councillors and Public Participation on draft by laws | 900000 | 949000 | Target achieved | Workshopping of Councillors and Public Participation on draft by laws was held on 24 february 20 16 councilor briefing/ 9 March 2016 Dzanani/ 8 March 2016 Makahdo/ 1 March 2016 Ha Mutsha / 2 March Bungeni | Only challenge was in makhado nobody showup | None | 4 draft bylaws Provisional approved by Council , newspaper notice, attendance registers for public consultation, Final council resolutions and Promulgation notice for the 4 by laws in the provincial gazzete | CORP
98 | Internal Auditing | Good governace and Administrative Excellence | To develop the Internal Audit Charter, Audit and Performance Audit Charter and submit to council for approval by 30th June 2016 | Internal Audit Charter, Audit and Performance Audit Charter was developed and submitted to council for approval | Internal Audit Charter, Audit and Performance Audit Charter developed and submitted to council for approval | Internal Audit Charter | Develop the charter and submit to council for approval | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Council Resolution, Copy of the plan | MM
99 | Internal Auditing | Good governace and Administrative Excellence | To submit the three (3) year Internal Audit rolling plan and Annual plan to council for approval by 30 June 2016 | Three (3) year Internal Audit rolling plan and Annual plan was approved | Approved three (3) year Internal Audit rolling plan and Annual plan | Internal Audit 3 Year Plan | Develop the internal audit 3 year plan | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/4/2015 | 30/6/2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Copy of the plan | MM
100 | Internal Auditing | Good governace and Administrative Excellence | % implementation of the Approved Internal Audit Plan by 30th June 2016 (# of queries addressed/# of queries in the action plan) | 100% | 100% | Internal Audit Plan | Implementation of the Approved Internal Audit Plan | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 100% (# of projects executed/# of projects in the action plan) | N/A | N/A |  |  |  |  | Internal Audit report to Audit and Performance Audit Committee | MM
101 | Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee meetings held by 30 June 2016 | 7 | 7 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 1 | N/A | N/A |  |  |  |  | Minutes, Attendance register, invitations | MM
102 | Internal Auditing | Good governace and Administrative Excellence | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2015 | 4 | 4 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 1 | N/A | N/A |  |  |  |  | Council resolution, Attendance register | MM
103 | Internal Auditing | Good governace and Administrative Excellence | To submit the IAA and APAC Assessment report submitted to Council by 30 June 2016 | 2 | 2 | IAA and APAC Assessment report | Organize IAA and APAC Assessment report and submit to council | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | N/A | N/A | N/A |  |  |  |  | Report, Council Resolution | MM
104 | Information Technology | Good governace and Administrative Excellence | To upgrade the municipal call center by 30 June 2016 | Manual system | Computerized call center system | Upgrade municipal call center | Upgrade municipal call center from manual system to computerized logging, recording and referencing system and audio recording system according to needs of business units Phase 1 2015/2016 - the logging and referencing system Phase 2 - Audio recording system for 2016/2017 | Civic Center |  | Income | R3000,000 | 0 |  | 1/7/2015 | 31/3/2016 | Municipal call centre adjusted to 16/17 |  |  | Municipal call centre adjusted to 16/17 | Municipal call centre adjusted to 16/17 | Municipal call centre adjusted to 16/17 | Municipal call centre adjusted to 16/17 | Advertisement for RFP | CORP
105 | Information Technology | Good governace and Administrative Excellence | To complete upgrade of network infrastructure by 31 december 2015 | Phase 1 done | Complete network upgrades | Upgrade network infrastructure | Increase speed of server output to networks for data transfer between workstations and servers | Civic Center and regional offices |  | Income | R200,000 | 159226 |  | 1/7/2015 | 31/3/2016 | N/A |  |  | N/A | N/A | N/A | N/A | Orders, Payment certificate and intallation report | CORP
106 | Information Technology | Good governace and Administrative Excellence | To complete upgrade of server upgrade project 31 December 2015 | Phase 1 done | Complete server upgrade project | Upgrade of servers | Complete upgrade of servers - expansion of data centre server | Civic Center |  | income | R200,000 | 148958 |  | 1/7/2015 | 31/3/2016 | N/A |  |  | N/A | N/A | N/A | N/A | Appointment letter, Project agreement, installation report and payment certicate | CORP
107 | Information Technology | Good governace and Administrative Excellence | To upgrade the internet dataline by 31 March 2016 | Existing dataline too slow | Internet dataline upgraded | Internet dataline upgrade | Upgarde the internet dataline to optimise speed for offsite backups and internet use. (Changed from Upgrade of TMS) | Civic center |  | Income | R150,000 | R150,000 |  | 1/7/2015 | 31/3/2016 | TELKOM complete the upgarde and payment out |  |  | Target achieved | TELKOM complete the upgarde and payment out done Installed, commissioned and tested in February 2016 | None | None | Approved memorandum, TELKOM agrement, Close out report, Proof of payment | CORP
108 | Information Technology | Good governace and Administrative Excellence | To upgrade the server room to acceptable standards by 31 December 2015 | Unacceptable standard of server room | Acceptable server room conditions | Replace UPS in server room | Upgrade of server room by removing carpets and workstation equipment | Civic Center |  | Income | R70,000 | 161816 |  | 1/7/2015 | 31/3/2016 | Signing off, sign service mantainance plan |  |  | Target achieved | Signing off, sign service mantainance plan completed | None | None | Approved memorandumpurchase order, signed service mantainance plan | CORP
109 | Information Technology | Good governace and Administrative Excellence | To procure video editing software by 31 December 2015 | N/A | Procure video editing software | Procure video editing software | Procure Video Editing software suitable for use by business process owner | Civic Center |  | Income | R10,000 | 14500 |  | 1/7/2015 | 2015-01-12 | N/A |  |  | N/A | N/A | N/A | N/A | Appointment letter, Installation, report; payment certificates, | CORP
110 | Information Technology | Good governace and Administrative Excellence | To procure ICT office equipment 31 March 2016 | 2014/15 critical needs only | According to needs analysis | Procure ICT office equipment | Procure laptops, computers, printers and desktops according to accurate needs analysis | Civic Center |  | Income | R200,000 | 155500 |  | 1/7/2015 | 31/12/2015 | Receive ordered equipments and allocate to users |  |  | Target not achieved | Receive ordered equipments and allocate to users | Quotation Committee not yet signed off - awaiting to sign off in April 2016 | Document signed on 12 April 2016 | Appointment letter, Orders, payment certificates and Asset Register | CORP
111 | Information Technology | Good governace and Administrative Excellence | To procure hand held communication radios 30 September 2015 | N/A | 2 | Hand held communication radios | Procure two (2) hand held communication radios for registry staff to communicate | Civic Center |  | Income | R10,000 | R10,000 |  | 1/7/2015 | 30/9/2015 | N/A |  |  | Target not achieved | Radios delivered last week in March 2016 but not yet installed and commissioned Installation in Q4 | Service Provider did not know how to program radios and delay caused | N/A | Appointment letter, payment certificates, | CORP
112 | Council Services | Good governace and Administrative Excellence | # of Council meeting convened by 30 June 2016 | 15 | 6 | Council meeting | Organize Council meeting as per schedule | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 2 | Operational | Operational | Target achieved | 5 council meeting were held | None | None | Minutes, Attendance register, notice of invitations. | CORP
113 | Council Services | Good governace and Administrative Excellence | # of Executive Committee Meetings convened by 30 June 2016 | 25 | 24 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 6 | Operational | Operational | Target achieved | 8 Executive Committee Meetings were held | None | None | Minutes, Attendance register, notice of invitations. | CORP
114 | Communication | Good governace and Administrative Excellence | To procure 2 x television sets by 30 September 2016 | N/A | 2 | Television sets | Procure and install television sets in the Office of the Speaker and the Office of the Chief Whip | Civic Center |  | Income | R20,000.00 | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | TVs and payment certificates | CORP
115 | Communication | Good governace and Administrative Excellence | To procure 2 X decoders by 30 September 2016 | N/A | 2 | Decoders | Procure and install decoders for DSTV in the Office of the Speaker and the Office of the Chief Whip | Civic Center |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Decoders and payment certificates | CORP
116 | Communication | Good governace and Administrative Excellence | To procure 2 X radios of regional broadcasting stations BY 30 June 2016 | N/A | 2 | Radios | Procure radios for regional broadcasting services that also have a recording function | Civic Center |  | Income | R800.00 | 2656 |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Radios and payment certificates | CORP
117 | Communication | Good governace and Administrative Excellence | To review the Reviewed BathoPele Service Standards by 31 December 2016 | 1 | Reviewed BathoPele Service Standards | Reviewed Bathopele service standards | Review the 2014/15 ed Makhado Bathopele Service Standards and submit to Council for approval | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | N/A | N/A |  | N/A | N/A | N/A | N/A | Approved 2015 Batho Pele Service Standards | CORP
118 | Communication | Good governace and Administrative Excellence | To develop a comprehensive website policy by 31 December 2016 | N/A | Council approved website policy | Comprehensive website policy | Develop website policy for approval by Council | Civic Center |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Council approval of policy | CORP
119 | Public Participation | Good governace and Administrative Excellence | # of imbizos convened by 30 June 2016 | 4 | 4 | Public Participation | Consult members of the public on service delivery issues | Makhado Municipality |  | Income | OPEX | OPEX |  | 1/7/2015 | 30/6/2016 | 1 | N/A | N/A | Target achieved | 1 imbizos convened on the 19 February 2016 at Mashau Village. | None | None | Attendance register and Programme | CORP
120 | Public Participation | Good governace and Administrative Excellence | # of imbizo feedback session convened by 30 June 2016 | 1 | 1 | Imbizo Feedback Session | Giving Feedback to community on service delivery issues raised during 2014/2015 financial year | Makhado Municipality | All wards | Income | OPEX | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Attendance register and program | CORP
121 | Public Participation | Good governace and Administrative Excellence | To review Makhado Stakeholders Management Framework BY 30 September 2016 | Stakeholders Management Framework | Stakeholders Management Framework reviewed | Review of Stakeholders Management Framework | Makhado Municipality | Income | Ward 20 | Income | OPEX | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Approved Stakeholders management Framework and council resolution | CORP
122 | Public Participation | Good governace and Administrative Excellence | To review Makhado Communications Strategy by 30 September 2016 | Communication Strategy | Communication Strategy reviewed | Review of Communication Strategy | Makhado Municipality | Income | Ward 20 | Income | OPEX | OPEX |  | 1/7/2015 | 30/9/2015 | N/A |  |  | N/A | N/A | N/A | N/A | Approved Communication strategy and council resolution policy and council resolution | CORP

## MRE
LIM344 Makhado - Budget Year 2014/15
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Revenue By Source
Property rates |  | 3673557.72 | 3680000 | 3742000 | 3630000 | 3945000 | 3845000 | 3512000 | 3412000 | 3658000 | 3223000 | 3460000 | 3861307.7461 | 43641865.4661 | 46693269.4319 | 49119040.5726
Property rates - penalties & collection charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - electricity revenue |  | 24071766.17 | 21432000 | 22490000 | 25600000 | 24758000 | 26456000 | 23071766.17 | 22458700 | 24560000 | 25607000 | 24880000 | 23475961.48 | 288861193.82 | 324101869.02 | 363641872.85
Service charges - water revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - sanitation revenue |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - refuse revenue |  | 818509.38 | 852000 | 812566 | 827000 | 812333 | 818000.38 | 800000.38 | 817000 | 813000 | 814000 | 820000 | 719482.2548 | 9723891.3948 | 10403778.0048 | 10944266.7264
Service charges - other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment |  | 37811.83 | 31000 | 33800 | 37450 | 31000 | 37811.83 | 33000 | 33000 | 34000 | 32900 | 37811.83 | 69618.9118 | 449204.4018 | 480612.4406 | 505580.8158
Interest earned - external investments |  | 276512.41 | 267000 | 288000 | 208000 | 267000.41 | 233000.41 | 254800 | 254000 | 247000 | 245088 | 284500 | 460066.2008 | 3284967.4308 | 3514649.6884 | 3697239.9442
Interest earned - outstanding debtors |  | 1098700 | 1008500.01 | 1058700 | 1021500 | 1050000 | 1087100 | 1040890 | 1008500.01 | 1018500.01 | 880000 | 960001 | 748589.0393 | 11980980.0693 | 12818680.5103 | 13484626.2802
Dividends received |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines |  | 138112.65 | 235000 | 148700 | 162000 | 125800 | 125487 | 104500 | 134560 | 148700 | 139112 | 138112.65 | 40693.9127 | 1640778.2127 | 1755500.0943 | 1846700.4207
Licences and permits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agency services |  | 947025.57 | 888000 | 935020 | 900450 | 988002 | 945000 | 780000 | 880555 | 947025.57 | 808000 | 947025.57 | 1284559.9626 | 11250663.6726 | 12037301.0045 | 12662653.1665
Transfers recognised - operational |  | 120000000 | 11600000 | 5000000 | 1920000 | 144000000 | 0 | 0 | 0 | 72490000 | 0 | 0 | 8586000 | 363596000 | 368360000 | 366556000
Other revenue |  | 2540000 | 1800900 | 1013000 | 1374000 | 1450000 | 1178665.19 | 1180000 | 1245000 | 2470000 | 1478090 | 2750000 | -1317953.36 | 17161701.83 | 23652834.42 | 24437350.55
Gains on disposal of PPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue (excluding capital transfers and contributions) |  | 153601995.73 | 41794400.01 | 35521786 | 35680400 | 177427135.41 | 34726064.81 | 30776956.55 | 30243315.01 | 106386225.58 | 33227190 | 34277451.05 | 37928326.1481 | 751591246.2981 | 803818494.6147 | 846895331.3264
Expenditure By Type
Employee related costs |  | 18450000 | 18950000 | 18650000 | 18880000 | 18450000 | 32074000 | 18950000 | 18990000 | 18780000 | 18990000 | 18780000 | 21233438.3 | 241177438.3 | 254442197.44 | 267927633.86
Remuneration of councillors |  | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1559609.73 | 22610107 | 23944103 | 25284973
Debt impairment |  | Budget Year 2014/15 June: 10000000 | 10000000 | 10550000 | 11109150
Depreciation & asset impairment |  | Budget Year 2014/15 June: 153426319.32 | 153426319.32 | 161864766.86 | 170443599.52
Finance charges |  | 542000 | 522450.54 | 520286.54 | 534000 | 567000 | 588000 | 521000 | 532000 | 519000 | 520286.54 | 520286.54 | 294693.9451 | 6181004.1051 | 6613174.9204 | 6956737.2584
Bulk purchases |  | 18078244.34 | 18178000.34 | 18757000.34 | 17654000 | 16000000 | 16800000 | 17870000 | 18978244.34 | 19078244.34 | 17078888.34 | 19078067.34 | 19388242.9 | 216938932.28 | 247831036.2 | 283122175.81
Other materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other expenditure |  | 14362465.24 | 14150000 | 11780007 | 14508780 | 11458700 | 11420000 | 14345600 | 14362111 | 14300000.24 | 14362465.24 | 11120000.24 | 38625885.9515 | 184796014.9115 | 187462607.21 | 197656659.4415
Loss on disposal of PPE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenditure |  | 53346391.15 | 53714132.45 | 51620975.45 | 53490461.57 | 48389381.57 | 62795681.57 | 53600281.57 | 54776036.91 | 54590926.15 | 52865321.69 | 51412035.69 | 244528190.1466 | 835129815.9166 | 892707885.6305 | 962500928.8899
Surplus/(Deficit) |  | 100255604.58 | -11919732.44 | -16099189.45 | -17810061.57 | 129037753.84 | -28069616.76 | -22823325.02 | -24532721.9 | 51795299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | -83538569.6185 | -88889391.0158 | -115605597.5635
Transfers recognised - capital |  | 0 | 0 | 0 | 4590000 | 43609000 | 5780000 | 1190000 | 0 | 74095000 | 0 | 0 | 0 | 129264000 | 136892000 | 143831000
Contributions recognised - capital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contributed assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surplus/(Deficit) after capital transfers & contributions |  | 100255604.58 | -11919732.44 | -16099189.45 | -13220061.57 | 172646753.84 | -22289616.76 | -21633325.02 | -24532721.9 | 125890299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | 45725430.3815 | 48002608.9842 | 28225402.4365
Taxation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attributable to minorities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surplus/(Deficit) | 1 | 100255604.58 | -11919732.44 | -16099189.45 | -13220061.57 | 172646753.84 | -22289616.76 | -21633325.02 | -24532721.9 | 125890299.43 | -19638131.69 | -17134584.64 | -206599863.9985 | 45725430.3815 | 48002608.9842 | 28225402.4365

## MREBV
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Revenue by Vote
Vote 1 - EXECUTIVE AND COUNCIL |  | 38956700 | 38908000 | 38908000 | 36978000 | 39067000 | 39890000 | 38078000 | 39112000 | 38867300 | 39050400 | 39050400 | 41739367.21 | 468605167.21 | 485863021.7 | 490454136.4
Vote 2 - WASTE MANAGEMENT |  | 450000 | 470000 | 610000 | 650000 | 655000 | 553000 | 557800 | 556000 | 520000 | 510000 | 513000 | 632510.02 | 6677310.02 | 5636338.37 | 5935296.93
Vote 3 - ROAD TRANSPORT |  | 998000 | 994000 | 950000 | 990000 | 1100000 | 1007000 | 1209800 | 1220000 | 1250000 | 1290000 | 1085000 | 923294 | 13017094 | 13733034.18 | 14460884.96
Vote 4 - WATER |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | 26789000 | 25785600 | 24560900 | 24112000 | 23456700 | 25489000 | 24345000 | 25489000 | 25008000 | 25602300 | 26908000 | 28320378.27 | 305865878.27 | 344107515.42 | 383648632.32
Vote 6 - CORPORATE SERVICES |  | 3909800 | 3921100 | 4825000 | 4709800 | 4712300 | 3867000 | 4175000 | 4189000 | 4170000 | 4187000 | 4186000 | 3218441.76 | 50070441.76 | 52824316.04 | 55624004.81
Vote 7 - PLANNING AND DEVELOPMENT |  | 10000 | 20000 | 30000 | 40000 | 41000 | 43000 | 44000 | 46000 | 47000 | 56000 | 57000 | 56926.51 | 490926.51 | 517927.46 | 545377.61
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | 7000 | 5000 | 7000 | 7000 | 8000 | 9000 | 10000 | 8000 | 8000 | 6000 | 7000 | 9585.47 | 91585.47 | 96622.66 | 101743.67
Vote 9 - HOUSING |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 591.61 | 55591.61 | 58649.16 | 61757.56
Vote 10 - OTHER |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION |  | 5000 | 8000 | 6000 | 8000 | 7000 | 8000 | 6000 | 8000 | 7000 | 8000 | 6000 | 7094.18 | 84094.18 | 88719.38 | 93421.5
Vote 12 - BUDGET AND TREASURY |  | 2890000 | 2720000 | 2691000 | 2799000 | 2891000 | 2946000 | 2965000 | 2978000 | 2989000 | 3130000 | 3590000 | 3308157.29 | 35897157.29 | 37784350.92 | 39801075.5
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Total Revenue by Vote |  | 74020500 | 33928700 | 72592900 | 70298800 | 71943000 | 73817000 | 71395600 | 73611000 | 72871300 | 73844700 | 75407400 | 78216346.32 | 880855246.32 | 940710495.29 | 990726331.26
Expenditure by Vote to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL |  |  | 10000000 | 5000000 | 1920000 |  | 0 | 0 | 0 | 76076000 | 0 | 0 | 12775721.33 | 105771721.33 | 104679593.11 | 109734952.2
Vote 2 - WASTE MANAGEMENT |  | 818509.38 | 852000 | 812566 | 827000 | 812333 | 818000.38 | 800000.38 | 817000 | 813000 | 814000 | 820000 | 13630577.92 | 22634987.06 | 23879911.34 | 25145546.65
Vote 3 - ROAD TRANSPORT |  | Budget Year 2014/15 June: 25228755.48 | 25228755.48 | 26616336.99 | 28027002.87
Vote 4 - WATER |  | Budget Year 2014/15 June: 19079906.12 | 19079906.12 | 20129300.97 | 21196153.92
Vote 5 - ELECTRICITY |  | 24071766.17 | 21432000 | 22490000 | 25600000 | 24758000 | 26456000 | 23071766.17 | 22458700 | 24560000 | 25607000 | 24880000 | 5429955.24 | 270815187.58 | 304670485.66 | 342974115.91
Vote 6 - CORPORATE SERVICES |  | 3673557.72 | 3680000 | 3042000 | 3630000 | 3945000 | 3045000 | 3512000 | 3412000 | 3658000 | 3223000 | 3460000 | 1150468.46 | 39431026.18 | 41599732.58 | 43804518.43
Vote 7 - PLANNING AND DEVELOPMENT |  | 4194000 | 4257000 | 4179000 | 4420000 | 4187000 | 4003200 | 4500000 | 4890000 | 5609700 | 5123340 | 2578000 | 2395828.79 | 50337068.79 | 52700607.57 | 56309289.76
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | Budget Year 2014/15 June: 7486816.63 | 7486816.63 | 7898591.57 | 8317216.91
Vote 9 - HOUSING |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 10 - OTHER |  | 2540000 | 1800900 | 5000000 | 1374000 | 1450000 | 1178665.19 | 1180000 | 1245000 | 2470000 | 1478090 | 2750000 | 4928080.93 | 27394736.12 | 28901446.62 | 30433223.28
Vote 11 - SPORTS AND RECREATION |  | 1469000 | 1645000 | 1783000 | 1648000 | 1796400 | 1384500 | 1870000 | 1802600 | 132600 | 1750300 | 131450 | 2219313.25 | 17632163.25 | 18601932.24 | 19587834.63
Vote 12 - BUDGET AND TREASURY |  | 120000000 | 11600000 | 5000000 | 1920000 |  | 0 | 0 | 0 | 76076000 | 0 | 0 | 34721447.57 | 249317447.57 | 263029947.19 | 276971074.38
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Total Expenditure by Vote |  | 156766833.27 | 55266900 | 47306566 | 41339000 | 36948733 | 36885365.57 | 34933766.55 | 34625300 | 189395300 | 37995730 | 34619450 | 129046871.72 | 835129816.11 | 892707885.84 | 962500928.94
Surplus/(Deficit) before assoc. |  | -82746333.27 | -21338200 | 25286334 | 28959800 | 34994267 | 36931634.43 | 36461833.45 | 38985700 | -116524000 | 35848970 | 40787950 | -50830525.4 | 45725430.21 | 48002609.45 | 28225402.32
Taxation |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Attributable to minorities |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Share of surplus/ (deficit) of associate |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Surplus/(Deficit) | 1 | -82746333.27 | -21338200 | 25286334 | 28959800 | 34994267 | 36931634.43 | 36461833.45 | 38985700 | -116524000 | 35848970 | 40787950 | -50830525.4 | 45725430.21 | 48002609.45 | 28225402.32

## CAP CASHFLOW
LIM344 Makhado - Supporting Table SA30 Budgeted monthly cash flow
MONTHLY CASH FLOWS | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Cash Receipts By Source | [12 empty] | 1
Property rates | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3673557.72 | 3232865.08 | 43642000 | 46693000 | 49119000
Property rates - penalties & collection charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - electricity revenue | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071766.17 | 24071765.95 | 288861193.82 | 324101869.02 | 363641872.85
Service charges - water revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - sanitation revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service charges - refuse revenue | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 818509.38 | 720396.82 | 9724000 | 10404000 | 10944000
Service charges - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental of facilities and equipment | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 37811.83 | 33069.87 | 449000 | 481000 | 506000
Interest earned - external investments | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 276512.41 | 243363.49 | 3285000 | 3515000 | 3697000
Interest earned - outstanding debtors | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 1008500.01 | 887499.89 | 11981000 | 12819000 | 13485000
Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fines | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 138112.65 | 121760.85 | 1641000 | 1756000 | 1847000
Licences and permits | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 947025.57 | 833718.73 | 11251000 | 12037000 | 12663000
Agency services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfer receipts - operational | 120000000 | 11600000 | 5000000 | 1920000 | 144000000 | 0 | 0 | 0 | 72490000 | 0 | 0 | 5000000 | 360010000 | 369813000 | 367641000
Other revenue | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1536958.92 | 20748000 | 22199000 | 23353000
Cash Receipts by Source | 152718254.02 | 44318254.02 | 37718254.02 | 34638254.02 | 176718254.02 | 32718254.02 | 32718254.02 | 32718254.02 | 105208254.02 | 32718254.02 | 32718254.02 | 36681399.6 | 751592193.82 | 803818869.02 | 846896872.85
Other Cash Flows by Source
Transfer receipts - capital | 0 | 0 | 0 | 4590000 | 43609000 | 5780000 | 1190000 | 0 | 74095000 | 0 | 0 | 0 | 129264000 | 136892000 | 143831000
Contributions recognised - capital & Contributed assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proceeds on disposal of PPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Short term loans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Borrowing long term/refinancing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase (decrease) in consumer deposits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (Increase) in non-current debtors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) other non-current receivables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease (increase) in non-current investments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cash Receipts by Source | 152718254.02 | 44318254.02 | 37718254.02 | 39228254.02 | 220327254.02 | 38498254.02 | 33908254.02 | 32718254.02 | 179303254.02 | 32718254.02 | 32718254.02 | 36681399.6 | 880856193.82 | 940710869.02 | 990727872.85
Cash Payments by Type
Employee related costs | 18450000 | 18950000 | 18650000 | 18880000 | 18450000 | 32074000 | 18950000 | 18990000 | 18780000 | 18990000 | 18780000 | 21233438.3 | 241177438.3 | 254442197.44 | 267927633.86
Remuneration of councillors | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1913681.57 | 1559609.73 | 22610107 | 23944103 | 25284973
Finance charges | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 520286.54 | 457848.06 | 6181000 | 6613000 | 6957000
Bulk purchases - Electricity | 18078244.34 | 18178000.34 | 18757000.34 | 17654000 | 16000000 | 16800000 | 17870000 | 18978244.34 | 19078244.34 | 17078888.34 | 19078067.34 | 19388242.9 | 216938932.28 | 247831036.2 | 283122175.81
Bulk purchases - Water & Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants - other municipalities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transfers and grants - other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other expenditure | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 1746458.28 | 165584973.8315 | 184796014.9115 | 187462607.21 | 197656659.4415
Cash Payments by Type | 40708670.73 | 41308426.73 | 41587426.73 | 40714426.39 | 38630426.39 | 53054426.39 | 41000426.39 | 42148670.73 | 42038670.73 | 40249314.73 | 42038493.73 | 208224112.8215 | 671703492.4915 | 720292943.85 | 780948442.1115
Other Cash Flows/Payments by Type
Capital assets | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 13874400 | 11319600 | 163938000 | 204440000 | 192200000
Repayment of borrowing | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 1800000 | 1900000 | 2000000
Other Cash Flows/Payments | Budget Year 2014/15 May: 36000000; Budget Year 2014/15 June: 0 | 36000000 | 15000000 | 10000000
Total Cash Payments by Type | 54583070.73 | 55182826.73 | 55461826.73 | 55488826.39 | 52504826.39 | 66928826.39 | 54874826.39 | 56023070.73 | 56813070.73 | 54123714.73 | 91912893.73 | 219543712.8215 | 873441492.4915 | 941632943.85 | 985148442.1115
NET INCREASE/(DECREASE) IN CASH HELD | 98135183.29 | -10864572.71 | -17743572.71 | -16260572.37 | 167822427.63 | -28430572.37 | -20966572.37 | -23304816.71 | 122490183.29 | -21405460.71 | -59194639.71 | -182862313.2215 | 7414701.3285 | -922074.83 | 5579430.7385
Cash/cash equivalents at the month/year begin: | 5000000 | 103135183.29 | 92270610.58 | 74527037.87 | 58266465.5 | 226088893.13 | 197658320.76 | 176691748.39 | 153386931.68 | 275877114.97 | 254471654.26 | 195277014.55 | 5000000 | 12414701.3285 | 11492626.4985
Cash/cash equivalents at the month/year end: | 103135183.29 | 92270610.58 | 74527037.87 | 58266465.5 | 226088893.13 | 197658320.76 | 176691748.39 | 153386931.68 | 275877114.97 | 254471654.26 | 195277014.55 | 12414701.3285 | 12414701.3285 | 11492626.4985 | 17072057.237

## CAP BV
LIM344 Makhado - Supporting Table SA28 Budgeted monthly capital expenditure (municipal vote)
Description | Ref | Budget Year 2014/15 | [11 empty] | Medium Term Revenue and Expenditure Framework
R thousand |  | July | August | Sept. | October | Nov. | Dec. | January | Feb. | March | April | May | June | Budget Year 2014/15 | Budget Year +1 2015/16 | Budget Year +2 2016/17
Multi-year expenditure to be appropriated | 1
Vote 1 - EXECUTIVE AND COUNCIL |  | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8971000 | 8975000 | 107656000 | 153694000 | 137424000
Vote 2 - WASTE MANAGEMENT |  | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 442000 | 438000 | 5300000 | 6000000 | 6400000
Vote 3 - ROAD TRANSPORT |  | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 119000 | 121000 | 1430000 | 1472900 | 1456127
Vote 4 - WATER |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1782000 | 1781000 | 21383000 | 32909471 | 35335190
Vote 6 - CORPORATE SERVICES |  | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4500000 | 4635000 | 4774050
Vote 7 - PLANNING AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575000 | 2575000 | 2729000 | 2811000
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 9 - HOUSING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 10 - OTHER |  | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 592000 | 588000 | 7100000 | 3000000 | 4000000
Vote 11 - SPORTS AND RECREATION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY |  | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1166000 | 1168000 | 13994000 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Capital multi-year expenditure sub-total | 2 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 16021000 | 163938000 | 204440371 | 192200367
Single-year expenditure to be appropriated
Vote 1 - EXECUTIVE AND COUNCIL |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 2 - WASTE MANAGEMENT |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 3 - ROAD TRANSPORT |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 4 - WATER |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 5 - ELECTRICITY |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 6 - CORPORATE SERVICES |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 7 - PLANNING AND DEVELOPMENT |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 8 - COMMUNITY AND SOCIAL SERVICES |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 9 - HOUSING |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 10 - OTHER |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 11 - SPORTS AND RECREATION |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Vote 12 - BUDGET AND TREASURY |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
- |  | Budget Year 2014/15 June: 0 | 0 | 0 | 0
Capital single-year expenditure sub-total | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital Expenditure | 2 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 13447000 | 16021000 | 163938000 | 204440371 | 192200367

## APPROVAL
10. APPROVAL BY THE MAYOR
Section 54 (1)(c) of MFMA states that 54. (1) On receipt of a statement or report submitted by the accounting officer of the municipality in terms of section 71 or 72, the mayor must— (a) consider the statement or report; (b) check whether the municipality’s approved budget is implemented in accordance with the service delivery and budget implementation plan; (c) consider and, if necessary, make any revisions to the service delivery and budget implementation plan, provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustments budget; (d) issue any appropriate instructions to the accounting officer to ensure— (i) that the budget is implemented in accordance with the service delivery and budget implementation plan; and (ii) that spending of funds and revenue collection proceed in accordance with the budget; (e) identify any financial problems facing the municipality, including any emerging or impending financial problems; and (f) in the case of a section 72 report, submit the report to the council by 31 January of each year.
Recommendation by The Municipal Manager: The Municipal Manager hereby recommend for the approval of the Adjusted SDBIP by Council via the Mayor in line with section 54 (1) (c) ___________________________ _____________________ Mutshinyali I.P DATE Municipal Manager
Approval by the Mayor The Adjusted SDBIP 2015/2016 is hereby submitted to Council by the Mayor for Approval ______________________________ ____________________ Hon Cllr Mutavhatsindi F. D DATE